[image: image1.jpg]


[image: image79.jpg]


[image: image80.jpg]




[image: image157.jpg]



2025 NAERPM PROCEEDINGS
 





HELD AT

NATIONAL AGRICULTURAL EXTENSION AND RESEARCH LIAISON SERVICES

AHMADU BELLO UNIVERSITY, ZARIA

                                 DECEMBER, 2025

TABLE OF CONTENTS

Preliminary Pages Keynote Address VCs Speech Director Speech

ARCN Special Message 

2025 APS Executive Summary

 2025 Reports Presentation

NARIs ADP

2026 Workplan NARIs

ADPs

PRELIMINARY PAGES

Pictures

President of FGN

Ministers of Agriculture (Main & State) Vice Chancellor, ABU

Director, NAERLS

Deputy Director, NAERLS

Assistant Director, ET&O, NAERLS Assistant Director, RPM&E – NAERLS

LOC

Names of LOC & Sub-Committees

  PRELIMINARY PAGES

[image: image2.jpg]



ASIWAJU AHMED BOLA TINUBU 

PRESIDENT, COMMANDER-IN-CHIEF OF THE ARMED FORCES FEDERAL REPUBLIC OF NIGERIA

[image: image3.jpg]



SENATOR ABUBAKAR KYARI (CON)

MINISTER OF AGRICULTURE
    FEDERAL MINISTER OF AGRICULTURE AND FOOD SECURITY

[image: image4.png]



SENATOR (DR.) ALIYU SABI ABDULLAHI 

MINISTER OF STATE

FEDERAL MINISTRY OF AGRICULTURE AND FOOD SECURITY

[image: image5.jpg]



PROFESSOR ADAMU AHMED

VICE CHANCELLOR AHMADU BELLO UNIVERSITY, ZARIA

[image: image6.jpg]



PROFESSOR YUSUF AHMAD SANI

EXECUTIVE DIRECTOR

NATIONAL AGRICULTURAL EXTENSION AND RESEARCH LIAISON SERVICES

[image: image7.jpg]



PROFESSOR MUHAMMAD M. JALIYA

DEPUTY DIRECTOR

NATIONAL AGRICULTURAL EXTENSION AND RESEARCH LIAISON SERVICES

[image: image8.jpg]



PROFESSOR A. A JAMILU
ASSISTANT DIRECTOR-EXTENSION, TRAINING AND OUTREACH 

NATIONAL AGRICULTURAL EXTENSION AND RESEARCH LIAISON SERVICES

                [image: image9.jpg]()




                  PROFESSOR ADETUNJI OROYE IYIOLA - TUNJI
ASSISTANT DIRECTOR-RESEARCH, PLANNING, MONITORING AND EXTENSION

NATIONAL AGRICULTURAL EXTENSION AND RESEARCH LIAISON SERVICES

ORGANIZING COMMITTEE

	S/N
	SUB-COMMITTEES
	NAME
	TOR

	1
	IN-HOUSE
	Prof. S H Kura
	Coordinate the conduct of In-house review

Ensure the reporting template for NAER&PM is intact and updated

Come up with word and power-point version of the institute’s 2025 report and 2026 work plan

	
	
	Dr. Bashir Bawuro
	

	
	
	Dr. Perpetual Orji
	

	
	
	Abdulshakur Mahmud
	

	2
	SPEECH AND PROCEEDING
	Prof. S Yunusa
	Identify the 2025 theme for the event and propose keynote speaker

Write VC’s and ED’s speech

Compile Proceedings and facilitate its publication

	
	
	Dr. Izzaddeen Saleh
	

	
	
	Dr. Adams Tijjani
	

	
	
	Adejoh, E. U
	

	3
	SECURITY
	Mohmmed D.Bawa
Ambi Ambo
	Ensure the security situation during the event

Ensure the security of hotels within ABU where guests would be lodged

	4
	TRANSPORT
	Dr T.O. Olanrewaju
	Coordinate the movement of guests from NAERLS to accommodation and vice versa.

	
	
	Dr.Yusuf A.A
	

	5
	PUBLICITY
	Dr. Abu Anamomeh
	Publicize the event through existing platforms of the institute (website, Facebook, IG, Twitter etc.)

Monitor online registration of guests

	
	
	P. G. Maiyaki
Halifat Momodu
	

	6
	MEALS AND REFRESHMENT
	Amina Baidu
	Handle affairs of refreshment and meals during the event

	
	
	Aisha Aliyu Muhammad
	

	
	
	Fatima Zahra Idris
Jamilu Jibrin Adam
	

	7
	HOTELS AND ACCOMMODATION
	Prof. Ali. Abdulrahman
	Work alongside Security committee to identify safe accommodation with price rates for guests

	
	
	Muhammad Kabir
	

	8
	VIRTUAL
	Prof Sani Usman
	Manage and handle the virtual processes of guests attending the event online

	
	
	Muhammad Tijjani
	

	
	
	Muhammad Amin Umar
	

	
	
	Aminu Khalid
	

	
	
	
	

	
	
	
	

	9
	EXHIBITION
	Prof Adamu Yakubu
	Coordinate the conduct of exhibition which includes invitation and registration of exhibitors both within and outside the institute

	
	
	Ibrahim Muazu
	

	
	
	Umar Aliyu
	

	10
	SECRETARIAT
	Dr. Muhammad I. Hudu
	Work closely with all sub-committees

Handle all logistics issues (budget, hotel billings, feeding etc.)

Work on and send invitations to all stakeholders

	
	
	Abubakar Rabiu Garba
	

	
	
	Aisha Asst Sec Inst
	

	
	
	Musa Yusuf
	


OPENING CEREMONY
Innovative Solutions for Sustainable Agricultural Extension in Nigeria: Addressing Climate Change, Digital Gaps, and Gender Equity

By
Dr Godwin Atser

Country Director, Sasakawa Africa association (SAA)

Nigeria Innovative solutions for sustainable agricultural extension in Nigeria must address the interconnected challenges of climate change, digital gaps, low productivity, and gender inequity. Agriculture continues to play a crucial role in Nigeria’s economy, yet budgetary allocations and investments in agricultural extension remain inadequate. Rural poverty persists, with many households living below the international poverty line. African food systems are further constrained by relatively low crop yields compared to other regions, where production gains are driven primarily by intensification rather than land expansion. Low productivity traps many Nigerian farmers in cycles of poverty, leaving them where Indian farmers were in the early 1970s. The impacts of climate change—including rising global temperatures, extreme heatwaves, flooding, droughts, pest outbreaks such as the Fall Armyworm, and widespread land degradation—continue to undermine food production and the livelihoods of smallholder farmers across the country. 

The Sasakawa Africa Association (SAA), founded in 1986 through the vision of Norman Borlaug, Jimmy Carter, and Ryōichi Sasakawa, has long focused on demonstrating improved agricultural technologies to farmers and extension agents. Its mission is to support African smallholder farmers in strengthening food, nutrition, and income security by catalyzing technological innovation. In Nigeria, SAA’s work spans regenerative agriculture, nutrition-sensitive agriculture, market-oriented agriculture, capacity building, digitalization, and inclusion of women, youth, and persons with disabilities. Through regenerative agriculture, SAA aims to restore soil health, enhance biodiversity, and build climate resilience. An example of this commitment is the evidence-based regenerative agriculture project in Ethiopia and Nigeria, which targets a 40–60% increase in productivity and a 30% improvement in farmer livelihoods. Additionally, SAA promotes environmentally friendly irrigation systems such as solar-powered water pumps, which reduce energy costs and emissions.

The SAA’s market-oriented agriculture model encourages farmers to approach agriculture as a business by strengthening linkages to markets, promoting value addition, and supporting agripreneurship. Nutrition-sensitive agriculture ensures that increased agricultural productivity also translates into improved dietary quality, particularly for women and children. Across Nigeria—Kano, Nasarawa, Jigawa, Gombe, and other states—SAA has facilitated trainings on rice parboiling, groundnut oil processing, backyard gardening, and preparation of balanced local diets. These efforts are supported by continuous capacity building for extension agents.

The SAA deploys multiple extension models, including the Farmer Learning Platform (FLP), which establishes demonstration plots such as Community Demonstration Plots (CDPs), Technology Adoption Plots, and Model Adoption Plots that enable farmers to evaluate productivity-enhancing technologies. The Private Extension Service Provision (PESP) model expands access to technologies and advisory services through youth spray service providers, agro-dealers, community-based facilitators, and commodity association trainers. Through the Community Savings for Investment in Agribusiness (CSIA) model, farmers organize into self-managed savings groups to improve access to finance and support agribusiness investments. The Community-Based Seed Multiplication (CBSM) initiative improves farmers’ access to quality seeds, while value chain development centers—such as the rice aggregation and processing centers in Nasarawa—provide one-stop hubs for rural agribusiness development.

Through its demand-driven SAFE curriculum, SAA strengthens advisory services by equipping mid-career agricultural professionals with skills needed to support value-chain development. SAA’s interventions have led to notable successes, including significant yield increases in Kano, expanded training for 1,409 extension agents, and transformative stories such as that of women farmers in Benue.

In conclusion, agricultural extension remains central to Nigeria’s agricultural transformation. Scaling up successful models requires increased investment from government, stronger partnerships, expanded digital advisory services, and sustained efforts to reach the last mile. The vision ahead is a resilient, innovative, and inclusive African agriculture sector where smallholders drive transformation, governments create enabling environments, private sector actors invest in co-creation of innovations, and farmers become champions of change.

Office of the Vice Chancellor

Ahmadu Bello University, Zaria

REMARKS

By

Prof Adamu Ahmed
                                   Vice Chancellor, Ahmadu Bello University Zaria

The Honourable Minister, Federal Ministry of Agriculture and Food Security

The Honourable Commissioner for Agriculture, Kaduna State

Vice-Chancellors, Deans, and Directors of Agricultural Institutions

Programme Managers of Agricultural Development Projects

Representatives of Farmers’ Associations and Cooperatives

Development Partners and the Private Sector

Distinguished Guests, Colleagues, Ladies, and Gentlemen. I welcome you all with immense joy and a deep sense of responsibility to Ahmadu Bello University, Zaria, for this year’s National Agricultural Extension Review and Planning Meeting. The theme of this year’s meeting, “Innovative Solutions for Sustainable Agricultural Extension in Nigeria: Addressing Climate Change, Digital Gaps, and Gender Equity,” is thought-provoking, reminding us that we must re-engineer our approaches to agricultural development in line with the constant and spontaneous realities. It is an honour to host you here yearly through the National Agricultural Extension and Research Liaison Services (NAERLS). This commitment equally reaffirms the university’s critical role in continually supporting NAERLS in driving agricultural innovation, research, and rural transformation in Nigeria. I say unequivocally that this annual review meeting is not just a routine exercise; it is a strong national platform for reflection, knowledge exchange, and collaboration. At every meeting, we assess past efforts, share lessons, and chart new directions for strengthening agricultural extension delivery across all states. 

It is a unifying opportunity to rekindle our collective vision of a vibrant, technology- driven, and inclusive agricultural sector that will ensure food security, economic prosperity, and environmental sustainability. Having said that, let me take us on climate change and resilient agriculture. Beyond what most of us will assume, climate change is not just a scientific debate; it encompasses many critical social, cultural, traditional, religious, political, and other concerns. These concerns continuously require our strategic observations, calculations, reporting and participatory deliberations with our farmers. For instance, erratic rainfall patterns, prolonged dry spells, flooding, and pest infestations have disrupted traditional farming calendars and also threatened farmers' livelihoods. The impacts of these were recorded and reported by NAERLS in its Executive Summary of the 2025 Agricultural Performance in Nigeria. Accordingly, our responses to the identified impacts of climate change must be science-based, coordinated, and farmer-centred.2 However, extension agents must not relent in their services as the frontline defenders, bridging the gap between research and the concerns and demands of rural farmers. Therefore, climate-smart agricultural practices such as conservation farming, agroforestry, water harvesting, and the use of drought-tolerant varieties must be mainstreamed through extension systems. To achieve this, we need stronger linkages between universities, research institutions, and extension networks. Research findings must not remain within academic journals they must reach the farmer’s field, in simple, practical, and actionable language. Nevertheless, digital transformation in agricultural extension is desirable. In today’s world, information is power, and technology is the key that unlocks it. Yet, millions of smallholder farmers in Nigeria are technically excluded from the digital ecosystem. Thus, we must not just introduce eco-friendly and sustainable technology, the technology must be inclusive, gender friendly, adaptive, and accessible. Mobile-based advisory platforms, e-extension systems, and digital weather alerts can be adapted to empower farmers with real-time information for better decision-making. More so, drone technology and data-driven tools can be configured to help extension agents monitor crop health and identify problems faster. However, the real impact of technology lies in its accessibility. Therefore, we must:

Develop low-cost, multilingual digital platforms accessible via basic mobile devices;

Build the capacity of extension agents as digital intermediaries who can translate data into

farmer-friendly advice;

Invest in rural digital infrastructure through public-private partnerships; and

Promote digital literacy, especially among women and youth.

As a matter of fact, digital transformation should not widen inequality across all value chain an farmers’ category. Digital transformation should bridge gaps and connect every farmer to knowledge, markets, and opportunity; fostering gender equity and inclusive development. This is because sustainable agricultural growth cannot happen when half of the population is left behind either by omission or intentionally through a wrong system design. Women contribute significantly to production, processing, and marketing, yet they often face barriers to land ownership, finance, and training. Studies about women in agriculture have argued for women to have equal access to productive resources as men in order to increase the former’s agricultural output by as much as 30 percent. We must therefore design gender-responsive extension systems that reach women wherever they are using flexible training schedules, women-led cooperatives, cultural and socially encouraging and targeted mentorship programmes. 

Empowering women farmers is not just about fairness; it is strategic economic imperative for national food security with a lot of nutrition enablement. Our agricultural future depends on the energy, creativity, and innovation of young people. We must meaningfully engage our youth in and for the future of agriculture. Unfortunately, only few young men and women will take farming as a viable career in Nigeria today. Hence, must reconfigure, reconsider and incentivize agriculture through real time investment with attractive returns. In this way, youths can happily and voluntarily embrace farming as a profitable, modern, and attractive career line. Enough of reactive unemployed-youth-focused and tenure-based programmes. Yes, these types of youth empowerment programmes have their advantages, but they have most engage the youths for a short period that the monetary or training session/support are active. Most beneficiaries abandoned the trade or agricultural activities not too long after the training is over.

In many instances, the youths are only co-opted to participate; many of them are not convinced in the principle and agenda of the training/programme. Nigeria must package farming as a lifeline with stages of growth from training to agribusiness incubation, and digital entrepreneurship. Empirical records have shown that if the youths have access to land, finance, and technology under moderate conditions, agricultural productivity can increase by more than 25 percent. Through mentorship, digital skills development, and innovative financing, we can turn agriculture into a sector of opportunity rather than an alternative.

A Call for Collaboration and Action

As a host institution, Ahmadu Bello University takes immense pride in partnering with the Federal Ministry of Agriculture, NAERLS, and all stakeholders represented here. Together, we must build a responsive, data-driven, and inclusive extension system that delivers real impact at the grassroots. Let us commit to transforming this meeting from an annual review into a launchpad for innovation and partnerships that strengthen our agricultural systems, enhance resilience, and uplift rural communities.

Distinguished participants, the farmer at the end of every extension chain is not merely a beneficiary he or she is a partner in innovation and a driver of change. As we deliberate over the next few days, let us ensure our recommendations are not only strategic but actionable and measurable. It is therefore my honour and privilege to declare open the 2025 National Agricultural Extension Review and Planning Meeting. I wish you fruitful deliberations, impactful networking, and safe travels back to your various destinations.

Thank you, and may God bless the Federal Republic of Nigeria

SPEECH BY PROFESSOR YUSUF AHMAD SANI, THE DIRECTOR, NATIONAL AGRICULTURAL EXTENSION AND RESEARCH LIAISON SERVICES (NAERLS), AHMADU BELLO UNIVERSITY, ZARIA, AT THE 2025 NATIONAL AGRICULTURAL EXTENSION REVIEW AND PLANNING MEETING HELD AT THE NAERLS CONFERENCE HALL, FROM 1st TO 4th DECEMBER 2025

PROTOCOL

The Honourable Minister of Agriculture and Food Security (FMAFS)

The Permanent Secretary, FMAFS

The Vice-Chancellors of Ahmadu Bello University, Zaria

Honourable Commissioners of State Ministries of Agriculture and Livestock

Executive Directors of National Agricultural Research Institutes

Programme Managers of Agricultural Development Programmes (ADPs)

Private Sector Partners

Representatives of Development Partners

Members of the Academia and Research Community

Representatives of Farmers’ Associations and Commodity Groups

Gentlemen of the Press

Distinguished Ladies and Gentlemen

It is my honour and privilege to welcome you to the 2025 National Agricultural Extension Review and Planning Meeting, organised by the National Agricultural Extension and Research Liaison Services (NAERLS). As Nigeria’s coordinating institution for agricultural extension, this annual gathering is essential for assessing our progress, refining our strategies, and shaping a future-ready extension system.

The theme of this year’s meeting, “Innovative Solutions for Sustainable Agricultural Extension in Nigeria: Addressing Climate Change, Digital Gaps, and Gender Equity,” is timely and compelling. It captures the reality that agriculture today is facing unprecedented pressures, requiring unprecedented innovations.

As Kofi Annan once said: “Food security is not only about feeding people, but also about empowering them.” This is the essence of extension work. Climate Change: The most urgent threat to food security climate variability has emerged as the defining risk to Nigeria’s agricultural productivity. According to the Nigeria Meteorological Agency (NiMet), Nigeria has experienced a 1.6°C rise in average temperature over the past century. Projections indicate further warming, which could reduce yields of major staples such as maize and sorghum by 2050 if adaptation measures are not implemented. In the past five years alone, Nigeria has recorded:

Over ₦700 billion in losses from flood-related crop damage (NAERLS, 2023; Tribune Online, 2023);

Increase in pest outbreaks, including the fall armyworm; and

Increased number of farmers affected annually by unpredictable rainfall patterns.

To address these challenges, NAERLS has strengthened its climate-smart extension models. We have also scaled up early warning systems that deliver actionable advisories on rainfall, temperature, pest outbreaks, and planting windows. Evidence shows that farmers who receive timely agro-advisories can increase yields.

We continue to promote climate-resilient crop varieties, livestock breeds, and fisheries technologies developed by National Research Institutes (NARIs). Additionally, we are expanding training on water-use efficiency, soil regeneration, and integrated nutrient management. Our goal remains unwavering to ensure that scientific innovations move beyond the laboratory and into the hands of farmers, where their impact is realized.

Across the world, digital technologies are transforming agricultural advisory systems. The FAO reports that digital extension can reduce advisory delivery costs and triple the number of farmers reached. Yet, digital exclusion remains significant in Nigeria, particularly in rural areas.  Key constraints include low and unreliable internet access, low digital literacy rates and use of smartphones for agricultural purposes among smallholder farmers. To close this gap, NAERLS is accelerating digital extension delivery through:

Mobile-based advisory platforms.

Interactive voice-response systems via the National Farmers’ Helpline Centre, which received 10,000 farmer calls in 2024 (NAERLS, Webpage, 2024);

WhatsApp and social media communities that support the rapid dissemination of videos, voice notes, and demonstrations; and

Expanded radio and television programmes reaching out to more Nigerians weekly.

We are also establishing community ICT hubs in underserved regions, enabling farmers to access digital knowledge tools. Furthermore, we are training ADP extension personnel in digital content creation, data management, and virtual facilitation to ensure that advisory messages are timely, accurate, and user-friendly. Ladies and gentlemen, digital transformation is no longer a choice; it is an imperative for modern extension delivery.

Advancing Gender Equity, Youth and People with Disability Inclusion 

Women constitute a significant share of the farming population in Nigeria; yet they face systemic barriers, such as limited access to land, credit, technology, and training (FGN, 2024). Additionally, Nigeria’s demographic future hangs in the balance, as over 60 per cent of the population is now under the age of 30, a statistic that the National Population Commission (NPC) says could be either a massive development opportunity or a ticking time bomb, depending on the country’s next steps (The Guardian Online, 2025, July).
Interestingly, closing the gender gap in agriculture could raise farm output by a credible percentage and, at the same time, reduce the number of hungry Nigerians annually. In recognition of this, NAERLS has strengthened its Gender Unit to promote equitable access and inclusive learning. We are scaling up the following:

Labour-saving and climate-smart technologies that reduce women’s

workload

Women-only training sessions to enhance participation and confidence

Youth-led community extension volunteer schemes, and

Partnerships with gender-focused NGOs and research institutions to integrate evidence-based gender strategies into extension planning.

I believe that when women and youth are empowered, entire communities rise. Their inclusion is not only proper; it is smart economics. Equally important are people with disabilities (PWD), who often encounter structural and social obstacles that limit their participation in agricultural value chains, despite their potential to contribute meaningfully when provided with accessible tools, tailored training, and supportive policies.

Strengthening Partnerships for National Impact

The challenges before us, that is, climate change, digital exclusion and gender inequality, are interconnected and cannot be addressed by any single institution. According to the 2025 International Finance Corporation (IFC) Nigeria Country Private Sector Diagnostic report, a low ratio of extension workers to farmers (1:7,500) compared to the (1:800) recommended by FAO can lead to inefficiencies in the value chain, which in turn can result in poor yields. Likewise, the NAERLS Annual Performance Survey (NAERLS, 2024) indicates an even more alarming Extension Agents– Farm Families ratio (1:6,466), underscoring the urgent need for stronger partnerships and innovative delivery mechanisms to bridge the advisory service gap nationwide. This situation makes institutional collaboration not an option, but an essential strategy for NAERLS; thus, we remain committed to leading a coordinated national extension architecture that mobilises:

Federal and State Ministries of Agriculture

National Agricultural Research Institutes (NARIs)

Agricultural Development Programmes (ADPs)

Universities and Colleges of Agriculture

Private sector and ag-tech innovators

Development partners and NGOs, and

Farmer associations and cooperative networks.

Distinguished participants, this meeting is not a ceremonial gathering. It is an opportunity to challenge our assumptions, refine our strategies, and commit to innovative, inclusive, and evidence-based solutions. Let us focus on the needs of our farmers and particularly the most vulnerable.

Let us pursue scalable, affordable, and practical innovations while working together to build a national extension system that delivers food security, prosperity, and resilience for all Nigerians. I reaffirm NAERLS’ unwavering dedication to leading a modern, efficient, and inclusive extension system. With innovation, partnership, and shared purpose, we can build an agricultural sector that is:

Resilient in the face of climate change

Competitive in the digital age, and

Inclusive of all genders and social groups.

Let us seize this moment to build an extension system that truly leaves no farmer behind.

Thank you, and I wish us all productive deliberations. 

God bless the Federal Republic of Nigeria.

God bless Nigerian farmers.

God bless Ahmadu Bello University, Zaria. 

God bless NAERLS.

SPECIAL MESSAGE BY THE EXECUTIVE SECRETARY, AGRICULTURAL RESEARCH COUNCIL OF NIGERIA (ARCN) DR. ABUBAKAR ADAMU DABBAN AT THE 2025 NATIONAL AGRICULTURAL EXTENSION REVIEW AND PLANNING MEETING (NAERPM) Held at NAERLS Ultra-Modern Conference Hall, ABU Zaria on 1st–4th December, 2025

PROTOCOL

Executive Directors and Provosts of National Agricultural Research Institutes and Federal Colleges of Agriculture

Dean of Faculties of Agriculture 

Representatives of the Federal Ministry of Agriculture and Food Security

Head of Departments, Researchers, and Extension Professionals

Development Partners and Private Sector Collaborators

Distinguished Farmers’ Representatives and Commodity Associations

Members of the press 

Ladies and Gentlemen

It is a great honour for me, on behalf of the Agricultural Research Council of Nigeria (ARCN), to extend my warm greetings to all distinguished participants at this year’s National Agricultural Extension Review and Planning Meeting (NAERPM). I commend the Executive Director of NAERLS, Prof. Y. A. Sani, and the organizing team for sustaining this important annual platform for reflection, coordination, and forward-looking planning in our national extension system.

The 2025 theme, “Innovative Solutions for Sustainable Agricultural Extension in Nigeria: Addressing Climate Change, Digital Gaps and Gender Equity,” is timely and fully aligned with the mandate of ARCN under the ARCN Act, as well as our ongoing reforms across the National Agricultural Research System (NARS). The challenges highlighted in the theme reflect the realities facing our farmers today. Climate variability continues to threaten productivity; digital divides limit the rapid flow of knowledge; and gender inequalities hinder the full participation of women who form a large proportion of our agricultural workforce.

This meeting provides a vital opportunity for all stakeholders—including NARIs, FCAs, universities, ADPs, private sector actors, development partners, and farmer groups—to jointly review the achievements and gaps in 2025 and to harmonize activities for 2026. The synchronized extension–research calendar expected from this engagement remains a key instrument for reducing duplication, optimizing resources, and strengthening partnerships across the entire agricultural value chain.

ARCN is committed to deepening result-oriented coordination that enhances technology dissemination, improves farmers’ access to innovations, and drives inclusive growth. We are also expanding our focus on demand-driven research, climate-smart technologies, youth-friendly innovations, and digital extension tools that will help Nigeria address the food and nutrition security challenges of the present decade.

I congratulate all participants and encourage you to make meaningful contributions throughout the meeting. Together, we must work towards an extension system that is modern, responsive, gender-inclusive, and capable of delivering sustainable solutions for our farmers.

I wish you successful deliberations and fruitful outcomes.

God bless the Federal Republic of Nigeria.

Thank you.

[image: image10.png]



[image: image11.jpg]



National Agricultural Extension and Research Liaison Services Federal Ministry of Agriculture and Food Security

Ahmadu Bello University, Zaria
2025 Wet Season Agricultural Performance in Nigeria

Executive Summary
www.naerls.gov.ng
October 2025
Executive Summary—2025 Wet Season Agricultural Performance in Nigeria
1
[image: image81.png]MANDATES

Conduct
agricultural
performance

assessment
Advance the and provide
frontiers of feedback
agricultural
extension Build the
research O 2 capacity and skill
and services of key actors for
effective

O 3 extension.

Review and

04

s:stl:a?::i(t)l:ne O 5 Plan, coordinate,
activities of monitor and
agricultural evalua.te. BEFILS
research Package and activities
institutes. disseminate nationwide.
improved

agricultural
innovations.



[image: image82.png]VISION

‘The foremost institute
for agricultural extension
research and capacity
"’”'3553';‘;2‘:,;222‘““ evaluate and disseminate
increased agricultural Pr_v:vdetr‘l::]ﬂ_ mlevz'rju
productivity, sustainable agricultural innovation

i and research on
SR extension methodologies

jand provide leadership
in capacity building of
stakeholders to meet the
present and future
L] agricultural development
challenges of the
country.

[}
MISSION

o develop, collat



[image: image83.jpg]


[image: image84.png]


www.naerls.gov.ng
Executive Summary—2025 Wet Season Agricultural Performance in Nigeria
2
[image: image85.jpg]SURVEY AREA

36 States of the Federation
and FCT

SURVEY DURATION
6 days

SURVEY TEAMS

Nineteen (19) multi-disciplinary
teams of 3 scientists each
Each team covered 2 states

SAMPLING PROCEDURE

36 States + FCT, 2 ADP zones
per State, 2 LGAs per zone,

1 Community per LGA and

10 respondents per community



EXECUTIVE SUMMARY
National Agricultural Extension and Research Liaison Services Federal Ministry of Agriculture and Food Security

Ahmadu Bello University, Zaria
P.M.B. 1067
Zaria, Nigeria
www.naerls.gov.ng
Citation:
NAERLS, FMAFS (Federal Ministry of Agriculture and Food Security) 2025.
Wet Season Agricultural Performance in Nigeria: Executive Summary.
NAERLS Press, Zaria ISSN: 2408-7459

©2025 All rights reserved by NAERLS
Certified By
National Technical Committee on Agricultural Statistics
Collaborators:
FDA, FDAE, P&PCD, FDF&A, NBS, NASC, NiMet, IAR, IAR&T, NRCRI, NCRI, LCRI, NIFOR, NAPRI, DAC-ABU, NIFFR, ADPs, FMLD, and State
Ministries of Agriculture, State Ministry of Livestock Development, Commodity- Based Associations

Executive Summary—2025 Wet Season Agricultural Performance in Nigeria
3
[image: image86.jpg]APS 2025

COMPLEMENTARY
RESEARCH AREAS

P

.. )
1
u. / v. /

Commodity
Prices

Extension Agent:
Farm Family
Ratio

Tractor Census
and Agricultural
Mechanisation




Preface
The 2025 Wet Season Agricultural Performance Survey (APS) was conducted across all 36 states and the Federal Capital Territory (FCT) by the National Agricultural Extension and Research Liaison Services (NAERLS), in collaboration with 22 Ministries, Departments and Agencies (MDAs) and development partners. The fieldwork was conducted between August 30th and September 7th, 2025, to assess crop and livestock performance, farmers’ production decisions, mechanization trends, and market dynamics during the 2025 wet season. This year, the APS adopted improved methodologies, including three complementary research components: a Farm Family Census to map extension coverage, a Tractor Census to establish a database of functional tractors, and Commodity Price Studies to monitor farm-gate and market variations for policy guidance.

The survey was highly collaborative, drawing expertise from six coordinating research institutes: NCRI, LCRI, IAR, NRCRI, IAR&T, and NIFOR—as well as departments of the Federal Ministry of Agri- culture and Food Security (FMAFS), national agencies such as NBS, NASC, NAPRI, NIFRRI, and all state ADPs. This extensive collaboration ensured credibility, ownership, and comprehensive cover- age, making the 2025 APS one of the most authoritative surveys of its kind. The 2025 APS confirms steady growth in Nigerian agriculture, with rice, maize, sorghum, millet, cowpea, yam, and cassava all recording higher outputs compared to 2024. Production gains were driven by modest expansions in cultivated areas, improved farming practices, and resilience across major producing states, rein- forcing food security and sustaining agro-industrial value chains.

We especially acknowledge the outstanding efforts of the Honourable Minister of Agriculture and Food Security, Senator Abubakar Kyari, CON, the Honourable Minister of State for Agriculture and Food Security, Senator Dr Aliyu Sabi Abdullahi, CON, the Permanent Secretary of FMAFS – Dr Marcus

O. Ogunbiyi and the Vice Chancellor of Ahmadu Bello University, Professor Adamu Ahmed. As well as the Directors of the Planning and Policy Coordination Department (P&PCD) – Dr Ibrahim Tanimu and Federal Department of Agricultural Extension (FDAE) – Mr. Ayodele Olawumi. In the same vein, NAERLS sincerely appreciates the cooperation of farmers and Commodity-Based Association, as well as officials of ministries, departments, and agencies at both Federal and State levels, whose contributions were critical to the success of the fieldwork.

Suggestions, observations, and comments are welcome to strengthen future surveys and reporting.
Prof. Yusuf Sani Ahmad Executive Director, NAERLS director@naerls.gov.ng www.naerls.gov.ng
Executive Summary—2025 Wet Season Agricultural Performance in Nigeria
4
[image: image87.jpg]DATA COLLECTION METHODS

Quantitative Data

field survey using semi
structured questionnaires

Qualitative Data

Participatory Rural Appraisal (FGDs,
Klls; using checklists) and
Observations

A
Secondary Data
Review of official documents and
reports from NiMet and others
DATA SOURCES
=N Ministries
I I I of Agriculture E
o] L
/ ADPs
N1/

(L

VL
-
<

()

A )

v Commodity
Based ‘=.
&an

Associations



Table of Contents
Preface
4
Introduction
6
Methodology
7
Rainfall Situation
8
Flood Occurrences
12
Crop Pest and Diseases
13
Farm Inputs Situation
14
Agricultural Mechanization
15
Cost of Production for Major Crops per Hectare
20
Food Commodity Prices
22
Production Estimates for Major Crops
24
Livestock Diseases
36
Fisheries Production Situation
39
Agricultural Development Programme Situation
40
Conclusion and Recommendations
42
Introduction
This Executive Summary presents the key findings of the 2025 Agricultural Performance Survey (APS). These include the survey methodology, rainfall patterns, flood occurrences, crop pests and diseases, use of improved inputs, agricultural mechanization, grain reserves, cost of production for major crops, food commodity prices, production estimates, livestock and fisheries performance, agricultural development programmes, extension activities, special projects, constraints to production, and the conclusion with recommendations. Each theme is presented in concise prose supported by relevant charts, ensuring clarity, logical flow, and easy reference for policymakers and stakeholders. The interconnected nature of these themes reflects NAERLS’ systematic approach to data collection, analysis, and presentation an approach refined over the years to strengthen coherence across diverse datasets.

Four strategic objectives guide the APS:
To assess the performance of the agricultural sector during the wet season and forecast likely production outputs for the year.

To identify constraints limiting agricultural productivity.
To highlight the conditions that affect effective technology transfer and advisory services.
To provide feedback on field realities and farmers’ challenges for improved research, extension, and policy action.
The 2025 APS fieldwork was conducted from August 30th to September 7th by NAERLS in collaboration with ministries, agencies, and development partners nationwide. As in previous years, the Executive Summary is formally presented to the public during the World Food Day celebrations by the Honourable Minister of Agriculture and Food Security. Its findings remain an essential tool for assessing sector performance, guiding policy decisions, and advancing Nigeria’s food security agenda.

[image: image88.png]Average Rainfall (mm)

160

140

120

100

80

60

40

20

114

89

Makurdi Lokoja

Benue

Kogi

167

Tlorin Lafia Bida

Minna

Kwara Nasarawa Niger

2024

2025

105110

Niger

| |
Jos  Jalingo

Plateau Taraba

93

56

Abuja
FCT



Methodology
Rainfall Situation
In 2025, the North-West, parts of the North-East, and the South-West experienced more rainy days and higher rainfall, which enhanced crop and livestock production and created opportunities for multiple planting cycles and pasture re- generation. Nonetheless, irregular rainfall patterns and frequent dry spells undermined the reliability of rainfall for farming, while soil erosion, water stress, and reduced rainfall in some areas continued to constrain agricultural productivity across the country.

North-Central
Nasarawa recorded the highest rainfall at 167 mm, boosting both crop and livestock productivity, while Plateau’s high number of rainy days provided stable farming conditions. In contrast, the FCT had the lowest rainfall at 56 mm, creating localized water stress, and the variability in rainfall between 2024 and 2025 has further complicated planning for farmers in the zone.

[image: image89.png]Average Rainfall (mm)
v 2 2 » B B B B B
8 523 E8EE8 B8 & E

°

59 65

Yola

Adamawa

154 158 190

94
Maidugusi Bauchi
Borno Bauchi

w2024

2()7"

85

63

Gombe
Gombe

92

58

Nguru
Yobe

107
93

Potiskum
Yobe




Average rainfall in North-Central (January to August 2025)
Source: NiMet
North-East
Bauchi, Borno, and Adamawa received more rainfall in 2025, which improved crop prospects, while Yola recorded the highest number of rainy days, creating opportunities for double cropping. However, widespread dry spells in June and July reduced overall productivity, and Yobe experienced a drop in rainfall, which may worsen existing water stress in the State.

[image: image90.png]200
180
160

140

Enro

= 100

Average Rainf:
o =
o 8 &5 38 2

99
91

Dutse

Jigawa

120

IllO

Kaduna
Kaduna

87

I77

Zaria

Kaduna

97

75
65 64

Kano Katsina
Kano Katsina

w2024 = 20725

96 93

Yelwa

Kebbi

180

80

Sokoto

Sokoto

125

75

Gusau

Zamfara




Average rainfall in North-East (January to August 2025)
Source: NiMet
North-West
Sokoto, Zamfara, and Jigawa experienced more rains in 2025, which improved water availability and pasture for livestock. Kaduna recorded the highest number of rainy days at 54, supporting both rain-fed crops and livestock production. In contrast, Kano had the lowest rainfall, limiting its crop production potential, and overall rainfall in the zone remained much lower than in the southern states, sustaining food security risks.

[image: image91.png]Average Rainfall (mm)

200
180
160
140
120
100
80
60
40
20

179
170
162
150
133

120
Umuahia Awka Enugu
Abia Anambra Enugu

w2024 20725

182 184

Owerri

Imo

179

139

Abakaliki

Ebonyi




Average rainfall in North-West (January to August 2025)
South-East
Imo and Abia had slightly better rainfall in 2025, which supported food crop production, and the adequate number of rainy days up to 91 allowed for multiple planting cycles. However, most states in the zone recorded lower rainfall than in 2024, which could negatively impact yields, while erosion challenges continued to threaten farmlands and reduce the availability of cultivable land.
[image: image92.png]377

400

200

168,

1mooreymIog

urueg

res

306
L Moy
84 I

eqesy

250

1

126,

©loS0

209

189,

wo

262

221

eqere)

voSouax

338
06
73

ofn

2 2 8% 88 g
« | =
R

0

<
“ N ~ "
(ww) [ejuTey sSeroay

Delta Delta Edo Rivers

2025

2024

A-Tbom Bayelsa C/Rivers C/Rivers C/Rivers




Average rainfall in South-East (January to August 2025) Source: NiMet
South-South
Akwa Ibom recorded the highest rainfall at 306 mm, which was favorable for fishponds, tree crops such as oil palm and rubber, and irrigated farming. The abundant rains also supported wet- lands and river-fed livelihoods. However, irregular rainfall distribution; for example, Asaba with only 67 rainy days compared to Warri’s 109 days, led to uneven planting success, while dry spells in Cross River disrupted crop cycles.

[image: image93.png]Average Rainfall (mm)
N oo o= B
8 53 38

°

164
153
141
125

Abeokuta  Akure
Ogun  Ondo

148

105

Ondo

Ondo

177
151
115
93

Oshogbo ~ Tbadan

Osun Oyo

151

102

Tkeja

Lagos

168
154
134
99

Oshodi  Ado-Ekiti
Lagos  Ekiti

2024
2025




Average rainfall in South-South (January to August 2025)
    South-West
Increased rainy days in 2025 boosted soil moisture and supported crop growth, while the early onset of rains provided farmers with an extended planting window. However, Lagos recorded the lowest rainfall at 99 mm, which may have reduced water availability for both crops and house- holds. The overall decline compared to 2024 also poses risks of stressing water resources and limiting opportunities for dry-season farming.

[image: image94.jpg]KATSINA
JIGAWA YOBE
KANO
KADUNA BAUCHI
ADAMAWA
PLATEAU
NASARAWA
TARABA foee
osun &M Joct BENUE
Legend
[ Very Severe Occurrence
Severe Occurrence L.
Mild Occurrence
T Not yet reported





Average rainfall in South-West (January to August 2025)
Source: NiMet
Floods and Climate Impacts
The 2025 floods severely affected all six geopolitical zones, damaging farmlands, crops, livestock, and critical infrastructure, including roads, bridges, schools, and markets. Niger State was the worst hit, with 161 deaths and widespread displacement, while Jigawa recorded 28 fatalities and heavy farmland losses. Staple crops, including rice, maize, cassava, yams, sorghum, and millet, suffered significant damage, alongside fisheries and tree crops, in the South-South and South-East Zones.
Despite the devastation, the floods also brought corrective opportunities. Nutrient-rich sediments are expected to improve soil fertility. Reservoirs and groundwater were replenished to support irrigation and dry-season farming, and the potential for aquaculture was highlighted for flood prone communities. Most importantly, the disaster underscored Nigeria’s vulnerability to climate risks, spurring momentum for stronger resilience and adaptation measures.

[image: image95.jpg]SOKOTO
KATSINA
o JGAWA
KEBBI KANO BORNO
GoMBE!
KADUNA BAUCHI
el NGER s
ADAMAWA
PLATEAY
oo SR, -
o TARABA -
OSUN
ro OGUN -
LAGOS ENUGU Legend
ANAVBRA EBONYI

= CROSSRIVER B

DELTA 4 MOABIA Not reported
sl Light infestation -,

BAYEL: nE Moderate infestation

B m 300 s I ooy nfeatation

e =




Severity of flood across the country in 2025 (as at September 2025)
Crop Pests and Diseases
A total of 19,358.5 hectares of farmland were affected by crop pests and diseases during the 2025 wet season, with estimated yield losses of about 22.5% (within the affected farmland).

As illustrated in the figures below, these infestations, ranging from fall armyworm, rice blast, blight, and stem borer to multi-crop pest and disease complexes, exhibited wide epidemiological distribution and variable severity indices across all agro-ecological zones, underscoring their nationwide spread and impact.The crops most affected included cereals, legumes, roots and tubers, vegetables, fruits, tree crops, and fibre crops.

Key threats were particularly severe for maize (fall armyworm in over 11 states, stem borers, and streak virus), rice (Quelea birds, blast, bacterial blight, and rodent damage), millet and cowpea (stem borers, gall midge, and aphids), root and tuber crops (cassava mosaic and yam nematodes), and tree and fibre crops (cocoa black pod and cotton smut).

[image: image96.jpg]



Severity of Fall Army Worm Infestation across the Country
[image: image97.jpg]


[image: image12.jpg]



Pest and Diseases that affected some crops
Blight infestation
Farm Inputs Situation
Average Fertilizer Prices in Nigeria by Zone (2024 vs 2025)
Despite improved availability of fertilizers following government interventions, price inflation re- mained a major challenge in 2025. The national average price of NPK rose sharply by 19.5%, from ₦43,500 to ₦52,000 per 50kg bag, with the North-West, North-Central, and North-East recording the steepest increases. Urea prices also climbed by 10.1%, from ₦39,500 to ₦43,500, particularly in the South-W

est, South-East, and North-East. Thus, while inputs were relatively more accessible, affordability remained a pressing concern for farmers nationwide.

[image: image98.png]



The average price of NPK fertilizer in Nigeria in 2025 compared to 2024
[image: image99.png]



The average price of Urea fertilizer in Nigeria in 2025 compared to 2024
Fertilizer Procurement & Distribution
Fertilizer distribution was heavily uneven, with states like Kogi, Jigawa, and Abia showing mas- sive support, while many others, especially in the North-East, South-West, and South-South, sup- plied negligible amounts.

[image: image100.png]60,000

50,000

40,000

30,000

R/50KgBag

20,000

10,000

o

52,500

43,000

North-Central

3,500

44,000

North-East

51,000

41,500

North-West

w2024 m2025

50,500

43,500

South-East

49,500

43,000

South-West

5,000

46,000

South-South




[image: image101.png]50,000
45,000
40,000
35,000
30,000
25,000
20,000
15,000
10,000

®/50KgBag

5,000

40,000
44,000

North-Central

42,000
,500

North-East

40,000
43,500

North-West

w2024 m 2025

=3
8

g 2

3 =

N

m |

South-East

36,000
40,000

South-West

41,500
5,500

South-South



Agricultural Mechanization
Tractor availability and functionality
The North-West (808) and North-Central (793) had the highest numbers of functional units, though the North-West also reported 65 non-functional units compared to just 6 in the North- Central. The South-East showed the best performance with 137 units all functional. By contrast, the South-West (107 functional, 58 non-functional) and South-South (48 functional, 24 non- functional) recorded the greatest reliability challenges.

[image: image102.jpg]Fertilizer Distributed

MT)
Urea
Kogi 50,000 50,000
North-Central | Nasarawa 298
Taraba 5,000
Bauchi 3,450
North-East
Gombe 40
Jigawa 9,625 4,312
North-West Katsina 12 8
Kano 510
Abia 30,000
South-East
Ebonyi 2,400 1,100
Akwalbom | 11.5
Bayelsa 225 2.5
South-South
Cross River 50 50
Delta 665 245 (MOP)
Lagos 25
South-West
Osun 7 3





Status of government owned tractor across the geopolitical zones in 2025
Animal traction situation
Animal traction use declined in most states compared to 2024. Adamawa (850; –9.1%), Bauchi
(34,990; –9.2%), and Yobe (755; –19.3%) all recorded reductions, while Gombe (3,326;
+0.33%) was the only state to show growth. Overall, the trend points to a general decline in animal traction across the zone, with Gombe as the exception.

	States
	Amount of Animal Traction in
each state in 2025 compared to
2024
	% Change

	Adamawa
	850
	-9.09

	Bauchi
	34990
	-9.21

	Yobe
	755
	-19.25

	Gombe
	3326
	0.331

	Benue
	54
	-34.18


Cost of land preparation: Animal traction vs
           tractor (per hectare)
The cost of land preparation per hectare was lower with animal traction than with tractors across all zones, with ridging consistently cheaper than ploughing. The North-East recorded the lowest costs (₦35,666/ha for animal ploughing vs. ₦52,833/ha for tractor ploughing), while the North-Central had the highest, especially for tractor ploughing (₦64,500/ha). These differences explain why many smallholders still rely on animal traction despite the greater efficiency of tractors.
	Zones
	Animal Traction (N)
	Tractor (N)

	
	Ploughing
	Ridging
	Plough
	Ridging

	North-Central
	50,000
	35,000
	64,500
	43,600

	North-East
	35,666
	27,500
	52,833
	33,300

	North-West
	36,000
	38,000
	63,822
	38,928


Cost of Tillage Operations
In 2025, tillage costs were lowest in the North-East and highest in the South-South and South-East. Ploughing, especially in Fadama lands, was the most expensive operation nationwide, while ridging was generally the least costly. The wide cost differences reflect variations in terrain, machinery availability, and service charges across zones.

[image: image103.png]



Cost of Production of Major Crops per Hectare
The cost of producing major crops in Nigeria rose significantly in 2025 compared to 2024, though the increases varied by crop. Among cereals, maize recorded the highest cost rise (+29.2%), while among legumes, soybeans rose the most (+36.8%). Roots and tubers also saw sharp increases, espe- cially yam (+25.8%) and cocoyam (+13.2%), while citrus and leafy vegetables recorded major cost

[image: image104.png]900

800

700

600

500

400

300

200

100

793

6

808

342

137
65
19 0

107

58
48 5,

L

North Central

North East  North West ~ South East

m Functional

m Non-Functional

South West  South South




[image: image105.jpg]North

Harrowing

N51,333
s N66,500 N62,00

North

East N55,000 N50,666
North

s N66,750 N50,666

South

e N116,667 N95,500 N91,000
South

N161,667 N134,000

South

SOt N65,000 N63,500 N50,000

West

N43,666

N33,333

N38,928

N79,166

N45,000




[image: image13.jpg]14.23% 13.19% 25.78% -5.0%

- N667,483 N778,666 N962,959.3 N1,482,800

2024 N584,666 N688,051.22 7754,308.3 1,560,000

Cassava Cocoyam Yam Banana/
Plantain




[image: image106.jpg]29.2%, 17.4% 28.5% 14.1%

- N659.72.3 N689,575.86 N431,258.89 N411,765.5

2024 N519361.18  N535286.88 N365,530.3 N357,765.5

Maize Rice Millet Sorghum




Food Commodity Prices
In 2025, food prices dropped sharply across all six zones compared to 2024, showing a clear and widespread fall in market values.

	Maize (White)

	Zones
	July 2024 price (₦/
Kg)
	July 2025 price (₦/
Kg)
	July 2024-2025 (% change)

	North-Central
	848
	425
	-49.9

	North-East
	972
	432
	-55.6

	North-West
	821
	410
	-50.1

	South-East
	989
	472
	-52.3

	South-South
	1154
	535
	-53.6

	South-West
	983
	464
	-52.8

	National Mean
	961
	456
	-52.5

	Prices of maize declined sharply across all zones from July 2024 to July 2025, with reductions ranging
from -49.9% in the North-Central (₦848 to ₦425/kg) to -55.6% in the North-East (₦972 to
₦432/kg), resulting in a national drop of -52.5% (₦961 to ₦456/kg).


	Milled Rice

	Zones
	July 2024 price (₦/
Kg)
	July 2025 price (₦/
Kg)
	July 2024-2025 (% change)

	North-Central
	1270
	776
	-38.9

	North-East
	1489
	1010
	-32.2

	North-West
	1433
	950
	-33.7

	South-East
	1572
	1093
	-30.5

	South-South
	1899
	1207
	-36.4

	South-West
	1344
	856
	-36.3

	National Mean
	1501
	982
	-34.6

	The price of milled rice fell across all zones from July 2024 to July 2025, with the sharpest decline of -
38.9% in the North-Central (₦1,270 to ₦776/kg) and the smallest drop of -30.5% in the South-
East (₦1,572 to ₦1,093/kg), leading to a national average reduction of -34.6% (₦1,501 to ₦982/ kg).


	Sorghum (Brown)

	Zones
	July 2024 price (₦/
Kg)
	July 2025 price (₦/
Kg)
	July 2024-2025 (% change)

	North-Central
	894
	453
	-49.3

	North-East
	928
	438
	-52.8

	North-West
	845
	422
	-50.1

	South-East
	1084
	544
	-49.8

	South-South
	1125
	565
	-49.8

	South-West
	1053
	523
	-50.3

	National Mean
	988
	491
	-50.2

	In July 2025, sorghum prices were significantly lower than in July 2024, with reductions ranging from -
49.3% in the North-Central (₦894 to ₦453/kg) to -52.8% in the North-East (₦928 to ₦438/kg), leading to a national average decline of -50.2% (₦988 to ₦491/kg).


	Cowpea (Brown)

	Zones
	July 2024 price
(₦/Kg)
	July 2025 price (₦/
Kg)
	July 2024-2025 (% change)

	North-Central
	1866
	1011
	-45.8

	North-East
	1983
	1124
	-43.3

	North-West
	1755
	906
	-48.4

	South-East
	2167
	1205
	-44.4

	South-South
	2345
	1253
	-46.6

	South-West
	2097
	1187
	-43.4

	National Mean
	2035
	1114
	-45.2

	Cowpea prices declined across all zones from July 2024 to July 2025, with reductions ranging from -
43.3% in the North-East (₦1,983 to ₦1,124/kg) to -48.4% in the North-West (₦1,755 to ₦906/ kg), leading to a national average decrease of -45.2% (₦2,035 to ₦1,114/kg).


	Groundnut (Shelled)

	Zones
	July 2024 price (₦/
Kg)
	July 2025 price (₦/
Kg)
	July 2024-2025 (% change)

	North-Central
	1567
	1553
	-0.9

	North-East
	1667
	1638
	-1.7

	North-West
	1640
	1615
	-1.5

	South-East
	2253
	2218
	-1.6

	South-South
	2283
	2256
	-1.2

	South-West
	2196
	2163
	-1.5

	National Mean
	1934
	1907
	-1.4

	Groundnut (shelled) prices showed minimal changes across all zones from July 2024 to July 2025, with
slight declines ranging from -0.9% in the North-Central (₦1,567 to ₦1,553/kg) to -1.7% in the North-East (₦1,667 to ₦1,638/kg), resulting in a national average decrease of -1.4% (₦1,934 to
₦1,907/kg).


Production Estimates for Major Crops
Rice
Estimated rice production in Nigeria increased by 2.66%, rising from 9.1 million MT in 2024 to 9.4 million MT in 2025, alongside a 1.4% expansion in cultivated area. Niger State achieved the highest output, while Kogi State accounted for the largest land area, reflecting steady growth in the rice subsector.
[image: image107.jpg]16.22% 16.97% 36.8% 32%

- N422,538.88 N504,816.7 N536,223.96 -

2024 M437,577.39 N430,283.3 N398,444.79 N366,000

Cowpea Groundnut Soybean Sweet
Potato




Production Estimates of the Top Ten Rice-producing States in 2025 compared with 2024
[image: image108.jpg]11.03% 13.19% 25.78%

755,000 828,500 600,000

2024 N680,000 N657,900 2340,000

Tomato Leafy Citrus
Vegetable




Land area cultivated by the top ten rice-producing States in 2025 compared with 2024
Maize
Nigeria’s estimated maize production grew by 2.0% from 11.2 million MT in 2024 to 11.4 million MT in 2025, driven by a slight 0.2% increase in cultivated area. Kaduna State recorded the highest output, while Bauchi State committed the largest land area, reflecting both productivity gains and sustained investment in key producing States.

[image: image109.png]800,000.00
700,000.00
600,000.00
500,000.00

400,000.00
300,000.00
200,000.00
100,000.00

0.00

0\ < O @
K +°‘b & @ q@‘ & @@" & \@@
e’b

12024 m2025

Metric Tonnes




Production estimates of the top ten maize-producing States in 2025 compared with 2024
[image: image110.png]5320,000.00
300,000.00
250,000.00
200,000.00
©
T
150,000.00
100,000.00

50,000.00

u2024 m2025




Land area cultivated by the top ten maize-producing States in 2025 compared with 2024
Sorghum
Nigeria’s estimated sorghum production increased by 1.3%, from 6,416,975.3 MT in 2024 to 6,501,048.3 MT in 2025, alongside a 1.4% rise in cultivated area from 5,246,412.0 ha to 5,321,964.3 ha. Kano State led the country with the highest output (645,386.5 MT) and the largest land area (580,664.1 ha). At the same time, most producing states recorded modest gains despite localized

[image: image111.png]Metric Tonnes

1,000,000.00
900,000.00
800,000.00
700,000.00
600,000.00

500,000.00
400,000.00
300,000.00
200,000.00
100,000.00

0.00

g & R £ @

S P & P S LS

S &4 & NS < & &

» S 0 Q\fo‘ Py 4 o S o
¥

12024 m2025




Production estimates of the top ten sorghum-producing States in 2025 compared with 2024
[image: image112.png]400,000.00
350,000.00
300,000.00

250,000.00

£ 200,000.00
150,000.00
100,000.00
50,000.00
0.00

g & &
q,b\) \A\q f Q\oa Qo‘& ~k° <

>

P &

12024 m2025




Land area cultivated by the top ten sorghum-producing States in 2025 compared with 2024
Millet
Nigeria’s estimated millet production rose slightly by 0.14%, from 1.55 million MT in 2024 to 1.55 million MT in 2025, alongside a 1.0% increase in cultivated area from 1.55 million ha to 1.56 mil- lion ha. Yobe State led with the highest output (207,922.4 MT) and the largest land area (182,752.0 ha), although declines were recorded in Sokoto, Zamfara, and Borno.

[image: image113.png]700,000.00

600,000.00
§500‘00000
S 400,000.00
)
2 300,000.00
O
= 200,000.00
100,000.00
0.00
A < N q\’b o’” &P
P & & &
*l-e{g’azg o +,§> ¢ § ,qo & wa b”é\

12024 m2025




Production estimates of the top ten millet-producing States in 2025 compared with 2024
[image: image114.png]700,000.00

600,000.00

500,000.00

400,000.00

©

T

300,000.00

200,000.00

100,000.00 II

0.00
& @ & P >

'b @ » > e. N ’b
~l~ »”;ﬁ o +@6 ¢ & P Oo‘(\ o 0
K

12024 m2025




Land area cultivated by the top ten millet-producing States in 2025 compared with 2024
Cowpea
Nigeria’s cowpea production estimate for 2025 stands at 4.28 million MT, up 4.65% from 4.09 mil- lion MT in 2024, supported by a marginal 0.45% expansion in cultivated area (4.83 million ha to 4.86 million ha). Gombe (329,061.5 MT), Taraba (271,711.2 MT), and Yobe (223,756.6 MT) dominate the national output, while Adamawa, Bauchi, and Kwara also posted substantial gains. However, Borno, Katsina, Zamfara, and Sokoto recorded declines despite relatively stable land areas.

[image: image115.png]250,000.00

200,000.00
?
i
£ 150,000.00
5
S
°
£ 100,000.00
]
=
50,000.00 II II II II
0.00
d?’ R SR < 'b(\c a‘
& & c,o@ & /\’0@ A
&

12024 m2025




Production estimates of the top ten cowpea-producing States in 2025 compared with 2024
[image: image116.png]Ha

200,000.00

180,000.00
160,000.00
140,000.00
120,000.00
100,000.00
80,000.00
60,000.00
40,000.00
20,000.00 I II

0.00

. N

RS g S SN

V‘
12024 m2025




Land area cultivated by the top ten cowpea-producing States in 2025 compared with 2024
Soybean
National soybean production is estimated to increase slightly by 0.40%, from 947,952.1 MT in 2024 to 951,702.5 MT in 2025, while land area expanded by 1.04% from 992,633.6 ha to 1,002,947.9 ha. Benue remains the dominant producer with 207,969.2 MT, contributing over one-fifth of total out- put, followed by Kaduna (94,960.5 MT), Kano (67,785.9 MT), and Taraba (60,816.9 MT). Notably, production declined in Sokoto (–17.7%) and Borno (–17.7%) despite relatively stable land areas, highlighting regional productivity challenges.

[image: image117.png]Metric Tonnes

5320,000.00
300,000.00
250,000.00
200,000.00
150,000.00
100,000.00
50,000.00
0.00

&
& < b&@ J;“ 5\& <&

& .00 °

2 Q o @
§ {_OQ & &>°

IS
12024 m2025




Production estimates of the top ten soybean-producing States in 2025 compared with 2024
[image: image118.png]400,000.00
350,000.00
300,000.00

250,000.00
£ 200,000.00
150,000.00

N

100,000.00
50,000.00
0.00

&

N
RN
2

2

a \a
& &g

S £ L
R &S

12024 m2025




Land area cultivated by the top ten soybean-producing States in 2025 compared with 2024
Groundnut
National groundnut production is projected to rise by 3.1%, from 5,084,548.6 MT in 2024 to 5,241,015.9 MT in 2025, even though land area contracted slightly by –0.3% from 4,400,927.3 ha to 4,387,998.2 ha. Bauchi leads production with 686,700.2 MT, followed by Kaduna (349,644.8 MT), Benue (347,422.5 MT), and Niger (345,185.1 MT). Substantial gains were recorded in Kwara (+5.2%), Taraba (+5.2%), and Plateau (+5.2%), while declines occurred in Zamfara (–25.6%), Soko- to (–8.9%), and Borno (–13.3%), reflecting localized challenges despite stable or rising land use in some cases.

[image: image119.png]250,000.00
200,000.00
150,000.00

100,000.00

50‘00000 “ II II II II II II
Niln
© S

@ o S
& 5T & &
¥

Metric Tonnes

12024 m2025




Production estimates of the top ten groundnut-producing States in 2025 compared with 2024
[image: image120.png]120,000.00

100,000.00
80,000.00
£ 60,000.00
40,000.00

20,000.00 II
0.00

@*’Qp&‘@ o o @"’ & & b,§®® @ > &
v

12024 m2025




Land area cultivated by the top ten groundnut-producing States in 2025 compared with 2024
Benniseed
Benniseed production is estimated to rise modestly by 5.5% nationally, from 508,920.6 MT in 2024 to 536,826.9 MT in 2025, supported by a slight increase in land area to 539,760.1 ha. Benue (95,057.5 MT), Kogi (66,038.2 MT), and Nasarawa (61,794.9 MT) lead production, while output declines in Katsina, Sokoto, and Zamfara highlight regional disparities.

[image: image121.png]Metric Tonnes

800,000.00
700,000.00
600,000.00
500,000.00
400,000.00

300,000.00
200,000.00
100,000.00
0.00
N
o
¢> e~

2 \d o \d
) & S
s @ &
g

12024 m2025




Production estimates of the top ten benniseed-producing States in 2025 compared with 2024
[image: image122.png]600,000.00

500,000.00
400,000.00
£ 300,000.00
200,000.00
100,000.00 II “ II II
0.00
N @ Q@ 2 @
O \,e N <§' & & o N
& & & @ S Q@"’ 43'
e@

12024 m2025




Land area cultivated by the top ten benniseed-producing States in 2025 compared with 2024
Yam
National yam production is projected to rise by 2.2%, from 54,577,973.2 MT in 2024 to 55,784,098.6 MT in 2025, driven by a modest increase in cultivated land area from 6,335,594.7 ha to 6,448,454.7 ha. Niger remains the leading producer with 5,252,711.1 MT, followed by Nasarawa (3,967,605.2 MT) and Enugu (3,171,607.8 MT). At the same time, Benue, Edo, and Taraba each con- tribute over 2.8 million MT, reflecting yams’ concentration in the North-Central and southern producing states.

[image: image123.png]Metric Tonnes

100,000.00
90,000.00
80,000.00
70,000.00

60,000.00
50,000.00
40,000.00
30,000.00
20,000.00
10,000.00

0.00

& *_OQ‘ ﬁ\m ‘(o Q@ » ©

S & &
o ’;? & o S 5&’” + éé‘
K 15

w2024 m2025




Production estimates of the top ten yam-producing States in 2025 compared with 2024
[image: image124.png]90,000.00
80,000.00
70,000.00
60,000.00
50,000.00

©
T 40,000.00
30,000.00
20,000.00
10,000.00 I II
0.00 I “

\)0 O% 4&’5 (’ .O’b ,bo (g, 'b 0
ol il @ N Q
e \“&4, C o g N & v&

12024 m2025




Land area cultivated by the top ten yam-producing States in 2025 compared with 2024
Cassava
National cassava production is estimated to rise from 64.36 million MT in 2024 to 65.39 million MT in 2025, reflecting a 1.6% increase, alongside a 1.4% expansion in land area (9.28 to 9.42 million hectares). Key producers, Benue (+1.7%), Kogi (+1.7%), Imo (+1.7%), Ondo (+1.7%), and Rivers (+1.7%), continue to lead output, reinforcing cassava’s central role in household consumption and agro-industrial value chains.

[image: image125.png]6,000,000.00

5,000,000.00
"
8 4,000,000.00
N
© 3,000,000.00
2
]
8 2,000,00000
1,000,000.00
0.00
$ &2 & & &
s &° (é\ &7’@ & @é\ & & N ,§>°
& d

12024 m2025




Production estimates of the top ten cassava-producing States in 2025 compared with 2024
[image: image126.png]700,000.00
600,000.00
500,000.00
400,000.00

©

T
300,000.00
200,000.00
100,000.00
0.00

o ®
é‘o‘;’é& 'b@ <& s

12024 m2025

Qn’;

&

0\@

((C;

&

e
N




Land area cultivated by the top ten cassava-producing States in 2025 compared with 2024
Ginger
Ginger production posted a modest recovery, yet the industry continues to grapple with acute seed scarcity and high input costs following the 2023 blight, underscoring the long path to full restoration. Output is projected to rise by 1.8%, from 514,356 MT in 2024 to 523,614 MT in 2025, driven largely by a 1.3% expansion in cultivated area. Kaduna remains the powerhouse of national supply, contributing over 335,000 MT—an increase of 1.8%—while Nasarawa, Benue, and Bauchi also recorded marginal gains.

[image: image127.jpg]4,500,000.00

4,000,000.00
3,500,000.00
& 3,000,000.00
§2,soo,ooo4oo
£ 2,000,000.00
§1,500,000400
1,000,000.00
500,000.00
0.00
Q>®°Qe & & f\“ & ¢ <é‘°% o 1—”60
& ¥ N

m2024 w2025




Production estimates of the four major ginger-producing States in 2025 compared with 2024
[image: image128.png]700,000.00

600,000.00
500,000.00
400,000.00
@
T
300,000.00
200,000.00
100,000.00 II
0.00
@ @ . @
& & F & &
& & I FS
Q, Nl & <
& & F

12024 m2025




Land area cultivated by the four major ginger-producing States in 2025 compared with 2024
[image: image14.png]Yield (MT/Ha)

6

5

4

~

o3
“ |

~

ey N"’
|| | |

w2024 m2025

oy

- o s
II T

]





Crop yield outlook for 2024 and 2025
	Category
	Crops
	Notes

	Improving
	Yam (8.6 → 8.7), Tomato (4.5 →
4.6), Maize (2.2 → 2.3), Cowpea
(0.8 → 0.9)
	Small but positive growth, showing potential if supported with improved seeds, inputs, and extension.

	Stagnant
	Cassava (6.9 → 6.9), Plantain/
Banana (6.6 → 6.7), Ginger (6 →
6), Cocoyam (3.9 → 3.9), Onion
(2.5 → 2.5), Rice (2 → 2), Sor-
ghum (1.2 → 1.2), Groundnut
(1.2 → 1.2), Okra (1.1 → 1.1),
Millet (1 → 1), Benniseed (1 →
1), Soybean (0.9 → 0.9)
	No significant yield changes, reflecting limitations in technology adoption and input use.

	Declining
	Cotton (0.9 → 0.8)
	Worrying trend for the textile value chain,
requires urgent intervention.


[image: image129.png]400,000.00
350,000.00
300,000.00
g 250,000.00
'9 200,000.00

150,000.00

Metric

100,000.00

50,000.00 I I I I
0.00 ]

Kaduna Nasarawa Benue Bauchi

B2024 m2025



Livestock Diseases
[image: image130.png]40,000.00

35,000.00

30,000.00

25,000.00

£ 20,000.00

15,000.00

10,000.00
5,000.00 I I I I

0.00

Kaduna Nasarawa Benue Bauchi

12024 m2025




[image: image131.png]



[image: image15.jpg]



States with CBPP and FMD in Cattle (2025)
This map shows where cattle diseases occurred. CBPP affected many states, especially Sokoto and Gombe. FMD was reported in most zones, except the South-East.

[image: image132.jpg]Contagious
Bovine
Pleuropneumo
nia (CBPP)
was recorded
across all agro-
ecological
zones, with the
highest cases
in Sokoto
(1,730) and
Gombe (501)
states.

Foot and
Mouth
Disease
(FMD)
occurred in
some states
across most
zones, but
was not
reported in
the South-
East.
Helminthias
is was
limited to
Niger,
Benue, Edo,
Rivers, and
Ekiti states.

Peste des
Petits

Ruminants
(PPR) in
sheep and
goats
remained
widespread
and
endemic
across all
Zones.

Poultry

Diseases

Newcastle
Disease (NCD)
was the most
common
poultry
disease
nationwide.
Other poultry
diseases such
as Fowl
Typhoid, Fowl
Pox,
Coccidiosis,
Gumboro,
CRD, and IBD
were also
reported in
different
regions.




States with PPR in Sheep and Goats (2025)
PPR affected sheep and goats in almost all parts of the country, showing that the disease is
[image: image16.jpg]



States with Poultry Diseases (NCD, Gumboro, and Coccidiosis) in 2025
Newcastle disease was the main poultry problem across Nigeria. Gumboro and Coccidiosis also affected birds in some states with large poultry farms.

[image: image133.png]



States with African Swine Fever (ASF) in Pigs (2025)
ASF spread to many states, but Akwa Ibom recorded the highest number of cases, causing seri- ous losses to pig farmers.

Fisheries Situation
Fresh fish trade in 2025 showed mixed outcomes across zones. Cultured fish production fell sharply in the North-Central and North-East (about 30–35%), while the North-West recorded modest gains. The South-South remained stable in both cultured and captured fish, reflecting its strong base in natural fisheries. The South-West presented conflicting figures, pointing to volatility in aquaculture and data inconsistencies.

Overall, captured fisheries were relatively stable in the South-South and North-West, but declined in the North-East and North-Central, areas heavily affected by insecurity and flooding. The data highlight the need to strengthen aquaculture development, climate adaptation, and fisheries data systems, especially in vulnerable zones.

	Agroecological
zones
	Quantity of fresh fish traded (MT)

	
	Cultured
	Captured

	
	2024
	2025
	% Change
	2024
	2025
	% Change

	North-Central
	663,227.1
	413,000.5
	-37.73
	114,759.5
	131, 268.9
	14.39

	North-East
	27,624
	36,917
	-3.64
	13,637
	17,696
	29.76

	North-West
	17,600
	27,700
	57.39
	7525
	8474
	12.61

	South-South
	1247.68
	1224.76
	-1.84
	1259.13
	1290.65
	2.50

	South-West
	11824.6
	14460
	22.30
	5810
	101,941
	165.46


	Agroecological
zones
	Quantity of smoked fish traded (MT)

	
	Cultured
	Captured

	
	2024
	2025
	% Change
	2024
	2025
	% Change

	North-Central
	601,769
	425,905
	-29.22
	144,774.9
	153,434.9
	5.98

	North-East
	70,921
	93,751
	32.20
	31,373
	43,224
	37.77

	North-West
	1800
	1800
	0
	4734
	4135
	-12.65

	South-South
	435.74
	738.61
	69.51
	506.34
	506.88
	0.107

	South-West
	308,761
	28,074
	-90.91
	8025
	26795
	233.90


Agricultural Development Programme Extension Situations
[image: image134.jpg]T 7 T ¥ T 7 T





Extension Agent-Farm Families Ratio
[image: image135.jpg]



Extension agents to farm families ratio across some states in Nigeria
Conclusion and Recommendations
Conclusion
The 2025 Agricultural Performance Survey reveals that Nigerian agriculture remains a vital source of stability and opportunity, contributing to food security and economic growth. Production of rice, maize, cowpea, yam, cassava, and groundnut increased over 2024 levels, while food prices fell across all zones, reflecting improved supply and the effectiveness of ongoing interventions. The results also indicate considerable interest in mechanization, the broader adoption of improved inputs, and enhanced collaboration among research institutes, ministries, and farmer groups. Farmers demonstrated resilience in adapting to climate variability, and innovative datasets, such as the Farm Family Census and Tractor Census, enriched evidence-based policymaking. Notably, the findings highlight the need to complement the wet season APS with a Dry Season Agricultural Performance Survey, ensuring year-round monitoring and planning to meet Nigeria’s food and nutrition security targets.

Recommendations
Institutionalize the Dry Season Agricultural Performance Survey as a national complement to the wet season APS. This will provide year-round data for planning, guide in- vestments in irrigation and input distribution, and ensure food security strategies are based on a complete agricultural calendar.

Secure Affordable Inputs for Farmers by expanding domestic fertilizer production, digitizing subsidy targeting, and partnering with the private sector to guarantee timely and affordable delivery to farmers across all zones.

Accelerate Climate-Smart Agriculture by scaling up resilient crop varieties, expanding sustainable water management, and strengthening operational early warning systems to provide farmers with actionable climate information.

Transform Extension and Market Systems through Public–Private Partnerships, digital integration, and scalable grassroots models such as the Community-Based Advisor (CBA) approach.
Revolutionize Mechanization Access by combining tractor hiring schemes with the pro- motion of simple, labour saving devices that ease drudgery and open greater opportunities for women and youth in agriculture.

Protect Livestock and Fisheries Productivity by scaling up vaccination campaigns, veterinary surveillance, and aquaculture development, supported by robust data systems for evidence-driven interventions.

[image: image17.jpg]



[image: image18.jpg]



Registration of participants

[image: image19.jpg]



Participants discussing 

[image: image20.jpg]



Director of NAERLS with the Dir of IAR and other principal officers

[image: image21.jpg]



Members of the high table

[image: image22.jpg]i Y e™





Executive Director NAERLS presenting his opening speech

[image: image23.jpg]



Dr Godwin Atser (Country Director Sasakawa Africa Association) 
Keynote speaker 

[image: image24.jpg]



Dr Samuel Ankeli (former senior special adviser to the president on people with disability

[image: image25.jpg]



Prof Raymond Bako (DVC Academics ABU Zaria)

[image: image26.jpg]b en
et





Group Photograph (NAERPM 2025)

[image: image27.jpg]



ED NAERLS with the press

[image: image28.jpg]



Prof. Adetunji Oroye Iyiola - Tunji during the plenary session

[image: image29.jpg]



Prof A A Jamilu with the MC in discussion mode

[image: image30.jpg]


          

Prof. A. A. Jamilu responding to questions

[image: image31.jpg]



Exhibition stand                
[image: image32.jpg]



Exhibition stand

[image: image33.jpg]AL
NATIONAL AGRICULTURAL EXTENS

Federal





Exhibition stand

2025 REPORTS

                                     NARIs REPORTS
[image: image34.jpg]


                                                                                                                [image: image35.png]



Name of Research Institute: Forestry Research Institute of Nigeria (FRIN)
Postal Address: P.M.B 5054, Jericho Hills, Ibadan, Oyo State
Website: www. frin.gov.ng

E-mail:  dgfrin@frin.gov.ng, info@frin.gov.ng
Telephone:
0704760 4000, 08070947851








A.   EXTENSION SUPPORT ACTIVITIES

	SN
	Title
	No Proposed
	No Achieved
	Collaborators
	Remarks

	1
	Diagnostic survey
	--
	--
	
	

	2
	On-Station Research (OSR)
	05
	03
	Farmers, Agroforestry Practioners, NARIs
	

	3
	OFR
	
	
	
	

	4
	MTRM
	03
	01
	IAR&T
	

	5
	Joint Scientific Field Evaluation
	02
	01
	NISER
	

	6
	Field days
	01
	0
	
	

	7
	Zonal REFILS Workshop
	01
	01
	IAR&T
	-

	8
	Pre-season training
	05
	04
	Agroforestry Practitioners, Farmers and NARIs
	

	9
	Post season training
	05
	03
	Agroforestry Practitioners, Farmers and NARIs
	

	10
	Zonal Steering Committee Meeting
	01
	0
	
	

	11
	Zonal Technical Committee Meeting
	01
	0
	
	

	12
	In-house Review Meeting/Cropping Scheme Meeting
	01
	0
	
	

	13
	National Agricultural Extension Review and Planning Meeting (NAERPM)
	01
	01
	NAERLS, NARIs and ADPs
	

	14
	Adopted Village (Established)
	1
	0
	
	

	15
	Training Workshop (Participated)
	10
	05
	NARIs, Farmers, Agro Foresters, NGOs 
	

	16
	Training Workshop (Organized)
	10
	05
	NARIs, Farmers, Agro Foresters, NGOs 
	

	17
	Training Workshop (As Resource Person attended)
	10
	05
	NARIs, Farmers, Agro Foresters, NGOs 
	

	18
	Agric. Research & trade Fair
	02
	0
	
	

	19
	Research Institute Field Day
	01
	01
	Researchers, NARIs, Farmers 
	

	20
	World food day
	01
	0
	
	

	21
	Wet & dry season evaluation
	01
	0
	
	

	22
	National Agric. Shows, State, NGOs and others
	01
	0
	
	


B1.    TECHNOLOGY DEVELOPMENT

	S/No
	Technology Developed within the Year Under Review 
	Month Released
	Level of Acceptance (If any)
	Identified Areas Requiring Improvements

	1
	Silvicultural improvement of Faidherbia albida (Fertilizer Tree/Gao)
	Ongoing
	
	Collaboration with IAR and ADPs in the North 

	2
	
	
	
	

	3
	
	
	
	

	4
	
	
	
	

	5
	
	
	
	

	6
	
	
	
	


C.        EXTENSION PUBLICATIONS PRODUCED IN 2025
	SN
	Title
	Copies Targeted
	Copies Achieved
	Collaborators

	1
	Bulletins

FRIN innovative technologies and Research Breakthrough Guide
	3,000
	WIP
	Research Departments and Research Coordinating Unit

	2
	Guides

1. Mushroom production

2. Snailery production

3. Rabbitery production

4. Grassgutters production

5. Tree planting

6. Faidherbia albida 
7. Parkia biglobosa
8. Tamarindus indica
9. Adansonia digitata
10. Syzygium cumuni
	3,000

3,000

3,000

3,000

3,000

3,000

3,000

3,000

3,000

3,000
	WIP

WIP

WIP

WIP

WIP

WIP

WIP

WIP

WIP

WIP
	Research Departments and Research Coordinating Unit

	3
	Leaflets

Forest Economics and Extension

Forest Conservation and protection

Sustainable Forest Management

Forest Product Development and Utilization

Soil and Tree Nutrition

Environmental Modelling and Biometrics

Wildlife and Ecotourism


	3,000

3,000

3,000

3,000

3,000

3,000

3,000
	WIP

WIP

WIP

WIP

WIP

WIP

WIP
	Research Departments and Research Coordinating Unit


D.     RADIO PROGRAMMES
	SN
	Programme Title
	Proposed

Episodes
	No. Achieved 
	Number aired
	Collaborators
	Channels 

	1
	Farmers Programme
	5
	3
	3
	Farmers, Agroforestry Practitioners
	Agbarigbo and Crest FM Stations, Ibadan

	2

Etc.
	Whatsapp Audio Messages
	3
	3
	3
	Farmers, Agroforestry Practitioners
	Whatsapp


E     TELEVISION PROGRAMMES

	SN
	Programme Title
	Proposed

Episodes
	No. Achieved 
	Number aired
	Collaborators
	Channels 

	1
	Spend a Day With the Forest Community
	WIP
	WIP
	WIP
	NTAi
	NTAi


F.    TRAINING WORKSHOP
	SN
	Title
	Category of trainees
	No of trainees
	Collaborators
	Duration

	1
	Sustainable Forest Management
	Training the Trainers
	50
	Researchers, SMS
	Forthnightly

	2
	Forest Product Development and Utilization
	Training the Trainers
	50
	Farmers, SMS, Researchers
	Twice in a year

	3
	Capacity Building and Training of Nigeria’s Scientific Authority on Producing Scientifically Based Non-Detriment Findings (NDF) of Pterocarpus erinaceus in Nigeria
	Scientists, Trainers
	30
	Researchers
	3 days


G.    ADOPTED VILLAGES AND SECONDARY SCHOOLS
	SN
	Activities
	No. Proposed
	No. conducted
	Technologies Promoted
	Remarks

	1
	Ijaye Orile, Iseyin,Otiri,Olokemeji,Ikija,Omi Adio and Idowu Oko Farmers
	        02
	01
	Rabbitry Production
	

	2
	School outreach
	05
	02
	Tree Planting/Rabbitry Production
	


CONSTRAINTS: 

Inadequate funding

Insecurity

Name of Contact Person: Dr. Osikabor Benson

Post/Rank: Associate Research Professor

Phone Number: +234 810 410 6631
[image: image136.png]Weak Human
Resources

Most ADPs are severely under-
staffed. The extension agent-to-
farmer ratio in many states
remains far below the FAO-
recommended 1:800, with Ogun,
Sokoto, and Bauchi particularly

Funding
Instability

ADP financing remains uneven.
While States, such as Bayelsa
and Lagos demonstrated full
budget performance, others

like Nasarawa, Plateau, Sokoto

affected. and Ondo, recorded drastic
underfunding, crippling
extension delivery.
Inadequate Role of NGO
Logistics And Media

Non-governmental
organizations (e.g.. YMCA,
AFAN, Helen Keller, JDPI) and
agricultural radio
programmes are increasingly
filling extension gaps,
reaching millions of farmers
with training and awareness.





Name of Research Institute: Institute for Agricultural Research, Ahmadu Bello University, Zaria

Postal Address: P.M.B.1044 ABU Zaria, Kaduna state, Nigeria

Website:    www.iar.gov.ng                  E-mail: aminusharifai@gmail.com

Telephone:  +2348023790983







A.   EXTENSION SUPPORT ACTIVITIES
	SN
	Title
	No Proposed
	No Achieved
	Collaborators
	Remarks

	1
	Diagnostic survey
	5
	6
	NARIs
	Good

	2
	On-Station Research (OSR)
	5
	5
	NARIs
	Very Good

	3
	OFR
	8
	8
	NARIs
	Very Good

	4
	MTRM
	3
	-
	ADPs
	Poor

	5
	Joint Scientific Field Evaluation
	3
	5
	NARIs
	Excellent

	6
	Field days
	5
	5
	NARIs
	Very Good

	7
	Zonal REFILS Workshop
	1
	1
	ADPs
	Good

	8
	Pre-season training
	10
	12
	NARIs
	Excellent

	9
	Post season training
	4
	2
	NARIs
	fair

	10
	Zonal Steering Committee Meeting
	1
	-
	ADPs
	Poor

	11
	Zonal Technical Committee Meeting
	2
	-
	ADPs
	Poor

	12
	In-house Review Meeting/Cropping Scheme Meeting
	11
	11
	Research Programmes and other NARIs


	Very Good

	13
	National Agricultural Extension Review and Planning Meeting (NAERPM)
	1
	1
	NARIs
	Good

	14
	Adopted Village
	5
	4
	Villages & Schools
	Good

	15
	Training Workshop (attended)
	3
	5
	NARIs
	Excellent

	16
	Training Workshop (Organized)
	5
	5
	NARIs
	Very  Good

	17
	Training Workshop 

(As Resource Person)
	10
	5
	NARIs
	Fair

	18
	Agric. Research & trade Fair/expo
	4
	4
	NARIs
	Very Good

	19
	Research Institute Field Day
	1
	1
	NARIs
	Good

	20
	World food day
	1
	1
	NARIs
	Good

	21
	Wet & dry season evaluation
	1
	1
	NARIs
	Good

	22
	National Agric. Shows/others, state, NGOs
	1
	1
	NARIs
	Good


B.    TECHNOLOGY DEVELOPMENT

	S/No
	Technology Developed within the Review Year 
	Month Released
	Level of Acceptance (%)
	Identified Areas Requiring Improvements

	1
	MAIZE HYBRIDS: SAMMAZ 77
	17th April, 2025
	100%
	Farmers & Extension Agents Linkages

	2
	THREE BARLEY LINES (With Lake Chad Research Institute):
LACRISSAMBARLEY 1
LACRISSAMBARLEY 2
LACRISSAMBARLEY 3
	17th April, 2025
	100%
	Farmers & Extension Agents Linkages

	3
	PUBLIC – PRIVATE PARTNERSHIP THAT DELIVERED MORE MAIZE (Wish ETG Inputs Nigeria Limited)                                     M401, ETG M601 
WITH AGRISEED COM. NIGERIA LIMITED 

SC451, SC563 & SC618
	17th April, 2025
	100%
	Farmers & Extension Agents Linkages

	4
	PASTURE FOR LIVESTOCK (In collaboration with NAPRI): 
2 PATURE LEGUME LINES:                                 . SHIKALEGUME 1 & 2 
6 PASTURES GRASS LINES:               SHIKAGRASS 1 – 6
	17th April, 2025
	100%
	Farmers & Extension Agents Linkages


C.        EXTENSION PUBLICATIONS COPIES PRODUCED
	SN
	Title
	Copied Targeted
	Copies Achieved
	Collaborators

	1
	Bulletins

  Extension guide on our mandate crops and Machineries
	500 copies each
	500 copies
	Programme Leaders/ HOU

	2
	Guides

1. Crop varieties posters
2. Institute Brochure
	50 copies
1000 copies
	 
20
500
	Programme Leaders/ HOU

	3
	Leaflets

Leaflets on newly released crops varieties

Technologies for women (Leaflets)
Factsheet on TELA maize
	2,000 copies
500 copies
	 
2,000
100
	Programme Leaders/ HOU

AATF / FGN

	4
	Posters

1. Roll-up banners
2. Institute Poster
3. Institute Year Planner
	 
12
500
1000
	 
11
50
-
	Programme Leaders/ HOU

	5
	Others (specify)

1. This week in IAR & FOA
2. News Letter
	52 volumes
4 volumes
	 
43
2
	Programme Leaders/ HOU


D.     RADIO PROGRAMMES
	SN
	Topic
	Proposed number of airings
	No. Achieved
	Collaborators
	Channels 

	1
	Breakfast Show
	5
	3
	NARIs
	KSMC

	2
	None
	None
	None
	None
	None


E     TELEVISION PROGRAMMES
	SN
	Topic
	Proposed number of airing
	No. Achieved
	Collaborators
	Channels 

	1
	None
	None
	None
	None
	None

	2
	None
	None
	None
	None
	None


F.    TRAINING WORKSHOP
	SN
	Title
	Category of trainees
	No of trainees
	Collaborators
	Duration

	1.
	Biotech Crops in Nigeria: Myths, Fallacies and Facts.
	Research Scientists, Extension Agents, Farmers, Stakeholders, etc.
	200
	NARIs
	1 Days

	2.
	Catch them fresh training on empowering Academic Excellence at the Institute.
	IAR Research Scientists & Technical Staff
	70
	NARIs
	1 Day

	3.
	Training on Empowering Water Users for sustainable Agriculture at Garri irrigation Scheme, Roni Local Government, Jigawa state.
	Farmers, Extension Agents, Stakeholders.
	100
	NARIs
	1 Day

	4.
	A one-day sensitization workshop on Biosafety and Biotechnology.
	Members of the Nigerian House of Representatives committee on Agricultural Production and Services.
	170
	NARIs
	1 Day

	5.
	Capacity building training on Advancing Drip Irrigation in Jigawa & Kano states
	Extension Agents & Farmers
	100
	NARIs
	1 Days

	6.
	Workshop on Introduction and Participatory Evaluation of Climate Resilient Sorghum varieties for poverty reduction and nutrition improvement in Nigeria.
	Farmers & Extension Agents
	100
	NARIs
	1 Day

	7.
	Preseason training on Crop Ontology and Digital Data Management
	Technical Staff
	40
	ICRISAT, AVISA, ADCIN
	2 Day

	8.
	 
Orientation programme for newly appointed staff
	Staff
	70
	NARIs
	1 Days

	9.
	Workshop on Bt Cotton production and climate-Smart Agriculture.
	Cotton Farmers & Extension Agents.
	50
	NARIs
	1 Day

	10.
	Pre-Release Seminar for New Crop varieties (SAMMAZ 77, ETG M401, ETG M601, SC451, SC563 & SC618)
	Scientists, breeders, stakeholdersseed companies & regulatory agencies.
	80
	IAR
	

	11.
	Training on building farmers’ capacity in Good Agronomic practices (GAPs), post-Harvest techniques, and Agro-Business development across five major crop value chains: rice, maize, cowpea, sorghum, and millet.
	Farmers & Extension Agents
	100
	IAR, TELA Maize, PBR Cowpea & Hon. Minister of Budget & Economic planning (Senator Abubakar Atiku Bagudu,CON)
	

	12.
	Preseason training on Crop Ontology and Digital Data management
	Breeders, Technicians & Research Scientists
	200
	IAR, AVISA, ICRISAT & ADCIN
	

	13.
	Media training workshop on Communicating Agricultural Biotechnology
	Media staff
	25
	IAR & AATF 
	

	14.
	Capacity building training workshop of Stakeholders on Best Agro ecological Practices as a climate smart strategy for soil health and sustainable crop production.
	Extension Agents & Farmers
	70
	IAR & FMAFS
	


`

CONSTRAINTS: 

Dissemination of technologies to end-users

Inadequate funds to upscale proven technologies

Weak collaboration with state and local governments

Low-capacity print and media infrastructure 

Name of Contact Person: Prof. A. Sharifai

Post/Rank:   Professor

Phone Number:   08023790983

[image: image36.jpg]


                                                                                          [image: image37.wmf]
Name of Research Institute: Lake Chad Research Institute Maiduguri

Postal Address: P.M.B 1293 Maiduguri, Borno State 

Website: www.lcri.gov.ng         E-mail: infor@lcri.gov.ng

Telephone: 













A.   EXTENSION SUPPORT ACTIVITIES

	SN
	Title
	No Proposed
	No Achieved
	Collaborators
	Remarks

	1
	Diagnostic survey
	2
	0
	LCRI
	Not achieved

	2
	On-Station Research (OSR)
	60
	51
	LCRI/OLAM/AVISA/CIMMYT/ICARDA
	

	3
	OFR
	70
	57
	LCRI/OLAM/AVISA/CIMMYT/ICARDA
	Achieved

	4
	MTRM
	12
	4
	LCRI/ADPs 
	Achieved

	5
	Joint Scientific Field Evaluation
	3
	2
	LCRI/AVISA/NASC/NAGRAB/BREWERIES/OLAM
	Achieved

	6
	Field days
	3
	2
	LCRI/ADPs/NGOs/Farmers Asso
	Achieved

	7
	Zonal REFILS Workshop
	1
	1
	LCRI/NARIs/ADPs
	Achieved

	8
	Pre-season training
	2
	0
	LCRI/UNIMAID
	Achieved

	9
	Post season training
	2
	0
	LCRI/UNIMAID
	Not achieved

	10
	Zonal Steering Committee Meeting
	4
	0
	LCRI/ZONAL ADPs
	Not achieved

	11
	Zonal Technical Committee Meeting
	2
	0
	LCRI/ZONAL ADPs
	Not achieved

	12
	In-house Review Meeting/Cropping Scheme Meeting
	1
	0
	LCRI/ADPs
	Not achieved

	13
	National Agricultural Extension Review and Planning Meeting (NAERPM)
	1
	1
	NAERLS/ADPs/NARIs
	Achieved 

	14
	Adopted Village (Established)
	2
	0
	LCRI/CRS/ AND ICRC
	Not achieved

	15
	Training Workshop (Participated)
	8
	4
	LCRI/CRS/ AND ICRC
	Achieved

	16
	Training Workshop (Organized)
	5
	2
	LCRI
	Not achieved

	17
	Training Workshop (As Resource Person attended)
	5
	3
	LCRI
	Achieved

	18
	Agric. Research & trade Fair
	1
	0
	LCRI/KANO MINISTRY OF TRADE AND INVESTMENT
	Not achieved

	19
	Research Institute Field day
	3
	1
	LCRI/FARMERS/NGOs/FMAFS/State Govt
	Achieved

	20
	World food day
	1
	0
	
	Not achieved

	21
	Wet & dry season evaluation
	2
	2
	LCRI/ALL NARIS
	Achieved

	22
	National Agric. Shows, State, NGOs and others
	1
	1
	National Agric Foundation/Naris/Farmers

NGOs/Input Dealers Agencies/ State& Local Govt Council
	Achieved


B1.    TECHNOLOGY DEVELOPMENT

	S/No
	Technology Developed within the Year Under Review 
	Month Released
	Level of Acceptance (If any)
	Identified Areas Requiring Improvements

	1
	LACRISambal – 1 ( C17-295-016)
	2025
	APRIL 2025
	

	2
	LACRISambal – 2 (C17-295 – 069)
	2025
	APRIL 2025
	

	3
	LACRISambal – 3 (C17-295 – 070)
	 2025
	APRIL 2025
	

	4
	
	
	
	

	5
	
	
	
	

	6
	
	
	
	


B2.    CLIMATE RESILIENT TECHNOLOGY DEVELOPMENT

	S/No
	Climate Resilient Technology Developed within the Year Under Review 
	Month Released
	Level of Acceptance (If any)
	Identified Areas Requiring Improvements

	1
	
	
	
	

	2
	LACRIWHT – 19 (SC W9103)
	APRIL 2025
	
	

	3
	LACRIWHT – 20 (SC W9105)
	APRIL 2025
	
	

	4
	LACRIWHT – 21 (SC W (9106)
	APRIL 2025
	
	

	5
	LCICMH-2 (High Zinc)
	APRIL 2025
	
	

	6
	LCICMH-3 (High Iron & Zinc)
	APRIL 2025
	
	

	7
	LCICMH-4 (High Iron & Zinc)
	APRIL 2025
	
	

	8
	LCICMH-5 (High Zinc)
	APRIL 2025
	
	

	
	
	
	
	


C.        EXTENSION PUBLICATIONS PRODUCED IN 2025
	SN
	Title
	Copies Targeted
	Copies Achieved
	Collaborators

	1
	Bulletins

1. Value Addition on the mandate crops

2.

3.

Etc. 
	4
	1
	LCRI

	2
	Guides

1. Improved millet 

2. Improved wheat

3. Improved Barley

Etc.
	500
	0
	LCRI

	3
	Leaflets

1. 

2.

3.

Etc.
	750
	0
	LCRI

	4
	Posters

1. 

2.

3.

Etc.
	
	
	

	5
	Others (specify)

1. 

2.

3.

Etc. 2025 LCRI year Planner
	1000
	0
	LCRI


D.     RADIO PROGRAMMES
	SN
	Programme Title
	Proposed

Episodes
	No. Achieved 
	Number aired
	Collaborators
	Channels 

	1
	Faraskiram Barewuye
	52
	13
	13
	LCRI/AVISA
	BRTV Maiduguri

	2

Etc.
	Filin Monoma


	52
	13
	13
	LCRI/AVISA
	FRCN/Peace FM Maiduguri


E     TELEVISION PROGRAMMES

	SN
	Programme Title
	Proposed

Episodes
	No. Achieved 
	Number aired
	Collaborators
	Channels 

	1
	Faraskiram Barewuye
	27
	13
	13
	LCRI/AVISA
	NTA Maiduguri

	2

Etc.
	TV Documentary in English On Our Mandate Crops


	27
	13
	13
	LCRI/AVISA
	NTA Maiduguri


F.    TRAINING WORKSHOP
	SN
	Title
	Category of trainees
	No of trainees
	Collaborators
	Duration

	1
	North East Zonal Refils Workshop

	Farmers & ADPs
	106 


	LCRI/Zonal ADPS


	Four Days 



	2

Etc.
	Improved Cultural and Management Packages for Wheat Production In Nigeria
	Farmers


	100
	LCRI/OLAM AGRI 


	Two Days

	
	
	
	
	
	


G.    ADOPTED VILLAGES AND SECONDARY SCHOOLS
	SN
	Activities
	No. Proposed
	No. conducted
	Technologies Promoted
	Remarks

	1
	Production of improved millet variety/ at mustapha umar el-kanemi school farm


	2
	0
	
	

	2
	Class lecture session for students on agronomic practice of improved millet production technologies
	1
	0
	
	


CONSTRAINTS:
Low funding from capital project affected the conduct of pre-season trainings for both the rain fed and irrigated agricultural production during the review year.

In adequate funding of the ADPs: This affected the non-conduct of the MTRM in Adamawa and Borno State ADPs.
Dwindling personnel: The number of extension staff has decreased in the ADPs, thus worsening the low 

ratio of extension to the farmers
Name of Contact Person: Dr. Jidda Umar
Post/Rank: Chief Research Officer/ HOD Agric Econs & Extn

Phone Number: 08032275499

[image: image137.png]25000 47708

20000
15732
> 15000
£
£
g
3
5
g
g ! 9403
' 10000 9000 ggoo
7197
6250
5199
5000 4600 4186 500
3292
I I I 1111 1000
0 | I |
SR R R R I S R R
&8 & & S <& & S & ¢ e &
o & <
A T R FF g W &€



[image: image138.png]The
average
EA-Farm
families
ratio in
2024 is
1:6,446



                                                                                                                              

Name of Research Institute: National Agricultural Extension and Research Liaison Services (NAERLS)
Postal Address: NAERLS, ABU Zaria, P.M.B. 1067, Zaria, Kaduna State, Nigeria.

Website: www.naerls.gov.ng                                         
E-mail: director@naerls.gov.ng 

Telephone: 08056694565















A.   EXTENSION SUPPORT ACTIVITIES

	SN
	Title
	No Proposed
	No Achieved
	Collaborators
	Remarks

	1
	Diagnostic survey (Post Graduate Research)
	84
	87
	
	

	2
	On-Station Research (OSR)
	-
	-
	
	

	3
	OFR
	-
	-
	
	

	4
	MTRM
	-
	-
	
	

	5
	Joint Scientific Field Evaluation
	-
	-
	
	

	6
	Field days
	-
	-
	
	

	7
	Zonal REFILS Workshop
	6
	4
	Cross Rivers ADP, IAR & T, NRCRI, IAR, LCRI
	

	8
	Pre-season training
	5
	5
	AshakaCem Agric. Ecology Project
	

	9
	Post season training
	-
	
	
	

	10
	Zonal Steering Committee Meeting
	24
	1
	
	

	11
	Zonal Technical Committee Meeting
	6
	1
	
	

	12
	In-house Review Meeting/Cropping Scheme Meeting
	1
	1
	
	

	13
	National Agricultural Extension Review and Planning Meeting (NAERPM)
	1
	1
	
	

	14
	Adopted Village
	40
	38
	
	

	15
	Training Workshop (attended)
	45
	61
	
	

	16
	Training Workshop (Organized)
	96
	70
	
	

	17
	Training Workshop (As Resource Person)
	-
	9
	
	

	18
	Agric. Research & trade Fair/expo
	-
	
	
	

	19
	Research Institute Field day
	2
	
	
	

	20
	World food day
	1
	
	
	

	21
	Wet & dry season evaluation
	2
	1
	
	

	22
	National Agric. Shows/others, state, NGOs
	-
	
	
	


B.    TECHNOLOGY DEVELOPMENT

	S/No
	Technology Developed within the Review Year 
	Month Released
	Level of Acceptance (%)
	Identified Areas Requiring Improvements

	1
	Establishment of SERVICOM Unit
	
	
	

	2
	Establishment of Agroforestry and Woodlot across 6 LGAs. 
	
	
	

	3
	Developed protocols on Livestock Farmers Field School establishment for L-PRES

	
	
	

	4
	Development of National Farm Mapping, Advanced Farmer, Farm and Crop Mapping Solution
	
	
	

	5
	Ware yam/ maize Production
	
	
	

	6
	Small plot cassava production
	
	
	


C.        EXTENSION PUBLICATIONS COPIES PRODUCED
	SN
	Title
	Copied Targeted
	Copies Achieved
	Collaborators

	1
	Bulletin

Carrot Marketing, Processing and Utilization in Nigeria

Maintenance of tractor diesel fuel system

Jatropha Oil Extraction

Groundnut production under Irrigation

Farm Business Analysis using Bench Marking Approach Published (Bulletin No. 367)

Community Communication Process for Agricultural Extension 
Visit

Farm Business Analysis using Bench Marking Approach. Published (Bulletin No. 367)

Techniques for sourcing vital information on agricultural 
research for extension personnels and farmers

Planning and Decision Making in Vegetable Production 

The Use of Some Selected Social Media Platforms in Agricultural Extension Delivery

Procedure for Writing Agricultural Broadcast script

Production and Use of Video Animation in Agricultural Practices

Production and Use of Visuals in Agricultural extension leaflets.

Rubber production, processing, utilization and marketing in Nigeria

Use of ODK and Google Form for Agricultural Data Collection.

Basic knitting skills using the knitting machine

PRODUCTION AND UTILIZATION OF BEETROOT IN NIGERIA

Mobilizing for viable Gender Based Cooperative Societies

Community Communication Process for Agricultural Extension Visits

Agricultural Extension Communication Approach in Intercultural Farming 
Community Conflict Resolution

Goat milk production and Utilization

Production and use of maggot meal as feeds in fish farming

Rubber Production, Processing, Utilization and Marketing in Nigeria.

Establishment and management and conservation of Browse plants


	86
	24
	

	2
	Guides

Production of Irish Potatoes (Extension Guide No.8 translated to Hausa Ajami)

Cowpea Storage Using PICS Bags for Small Holder Farmers

Extension guides on enhancing farm labor efficiency for small holder farmers in Nigeria

Solar System Energy Generation: Options for Calculation in small farm

Brooding management
	72
	5
	

	3
	Leaflets

1. 
	
	
	

	4
	Posters

1. 
	
	
	

	5
	Others (specify)

Chapters in Book

Roles of Adopted Village Concept in Youth and Women   Entrepreneurial Skills Development
WATER YAM PRODUCTION, PRIMARY AND SECONDARY PROCESSING AND NUTRITIONAL COMPOSITION AND ANALYSIS OF ITS QUALITY

GOOD AGRICULTURAL PRACTICES OF WATER YAM PRODUCTION

SHEA NUT TREE CATERPILLARS (CIRINA BUYTROSPERM): HARVESTING, PROCESSING, NUTRITION AND UTILIZATION

Extension services: Bridging research and practice

Upscaling Nature-Based Solutions for Climate 
Change Adaptation in the Nigerian Agricultural Sector: Issues and 
Concerns.

GIS in livestock and fisheries management

Gender Analysis and Human Rights in 
Agriculture

Current Trends in Livestock Research, In Trend in fisheries and livestock research and extension in Nigeria

FISHERIES AND LIVESTOCK DEVELOPMENT IN NIGERIA FOR FOOD AND NUTRITION SECURITY

CURRENT TRENDS IN LIVESTOCK RESEARCH

CURRENT TRENDS IN LIVESTOCK AND FISH DISEASE CONTROL AND PREVENTION

EXTENSION SERVICES: BRIDGING RESEARCH AND PRACTICE

CHALLENGES TO FOOD AND NUTRITION SECURITY IN NIGERIA

INNOVATIONS AND TECHNOLOGIES IN FISHERIES AND LIVESTOCK

CASE STUDIES AND SUCCESS STORIES IN THE FISHERIES, AQUACULTURE AND LIVESTOCK SECTORS

MAPPING OF MARKET AND MARKET ACTORS ALONG THE RICE-FISH VALUE CHAINS FOR IMPROVED FOOD AND NUTRITION SECURITY IN LIBERIA

Sustainable Food Production: Threats and Opportunities: In Building a Resilient Root and Tuber Crops Farming System for Prosperity

Trends and Opportunities in smallholder agribusiness

Climate Change and Sustainable food production: Impact and Mitigation Strategies


	
	20
	


D.     RADIO PROGRAMES

	SN
	Topic
	Proposed number of airing
	No. Achieved
	Collaborators
	Channels 

	1
	Importance of Extension Agents to Farmers (Hausa version)
	1
	1
	NAERLS
	ABU FM 101.1 Radio Station

	2
	Mu raya Karkara
	1
	1
	AshakaCem Agric. Ecology Project
	ABU FM RADIO

	3
	Importance of Farmers Field Day (Hausa version)
	1
	1
	NAERLS/AshakaCem Agric. Ecology Project
	Gombe Media Cooperation Ltd

	4
	AGRA NAERLS KADUNA CONSORTIUM PROJECT ACTIVITIES IN KADUNA STATE


	1
	1
	NAERLS
	ABU FM RADIO

	5
	Organic agriculture
	1
	1
	NAERLS
	

	6
	Smart Agriculture
	1
	1
	NAERLS
	

	7
	Cowpea relay cropping in Maize farm
	1
	1
	NAERLS
	

	8
	Pro Vitamin A Maize production
	1
	1
	NAERLS
	

	9
	Farmer Capacity Advancement during price crashing of farm produce
	1
	1
	NAERLS
	

	10
	White & Brawn Cowpea production technique during the wet-season
	1
	1
	NAERLS
	

	11
	Climate change & how it affects farmer
	1
	1
	NAERLS
	FRCN (Jakar Magori)

	12
	Harvesting, processing and storage of Rice crop
	1
	1
	NAERLS
	

	13
	Post season Maintenance & storage of Tractor and implements
	1
	1
	NAERLS
	

	14
	Post season maintenance and storage of tractor and its implement
	1
	1
	NAERLS
	ABU FM, Zaria

	15
	Yadda ake kula da tarakta da kayan aikin ta, musamman bayan kamala ayyukan kaka

	1
	1
	NAERLS
	FRCN, Kaduna

	16
	Baturen Gona Group Dynamics (Amfanin kafa kungiyoyin Gama kai da yadda ake tafiyar dasu)
	1
	1
	NAERLS
	Samaru FM

	17
	Murara karkara Ingantaccan tsarin Girbin Masara da Ajiya
	1
	1
	NAERLS
	Farm Broadcast NAERLS/ABU

	18
	Agric Panorama
	48
	19
	NAERLS
	ABU FM

	19
	Noman Zamani
	48
	24
	NAERLS
	FRCN, Kaduna

	20
	Mu Raya Karkara
	48
	4
	NAERLS
	Gombe State Radio

	21
	Pest and Disease Management in Sweet Potato Production
	1
	1
	NAERLS
	FRCN

	22
	Good Agronomic Practices of Maize
	1
	1
	NAERLS
	FRCN

	23
	Noman shinkafa a ilimance
	1
	1
	NAERLS
	ABU Zaria FM

	24
	Hanyoyin Rage Asarar Kayan Gona Bayan Girbi
	1
	1
	NAERLS
	ABU Zaria FM

	25
	Abubuwan Dake Haifar Da Tsatsar Shinkafa Da Matakan Magance Ta
	1
	1
	NAERLS
	ABU Zaria FM

	26
	Noman Waken Soya a Ilimance
	1
	1
	NAERLS
	ABU Zaria FM

	27
	Ingantaccen Tsarin Girbin Gero da Ajiya
	1
	1
	Ashaka-Cem
	

	28
	Ingantaccen Tsarin Girbin Waken Soya da Ajiya
	1
	1
	Ashaka-Cem
	

	29
	Baturen Gona
	48
	21
	NAERLS
	ABU FM

	30
	Kitchen Deligt
	1
	1
	NAERLS
	

	31
	Fiber what it is and what it does
	1
	1
	NAERLS
	

	32
	Formulation of breakfast for adults
	1
	1
	NAERLS
	

	33
	Cooking on a budget
	1
	1
	NAERLS
	

	34
	Hanyoyin inganta hatsi da kara mashi daraja
	1
	1
	NAERLS
	

	35
	EGG GLUT AND PROCESSING TO POWDER
	1
	1
	NAERLS
	ABU 101.1 FM

	36
	Dabarun kiwon Awaki da Tumaki
	1
	1
	NAERLS
	

	37
	Brooding day-old chicks using Local materials
	1
	1
	Poultry Farmers Association Bida, Niger State
	Bida F.M, Niger State

	38
	Technology Involves in preparing broiler Feeds using locally available Source of Feeds ingredients.
	1
	1
	Poultry Farmers Association Bida, Niger State
	Bida F.M, Niger State

	39
	Harvest Plus/NAERLS nutritive value of soybean
	1
	1
	Harvest Plus & NAERLS


	

	40
	Precaution and Hazard of Agro Chemicals
	1
	1
	CANDEL, NAERLS, IAR & IAR and T.


	

	41
	Awareness of the National Farmers Helpline Centre
	1
	1
	NAERLS
	

	42
	Ayyukan Cibiyar amsa Korafe Korafen Manoma
	1
	1
	NAERLS
	

	43
	Commodity prices - Daga kasuwanninmu, weekly episodes
	48
	48
	
	

	44
	Ayyukan Kungiyar Sashen Koyarda Sana’o’I da inganta Kananan Masana’antu
	1
	1
	NAERLS
	ABUc101.1 FM

	45
	Kebi ma palu
	1
	1
	NAERLS
	

	46
	L’atoju  Oja
	1
	1
	NAERLS
	

	47
	Commodity Trend
	1
	1
	NAERLS
	


E     TELEVISION PROGRAMMES
	SN
	Topic
	Proposed number of airing
	No. Achieved
	Collaborators
	Channels 

	1
	Farmers Groups Formation and Management (A Smarth Approach)
	
	
	AGRA Kaduna Extension, Market and Agricultural Regeneration Consortium Project


	

	2
	NAERLS Farming Smart YouTube Channel Series
	
	41
	AGRA/NAERLS
	

	3
	WOFAN ICON Ikara community entry (short documentary)
	1
	1
	WOFAN
	

	4
	Rice production (WOFAN)short documentary
	1
	1
	WOFAN
	

	5
	Agra Kaduna Consortium Green field days
	1
	1
	AGRA
	NAERLS Farming Smart YouTube Channel

	6
	Production of stakeholders’video for NAERLS – Ashakacem Agric Ecology

	1
	1
	Ashakacem Agric Ecology

	

	7
	Production of video on snails infestation on cabbage and control for NAERLS – Ashakacem Agric Ecology

	1
	1
	Ashakacem Agric Ecology

	

	8
	Production of video on striga infestation on Guinea corn and control for NAERLS – Ashakacem Agric Ecology

	1
	1
	Ashakacem Agric Ecology
	

	9
	AGG production series
	
	
	
	

	10
	Ashaka Cem Agric Ecology Production series
	
	
	Ashaka Cem Agric Ecology Project
	

	11
	PBRC/AATF Production series
	
	
	AATF
	

	12
	Baturen Gona
	
	21
	NAERLS
	Facebook

	13
	Agric. Panorama
	
	
	NAERLS 
	Agric Media, South West Zone


F.    TRAINING WORKSHOP
	SN
	Title
	Category of trainees
	No of trainees
	Collaborators
	Duration (day)

	1
	Training on Data collection survey instrument tool for Farmers profile under Adopted Villages and Schools Outreach to develop farmers Database
	NAERLS Staff
	25
	NAERLS
	1

	2
	Preseason Training on Maize, Rice, Soybeans Production, Seasonal Climate Prediction and Field Mapping for Giwa, Sabon Gari and Zaria LGA Adopted Village Farmers

	Adopted Villages farmers from Giwa, S/gari and Zaria LGAs, Kaduna State
	187
	NAERLS
	7

	3
	Pre-Season Training on Good Agronomic Practices for Maize, Rice and Soybeans
	Adopted Villages farmers from T/Iya, Funtua LGA, Katsina State

	45
	NAERLS
	1

	4
	Pre-Season Training on Maize, G/Nut, Millet and Soybeans Production
	Farmers in Ashaka, Bajoga and Bage, Districts in Funakaye LGA, Gombe State.
	339
	AshakaCem
	3

	5
	Pre-Season Training on Good Agronomic Practices for Maize, Rice and Soybeans
	Atiku and Piyau Farmers ,Akko LGA, Gombe State
	238
	AshakaCem
	2

	6
	Training on Good Agronomic Practices for  Cabbage,Onion and Tomato
	Ashaka, Gongila and Juggol  Farmers ,Funakye LGA, Gombe State
	
	AshakaCem
	1

	7
	L-PRES Training
	Kaduna state livestock farmers
	
	
	

	8
	Economic way of estimating crop yield and post-harvest losses using crop-cutting technique
	Agric. Econs. Programme/Institution staffs
	
	
	

	9
	Supporting women and girls in leadership, decision-making and agribusiness leveraging agricultural knowledge and innovation


	AGRA Kaduna consortium project
	
	
	

	 10
	Building strong market linkages and effective partnerships with stakeholders
	AGRA Kaduna consortium project
	
	
	

	11
	SWAY AgFin Project
	Enumerators
	
	
	

	12
	Building Resilient Food Systems
	
	
	
	

	13
	SWAY AgFin Project
	Agricultural Prime Anchors and Enumerators
	
	
	

	14
	Skills 2 Wealth Programme
	189 selected individuals across the 7 North-West States
	
	
	

	15
	Meaning And Importances of Economics in Poultry Production
	Adopted village 
	
	
	

	16
	Building Resilient Food Systems
	Trainee
	
	
	

	17
	Conflict resolution in L-PRES Project
	L-Press Beneficiaries
	
	L-Press
	1

	18
	Animal Nutrition in L-PRES Project
	L-Press Beneficiaries
	
	L-Press
	1

	19
	Participatory Irrigation Water Management (PIWM)

	
	60
	NRF: SWAT modeling research
	1

	20
	2025 Seasonal Climate Prediction in Northern Nigeria
	NAERLS Staff
	15
	NAERLS
	1

	21
	Myths and Realities of Plagiarism: Discourse for high impact and sustainable Extension communications
	NAERLS Staff
	60
	NAERLS
	1

	22
	How to write a winning proposal for a grant award
	NAERLS Staff
	
	NAERLS
	1

	23
	Training on identification, Analysis, interpretation and Communication of Emprical Research Results
	NAERLS Staff
	35
	NAERLS
	1

	24
	Workshop on grant acquisition and writing techniques
	NAERLS Staff
	30
	NAERLS
	1

	25
	Identification of Research question and data analysis
	NAERLS Staff
	
	NAERLS
	

	26
	NFHL REFRESHER TRAINING
	NAERLS Staff and Corpers
	30
	NAERLS
	2

	27
	Carbon Credit and Financing
	AEAS, CBAs, Staff and Students
	80+
	AGRA
	1

	28
	How to write a proposal for a Grant Award
	NAERLS Staff
	
	NAERLS
	

	29
	Identification, Analysis, interpretation and communication of empirical Research Results
	NAERLS Staff
	
	NAERLS
	2

	30
	Anti- Corruption and Transparency  
	NAERLS Staff
	
	NAERLS/ICPC
	1

	31
	Grounding AI in Practice: Extensionist Insight for Digital Advisory Tools
	Extension Personnel
	25
	IFPRI
	1

	32
	Capacity Building Training for Girl Child Empowerment
	Girls Child
	
	Center for Girl Child
	

	33
	Capacity building of the Gender Focal Person (GFPs) of NARIs and FCAs
	NARIs Staff
	
	ARCN/NARIs
	1

	34
	Sensitization on the Use of Academic Networking Platforms for Enhanced Visibility


	NAERLS Staff
	
	
	1

	35
	Guide on fish feeding
	Farmers
	300
	Inner circle friends Club of Nigeria and FFN
	1

	36
	Training on Marketing Linkages for AGRA-BAYER Vegetables CBAs
	CBAs
	20
	AGRA, NAERLS and Bayer
	1

	37
	Training of CBAs on seedling production for sustainable agroforestry and climate resilience in Kaduna State
	CBAs and AEAs
	200
	AGRA, NAERLS, FRIN, DAC, EcoClimate
	2

	 38
	Horticultural Training for Out of School Girl
	Girls
	30
	NAERLS
	30

	39
	Effective Leadership Skills
	
	
	SPESSECE
	2

	40
	Operation of Drone for TV production
	Producers/ Cameramen/ Non-linear Editors
	
	Soundmind Events Media
	3

	 41
	Camera Handling Technique
	Cameramen
	
	Soundmind Events Media
	3

	42
	Modern technique in Non-Linear Editing
	Non-Linear Editors
	
	Soundmind Events Media

	3

	43
	Staff training on Briquette Production for Income Generation
	
	
	
	1

	44
	Training on Food Processing and Preservation on Tomatoes, Maize, Rice, Date and Spice Under CGE (1st and 2nd Cohort) 


	Girls Child
	
	Girls Child
	4 Months 

	 45
	Training of kwarbai women multipurpose group on composite flour production for pasrteries and confectioneries.


	Women group
	
	Girls Child
	1

	46
	Pre-season training of 150 women and youths in Dukku/Nafada Federal constituency Gombe State, on vegetable and livestock production/fattening.
	farmers
	
	Hon. Abdullahi El. Raheed. Member representing Dukku/Nafada Federal constituency.
	2

	47
	Training on Economic sources of cooking in collaboration with Adopted Village
	Giwa, Sabo-gari, and Zaria AROC
	
	NAERLS, Adopted Village
	3

	48
	Training workshop to profile beneficiaries on animal nutrition and feed management
	Livestock Farmers
	200
	NAERLS
	5

	49
	Training of Enumerators on Data Capturing of Adopted Village Farmers and Farmer cooperatives using ODK Collect in Giwa, Sabon Gari and Zaria LGAs Kaduna state
	Selected NAERLS staff and SIWES students for the Enumeration
	
	NAERLS, Adopted Village
	1

	50
	GENERAL REQUIREMENTS FOR POULTRY FARMING
	NAERLS Staff
	30
	NAERLS
	1

	51
	POULTRY SPECIES AND BREEDS
	
	30
	NAERLS
	1

	52
	HOUSING FOR LAYERS
	
	30
	NAERLS
	1

	53
	Training on creation of knowledge product digital content
	NIFAAS Members
	100
	NAERLS, NIFAAS
	1

	54
	Gender and Inclusivity Concepts
	NIFAAS Members
	30
	NAERLS, NIFAAS
	1

	55
	Transforming Nigeria’s Livestock Sector with National Animal Identification and Traceability System content.
	NIFAAS Members
	40
	NAERLS, NIFAAS
	

	56
	ICERFE Technology Commercialization Workshop
	Students, Academicians, Researchers
	40
	
	1

	57
	Training of Kusopa Woman Cooperative Adopted Village on Palm Oil 
Value Chain
	
	
	NAERLS & NIFOR
	

	58
	Mid-season training on GAP for AGRA/ONYX Rice farmers growers in Niger State, Bida Zonal office.
	Rice Farmers
	
	Onyx/AGAN/AGRA/Alluvial and Niger Foods
	

	59
	Two days training on the Soybean Value chain
	Farmers
	
	Harvest Plus and UNICEF
	

	60
	One day capacity building on gender responsive policy analysis in Nigeria Agric-food sector: An application of GAPO and WEAGOV
	
	
	
	

	61
	Use of ODK app for data collection (2nd -3rd Phase L-PRES Borno)


	Enumerators
	
	GIBKAM CONSULT NIGERIA limited
	1

	62
	Training on Goat Production
	
	
	National Directorate of Employment
	1

	63
	Pilot Survey (Wet Season), Borno, For selected Crops
	Enumerators
	
	PFSCU-NAPM
	1

	64
	use of ODK collect app for APS 2025 data collection 
	Enumerators
	
	NAERLS, FMAFS and Research Institutes
	1

	65
	Training of the NFHL call agents on the use of the call center application
	Call Agents
	
	
	

	66
	Training of the NYSC member call agents on the use of the call center application
	NYSC Members
	
	
	1

	67
	Data Analysis Using R- Software on Discord App


	
	
	
	

	68
	Training SIWES Students on GAP for different crops
	
	
	
	

	69
	Training course on “productivity enhancement of cotton by using modern agronomic practices”.
	
	
	
	

	70
	Genetic engineering and genetically modified organisms (GMOs). 
	
	
	
	

	71
	Training course on “Eco-Friendly Livestock Production Practices for Sustainable Agriculture”. 
	
	
	
	

	72
	Training course on “Disease Control, pesticides, Spray Pumps and Fertilizers in Cotton”. 
	
	
	
	

	73
	Training course on “Exploring Water Energy-Food Security Nexus for Sustainable Development in OIC Countries”. Conducted by SESRIC
	
	
	
	

	74
	Training course on “Soft Skill and Entrepreneurship”. 
	
	
	
	

	75
	SERVICOM Capacity Building Workshop
	
	
	SERVICOM Headquarters, The Presidency, in collaboration with NAERLS


	4

	76
	Grand Acquisition/Sourcing Training


	NAERLS
	
	NAERLS
	1

	77
	Training on data collection tool for optimum/NADF/FMARD dry season farming – Baseline and feasibility survey on selected irrigation sites in the South East Zone.
	NAERLS, ADPs, FMAFS,and FMARD
	
	NAERLS, FMAFS, NADF and Optimum Seeds production
	1

	78
	Optimum/NADF/FMARD Dry season farmers profiling and Baseline Survey on irrigation cluster in the South Eastern Nigeria.
	All zonal staff
	
	NAERLS, FMARM, NADF and Optimum Seeds Nig. Ltd.
	11

	79
	Enumeration of farmers on the targeted Agricultural information. Delivery Approach on resilience and livelihood outcome of maize farmers in Nigeria.
	
	
	NAERLS and ABSU
	

	80. 
	Steward workshop on MON89034 TELA maize
	NAERLS, Seed companies, AATF, UniAbuja, etc.
	
	AATF, NAERLS, Registered seed companies, UniAbuja
	2

	81
	Youth leadership and climate action – youth in the driver’s seat:  leading climate solutions through smart agriculture
	
	
	NAERLS, ADP, MOA, MOUAU, etc.
	1

	82
	NAERLS–CGE Partnership on Entrepreneurship Skills Capacity Building Training for out-of- School/Vulnerable Girls on Poultry Production (One Cohort)


	Girl Child Education
	30
	NAERLS, Gild Child Education
	

	83
	NAERLS–CGE Partnership on Entrepreneurship Skills Capacity Building   Training 
 for out-of-School/Vulnerable Girls on Fisheries Production (One Cohort)
	Girl Child Education
	30
	NAERLS, Gild Child Education
	

	84
	NAERLS–CGE Partnership on Entrepreneurship Skills Capacity Building Training   
for out-of- School/Vulnerable Girls on Food Processing (Cohorts-one)
	Girl Child Education
	30
	NAERLS, Gild Child Education
	

	85
	Tomatoes sack farming techniques for landless farmers
	ADP Staff and Farmers, Industrial Training (IT) student under ADP and Staff of NAERLS SS Zone
	
	Rivers State ADP & NEARLS SS Zone
	1

	86 
	Climate Smart Rice-Fish integrated farming: A sustainable solution for food security
	ADP Staff and Farmers, Industrial Training (IT) student under ADP and Staff of NAERLS SS Zone
	
	Rivers State ADP & NEARLS SS Zone
	1

	87
	Yam Minisett Technology: A panacea for rapid seed yam multiplication
	Adopted village farmers and Staff of NAERLS SS Zone
	
	
	1

	88
	Good agronomic practices for ware yam production in Port Harcourt
	Adopted village farmers and Staff of NAERLS SS Zone
	
	
	1

	89
	Fodder Production and Conservation
	Ruminant animal Farmers, Extension Agents from all ADPs and Ministries of Agriculture in the zone.\
	
	Department of Animal Science UI
	


G.    ADOPTED VILLAGES AND SECONDARY SCHOOLS
	S/N
	Activities
	No. Proposed
	No. established/conducted
	Technologies Promoted
	Remarks

	1
	Facilitate Training of Vulnerable Girls on Skills Acquisition empowerment /Capacity Building under Centre for Girls Education


	
	
	
	

	2
	AshakaCem Agric. Ecology Project
	
	
	
	

	3. 
	Renovation/Construction of NAERLS Zonal AROCs


	
	
	
	

	4
	Adopted Village farmers Database Development


	
	
	
	

	4
	TV Programme 
	1
	
	
	

	5
	Total Adopted Villages
	66
	
	
	

	6
	New adopted villages
	04
	
	
	

	7
	New groups to be formed
	38
	
	
	

	8
	New groups to be trained
	27
	
	
	

	9
	Demo plots
	4
	
	
	

	
	Special Project



	1
	AGRA Kaduna Agroforestry Consortium Project


	1
	1
	
	Completed 

	2
	L- Press
	1
	1
	
	Completed 

	3
	NAERLS/AshakaCem Agric. Ecology Project in Ashaka and Mai-ganga, Funakaye and Akko LGAs, Gombe State
	1
	1
	
	Completed

	4
	Feasibility studies of Briquettes production in Nigeria (Kano, Katsina, Niger, Maiduguri, Nasarawa, Ogun, and Lagos)
	1
	1
	
	Completed

	5
	Comprehensive Assessment of Informal Water Users in TRIMMING Project Schemes; KRIS, HVIS and BIS
	1
	1
	
	Completed 

	6
	NRF-Development of an Artificial Intelligence Based Multi-Crop Planter
	
	
	
	Ongoing

	7
	NRF- Integration of Biodigester into Conventional Septic Tank for Sustainable Energy Generation and Households’ Economic Viability in Nigeria
	1
	1
	
	Ongoing 

	8
	NRF - SWAT Modeling Development and Development for Management of Irrigation Scheme to improve to improve small scale farmers’ livelihood in Nigeria
	
	
	
	Ongoing 

	9
	AATF/PBRC Project
	
	
	
	Established 

	10
	NRF- Development of Convolutional-Neural-Network-Based Model for Cropland area, Output, and Yield estimates for Nigeria
	
	
	
	Ongoing

	11
	Accelerated Genetics Gains (AGG)

	
	
	
	Ongoing 

	12
	Child for Girls Education (CGE)


	
	
	
	Ongoing

	13
	C4SEAS Regional Training Hub Project – Strengthening Human Capital for Soil-Health Focused Extension in West Africa
	
	
	
	Ongoing

	14
	AfDB Farmers interview on behalf of National Agricultural Scheme (NGS)


	
	
	
	Completed


CONSTRAINTS:

Inadequate funding

Inadequate staff especially the non-academic
Non-inclusion of zonal office staff in the Research/ Extension activities domicile in NW geo-political zone

Refrigerator and Air condition units are required for the offices
Outdated and nonfunctional computers and printer(s) for official activities
Studio Equipment and set up

Bad roads leading to the office
Dilapidated offices (Infrastructures)
Bad cars/Lack of project vehicle for site visits/inspection
Electricity
Renovation of the AROC at the adopted village is required

Name of Contact Person: Prof. A.A JAMILU 
Post/Rank: Assistant Director Extension training and outreach, NAERLS
Phone Number: 08028448193

[image: image38.jpg]


                                                                                                                   [image: image39.png]



Name of Research Institute: National Institute for Freshwater Fisheries Research,

Postal Address: P.M.B. 6006, New Bussa

Website:     www.niffrng.org                          E-mail:niffish@gmail.com , contact@niffr.gov.ng

Telephone: 
08063093027











A.   EXTENSION SUPPORT ACTIVITIES

	SN
	Title
	No Proposed
	No Achieved
	Collaborators
	Remarks

	1
	Diagnostic survey
	2
	- 
	Kwara State government 
	Non availability of fund

	2
	On-Station Research (OSR)
	4
	-
	
	

	3
	OFR
	5
	- 
	Kainji  Aquaculture 
	

	4
	MTRM
	12
	-
	ADPs
	No invitation

	5
	Joint Scientific Field Evaluation
	1
	-
	NAERLS 
	

	6
	Field days
	2
	       -
	Stakeholders 
	

	7
	Zonal REFILS Workshop
	4 
	-
	Stakeholders 
	

	8
	Pre-season training
	1
	1
	Stakeholders 
	

	9
	Post season training
	1
	-
	Stakeholders
	

	10
	Zonal Steering Committee Meeting
	2
	-
	Stakeholders 
	

	11
	Zonal Technical Committee Meeting
	4
	- 
	Stakeholders 
	

	12
	In-house Review Meeting/Cropping Scheme Meeting
	5
	1
	Stakeholders 
	

	13
	National Agricultural Extension Review and Planning Meeting (NAERPM)
	1
	1
	Stakeholders 
	

	14
	Adopted Village (Established)
	5
	1
	Village Heads
	Insufficient fund

	15
	Training Workshop (Participated)
	4
	3
	
	

	16
	Training Workshop (Organized)
	4
	1
	
	

	17
	Training Workshop (As Resource Person attended)
	
	2
	
	

	18
	Agric. Research & trade Fair
	1
	1
	
	

	19
	Research Institute Field Day
	1
	-
	
	

	20
	World food day
	1
	-
	
	No invitation

	21
	Wet & dry season evaluation
	1
	-
	NAERLS
	No invitation

	22
	National Agric. Shows, State, NGOs and others
	1
	
	
	No invitation


B1.    TECHNOLOGY DEVELOPMENT

	S/No
	Technology to be Developed within the Year Under Review 
	Month to be Released
	Level of acceptance (if any)
	Identified areas requiring improvements

	1
	Motorized Atala gear 
	Not yet 
	
	

	2
	Fingerling counting machine
	Not yet  
	
	    

	4
	A monitoring device for fish dryer
	        Not yet
	
	

	5
	Multi-sensing device for monitoring water quality
	         Not yet
	 
	

	6 
	Fingerling sorting machine
	         Not yet 
	
	


B2.    CLIMATE RESILIENT TECHNOLOGY DEVELOPMENT

	S/No
	Climate Resilient Technology Developed within the Year Under Review 
	Month Released
	Level of Acceptance (If any)
	Identified Areas Requiring Improvements

	1
	Cage culture of tilapia in a reservoir
	Ongoing 
	
	


C.        EXTENSION PUBLICATIONS PRODUCED IN 2025

	SN
	Title
	 Copies targeted
	Copies achieved 
	Collaborators

	1
	Bulletins

Fish feed formulation

handling fish inland water 
	200

200
	     -

     -
	

	2
	Guides

 1.management of homestead fish pond

2.precautions for good water quality management in fish ponds

3. fertilizer application in fish ponds

4. prevention of losses in stored dried fish

5.feeding practices in fish farming

6.species combination and stocking density in fish ponds
	200

200

200

200

200

200
	     -

     -

     -

     -

     -

     -
	

	3
	Leaflets

1. control of some common diseases in fish pond

2. integrated rice cum fish farming
	200

200
	     -

     -
	

	4
	Posters

1. control of some common disease in fish pond
	200
	     -
	

	5
	Others (Specify)

NIFFR technology booklet

Journals (both local & International) 

Conference proceedings


	-

-

-
	500

12

4
	


D.     RADIO PROGRAMMES

	SN
	Programme Title
	Proposed

Episodes
	No. Achieved 
	Number aired
	Collaborators
	Channels 

	1
	Fish farming and types of farming practices
	2
	Nil 
	 Nil 
	ARCN
	

	2


	Best practices in fisheries & aquaculture
	3
	Nil 
	Nil 
	ARCN
	

	3
	Fish feed formulation for culture fish
	3
	Nil 
	Nil 
	ARCN
	

	4
	Water quality parameters in fish farming
	2
	Nil 
	Nil 
	ARCN
	

	5
	Hatchery management practices
	2
	Nil 
	Nil 
	ARCN
	

	6
	Fish processing techniques 
	4
	Nil 
	Nil 
	ARCN
	

	7
	Fisheries cooperatives
	2 
	Nil 
	Nil 
	 ARCN
	


E     TELEVISION PROGRAMMES

	SN
	Programme Title
	Proposed

Episodes
	No. Achieved 
	Number aired
	Collaborators
	Channels 

	1
	Documentary on aquaculture activities
	10 
	Nil 
	Nil 
	
	NTA/NYSC


F.    TRAINING WORKSHOP
	SN
	Title
	Category of trainees
	No of trainees
	Collaborators
	Duration

	1
	Capacity building and empowerment training for youth and women  
	Youth, Women  
	Nil 
	
	

	2


	Capacity building and empowerment training for youth in fish processing & value addition 
	Youth

Men 

Women
	Nil 
	
	

	3
	Training on fish feed formulation & production
	Youth

Men 

Women
	Nil 
	
	

	4
	Entrepreneurship skills in fish processing, preservation, value addition & quality control
	women
	Nil 
	
	

	5
	Training on fish pond construction techniques
	Youth 

Men 
	Nil 
	
	

	6
	Training on organic farming 
	Civil servants

Fish farmers

Students 

Youth 

Women
	100
	Thrive Institute
	7 days

	7
	Student Industrial Working Experience Scheme (SIWES)

	Students 
	165
	Universities, Polytechnics 
Colleges of Agriculture

	Minimum of three months


G.    ADOPTED VILLAGES AND SECONDARY SCHOOLS
	SN
	Activities
	No. Proposed
	No. conducted
	Technologies Promoted
	Remarks

	1
	Stocking of ponds
	5
	Nil 
	-
	No fund

	2
	Fish processing &value addition
	5
	Nil 
	-
	

	3
	Formation of new adopted villages & Schools
	3
	1
	Agribusiness
	

	4
	Renovations pond facilities in adopted villages & schools
	5
	Nil 
	-
	

	5
	Introduction of all male tilapia, modern smoking dryers
	5
	Nil 
	-
	

	6
	Training on fish farm management practices
	5
	Nil 
	-
	

	7
	Alternative income generating activities
	5
	1
	-
	

	8
	Formation and reactivation of young farmers’ club
	-
	2
	Agribusiness 
	

	9
	Establishment of organic farming garden
	
	2
	
	


CONSTRAINTS: 

Insufficient and untimely release of fund

Insecurity 

Name of Contact Person: Dr. Toyin Olowosegun

Post/Rank: Director/HOD (Research Outreach)
Phone Number: 08055362968, 08036328

[image: image40.jpg]


                                                                                                                 [image: image41.wmf]
Name of Research Institute: NATIONAL CEREALS RESEARCH INSTITUTE (NCRI)          

BADEGGI NIGER STATE

Postal Address: P.M.B. 8 Bida Niger State

Website: www.ncribadeggi.org.ng E-mail: ncribadeggi15@yahoo.com 

ncribadeggi@gmail.com  infor@ncribadeggi.org.ng   






A.   EXTENSION SUPPORT ACTIVITIES

	SN
	Title
	No Proposed
	No Achieved
	Collaborators
	Remarks

	1
	Diagnostic survey
	1
	-
	-
	No release of fund 

	2
	On-Station Research (OSR)
	2
	5
	Gate foundation,

Harvest plus and AfricaRice
	Completed 

	3
	OFR
	2
	10
	Gate foundation

Harvest plus and AfricaRice
	Completed 

	4
	MTRM
	96
	3
	NCRI, IFAD, & NAMDA
	Inadequate funds

	5
	Joint Scientific Field Evaluation
	1
	-
	
	

	6
	Field days
	10
	15
	Institute of crop science China, Gate foundation, Harvest Plus and AGRA
	Completed 

	7
	Zonal REFILS Workshop
	1
	-
	
	No release of fund 

	8
	Pre-season training
	3
	5
	Institute of crop science China, Gate foundation
	Achieved beyond the target

	9
	Post season training
	3
	
	
	

	10
	Zonal Steering Committee Meeting
	4
	-
	NARI, ADPs, in NCZ 
	No release of fund 

	11
	Zonal Technical Committee Meeting
	1
	-
	NARIs, FMA&FS, Uni, in NCZ
	No fund

	12
	In-house Review Meeting/Cropping Scheme Meeting
	1
	1
	NARIs, ADPs, farmers & other agencies
	Achieved 

	13
	National Agricultural Extension Review and Planning Meeting (NAERPM)
	1
	1
	NAERLS
	

	14
	Adopted Village (Established)
	10
	10
	FMAFS
	Achieved  

	15
	Training Workshop (Participated)
	10
	4
	JAICA, AGRA, Harvest plus
	Inadequate support 

	16
	Training Workshop (Organized)
	10
	5
	Institute of crop science China, Gate foundation, AGRA
	Inadequate support 

	17
	Training Workshop (As Resource Person attended)
	10
	15
	AfricaRice, AGRA
	Achieved beyond the target 

	18
	Agric. Research & trade Fair
	6
	2
	
	Inadequate funding 

	19
	Research Institute Field Day
	3
	-
	
	No fund released 

	20
	World food day
	1
	-
	Federal Government, AFAN, NARIs, State Governments, Private Orgs. and other agencies
	Proposed but no fund released 

	21
	Wet & dry season evaluation
	2
	1
	
	Participated being a stakeholder 

	22
	National Agric. Shows, State, NGOs and others
	1
	-
	Federal Government, AFAN, NARIs, State Governments, Private Orgs. and other agencies
	The institute intends to attend 


B1.    TECHNOLOGY DEVELOPMENT

	S/No
	Technology Developed within the Year Under Review 
	Month Released
	Level of Acceptance (If any)
	Identified Areas Requiring Improvements

	1
	FARO 71(lowland)
	February

2025
	Just released
	Thresherability

	2
	FARO 72(lowland)
	February

2025
	Just released
	Iron sensitivity 

	3
	NCRISOY 5M(TGX 2029-27F)
	February

2025
	Just released
	Increase the yield potential 

	4
	NCRIBEN 06
	February

2025
	Just released
	Increase the yield potential  

	5
	NCRIBEN 07
	February

2025
	Just released
	Increase the yield potential  


C.        EXTENSION PUBLICATIONS PRODUCED IN 2024
	SN
	Title
	Copies Targeted
	Copies Achieved
	Collaborators

	1
	Bulletins

1. NCRI news letters

2.

3.

4.

5.
	1000
	1000
	

	2
	Guides

1. Extension guides on all the institutes mandate crops

2.

3.

4.

5.
	1000 each
	NIL
	

	3
	Leaflets

1.  rice pest and diseases

2. seed production

4.

5.
	1000

1000

1000
	NIL

NIL


	


D.     RADIO PROGRAMMES
	SN
	Programme Title
	Proposed

Episodes
	No. Achieved 
	Number aired
	Collaborators
	Channels 

	1
	Agric panorama
	52
	NIL
	NIL
	Radio Nigeria
	100.5 power FM Bida

	2

Etc.
	Agric quiz
	2
	NIL
	NIL
	
	


E     TELEVISION PROGRAMMES

	SN
	Programme Title
	Proposed

Episodes
	No. Achieved 
	Number aired
	Collaborators
	Channels 

	1
	Documentary on NCRI
	2
	NIL
	
	
	

	2

Etc.
	
	
	
	
	
	


F.    TRAINING WORKSHOP
	SN
	Title
	Category of trainees
	No of trainees
	Collaborators
	Duration

	1
	Awareness creation for small holder farmers to accelerate farmers adoption of improved varieties and crop performance feedback
	farmers
	50
	AGRA
	1day August 2025

	2.
	Capacity building for seed companies for quality seed production
	Seed companies
	9
	AGRA
	1day August 2025

	3.
	Training of out growers on production of GAP for FARO 71&72
	Farmers 
	20
	Harvest plus
	2 days September 2025

	4.
	Training of seed companies on GAP 71&72
	Seed companies
	20
	Harvest plus
	3 days October 2025


CONSTRAINTS: 

Insecurity

Untimely release of funds

Inadequate cold rooms (for storage of genetic materials) 

Communal conflict involving adjoining villages (hindering field research activities) 

Name of Contact Person: Dr. Habib Abubakar Ndagi

Post/Rank: Chief Research Officer/Zonal REFILS Coordinator (NCZ) 

Phone Number: 08062707390
Name of Research Institute: Nigerian Institute for Oil Palm Research, (NIFOR).

Postal Address: P.M.B 1030, Benin City, Edo State.

Website:  





 E-mail: info@nifor.org     
Telephone: 08068012422

A.   EXTENSION SUPPORT ACTIVITIES

	SN
	Title
	No Proposed
	No Achieved
	Collaborators
	Remarks

	1
	Diagnostic survey
	1
	         1
	ADPs, MANR, FMAFS
	100%

	2
	On-Station Research (OSR)
	-
	-
	-
	-

	3
	OFR
	1
	1
	ADP
	100%

	4
	MTRM
	12
	2
	ADP
	16.7%

	5
	Joint Scientific Field Evaluation
	1
	-
	-
	-

	6
	Field days
	1
	-
	ADP, MANR, OCP
	-

	7
	Zonal REFILS Workshop
	1
	1
	MANR, FMAFS, IAR&T, ADPs
	100

	8
	Pre-season training
	1
	1
	ADPs
	100

	9
	Post season training
	1
	1
	ADPs
	100

	10
	Zonal Steering Committee Meeting
	1
	1
	ADPs, NARIs, UNIVERSITIE, INPUT AGENCIES, FMAFS, FARMERS’ ORGANIZATIONS 
	100

	11
	Zonal Technical Committee Meeting
	2
	-
	-
	-

	12
	In-house Review Meeting/Cropping Scheme Meeting
	1
	1            


	ADPs, NARIs, UNIVERSITIES, FMAFS, FARMERS’ ORGANIZATIONS
	100

	13
	National Agricultural Extension Review and Planning Meeting (NAERPM)
	1
	1
	NAERLS 
	100%

	14
	Adopted Village (Established)
	3
	-
	-
	-

	15
	Training Workshop (Participated)
	       5
	-
	-
	-

	16
	Training Workshop (Organized)
	5
	5
	ADPs, NARIs, AND UNIVERSITIES
	100%

	17
	Training Workshop (As Resource Person attended)
	5
	3
	FMAFS, ADPs
	60%

	18
	Agric. Research & trade Fair
	2
	-
	-
	-

	19
	Research Institute Field Day
	1
	-
	-
	-

	20
	World food day
	1
	1
	FMAFS
	100%

	21
	Wet & dry season evaluation
	1
	1
	 NAERLS, ADPs, NARI’s 
	100%

	22
	National Agric. Shows, State, NGOs and others
	1
	1
	FMAFS
	100%


B1.    TECHNOLOGY DEVELOPMENT

	S/No
	Technology Developed within the Year Under Review 
	Month Released
	Level of Acceptance (If any)
	Identified Areas Requiring Improvements

	1
	NIFOR CPO Adulteration Analysis Kit (NIFOR CAAK)
	February 2025
	-
	-

	2
	
	
	
	

	3
	
	
	
	

	4
	
	
	
	

	5
	
	
	
	

	6
	
	
	
	


F.    TRAINING WORKSHOP
	SN
	Title
	Category of trainees
	No of trainees
	Collaborators
	Duration

	1
	Nursery establishment and management techniques for oil palm 
	Oil palm field supervisors, Youth
	15
	-
	10 days

	2


	Operation & Maintenance of NIFOR SSPE
	Fabricators & Oil palm field supervisors 
	10
	-
	10 days

	3
	Techniques for Effective Plantation Management in the Palm Industry
	Farmers groups, ADPs/Agric officers, Field supervisors
	2
	-
	20 days

	4
	Packaging and Storage of Palm oil
	Processors, Farmers groups, cooperatives, Entrepreneurs and Interested Members of the Public 
	3
	-
	10 days


CONSTRAINTS: Inadequate fund, Lack of mobility (i.e project vehicles and motor cycles) and Inadequate and effective ICT facilities.

Name of Contact Person: Dr Lucky Igene

Post/Rank: Head, Extension Division/ Chief Research Officer
Phone Number: 08068012422

[image: image42.jpg]


                                                                                                 [image: image43.jpg]FEDERAL GOVERNMENT OF

NIGERIA




Name of Research Institute: Nigerian Stored Products Research Institute (NSPRI)
Postal Address: KM 3 Asa Dam Road Ilorin, Kwara State

Website: https://www.nspri.gov.ng          E-mail: nspriheadquarters@yahoo.com

Telephone: 
08117767204












A.   EXTENSION SUPPORT ACTIVITIES

	SN
	Title
	No Proposed
	No Achieved
	Collaborators
	Remarks

	1
	Diagnostic survey
	10
	10
	ADPs
	

	2
	On-Station Research (OSR)
	5
	5
	Students, Farmers, ADPs, Consultant
	Excursions and Exhibitions

	3
	OFR
	NA
	NA
	
	

	4
	MTRM
	12
	10
	Stakeholders and SMS
	

	5
	Joint Scientific Field Evaluation
	3
	3
	Consultant
	

	6
	Field days
	1
	Nil
	Staff
	

	7
	Zonal REFILS Workshop
	1
	Nil
	Staff
	

	8
	Pre-season training
	NA
	NA
	
	

	9
	Post-harvest training
	6
	6
	ADPs, NYSC
	

	10
	Zonal Steering Committee Meeting
	1
	Nil
	REFILs
	

	11
	Zonal Technical Committee Meeting
	1
	Nil
	REFILs
	

	12
	In-house Review Meeting/Cropping Scheme
	1
	Nil
	Staff
	

	13
	National Agricultural Extension Review and Planning Meeting (NAERPM)
	1
	1
	NAERLS
	

	14
	Adopted Village
	6
	6
	CATFAN, FAMAN
	

	15
	Training Workshop (attended)
	3
	1
	ADPs, NEPC, NIFOR, FACAN, NAQS, NIOMR, CRIN, NIHORT, NCRI, FPIS, NAERLS


	

	16
	Training Workshop (Organized)
	7
	7
	
	

	17
	Training Workshop (Resource Person)
	6
	4
	IITA, Stakeholder, Consultant


	Successful

	18
	Agric. Research & trade Fair/expo
	1
	Nil
	
	

	19
	Research Institute Field day
	1
	Nil
	
	

	20
	World food day
	1
	Nil
	
	

	21
	Wet & dry season evaluation
	NA
	NA
	
	

	22
	National Agric. Shows/others, state, NGOs
	5
	1
	JDPM
	


B.    TECHNOLOGY DEVELOPMENT

	S/No
	Technology Developed within the Review Year 
	Month Released
	Level of Acceptance (%)
	Identified Areas Requiring Improvements

	1
	Parabolic Dryer
	January
	65
	Nil

	2
	Solar Powered Cooling System
	NA
	NA
	NA

	3
	Modified Ice Fish Box
	August
	Analysis ongoing
	NA

	4
	NSPRI Silo
	August
	Analysis ongoing
	NA


C.        EXTENSION PUBLICATIONS
	SN
	Title
	Target
	Achievement
	Collaborators

	1
	Bulletins


	10000
	Nil
	

	2
	Guides

1. Postharvest Management of Perishable Agricultural Products
2. Postharvest Management of Durable Agricultural Products
	2000
	1750
	ADPs

	3
	Leaflets

1. NSPRI Developed Technology
	10,000
	10,000
	Nil

	4
	Posters

1. Nil
	
	
	

	5
	Others (specify)

1. Appropriate Postharvest Management of Crops for Export and Mitigating the Challenges
	1000
	500
	NARIs


D.     RADIO PROGRAMMES
	SN
	Topic
	Proposed number of airing
	No. Achieved
	Collaborators
	Channels 

	1
	NSPRI Advert
	20
	18
	Nil
	Freedom FM Kano, Royal FM Ilorin, WAZOBIA FM Abuja,



	2
	Spiral inflation, food security in the face of security challenge

	10
	
	Nil
	Diamond FM Ilorin



	3
	Awareness on NSPRI Incubation Centre

	10
	
	Nil
	Cool FM Port Harcourt, Sobi FM Ilorin, Freedom FM Kano




E     TELEVISION PROGRAMMES
	SN
	Topic
	Proposed number of airing
	No. Achieved
	Collaborators
	Channels 

	1
	Nil
	
	
	
	

	2
	Nil
	
	
	
	


F.    TRAINING WORKSHOP
	SN
	Title
	Category of trainees
	No of trainees
	Collaborators
	Duration

	1
	Training on postharvest technology innovation

	ADP Staff


	240
	ADPs
	5 days

	2
	Training on youth empowerment
	Corp members
	80
	NYSC
	5 days


G.    ADOPTED VILLAGES AND SECONDARY SCHOOLS
	SN
	Activities
	No. Proposed
	No. established/conducted
	Technologies Promoted
	Remarks

	1
	Fumigation of Warehouses
	55
	On-going
	IPM


	Successful


CONSTRAINTS: 

Paucity of funds

Insecurity

Name of Contact Person: Dr Atibioke O. A.

Post/Rank: Assistant Director (Research)

Phone Number: 08030671659

[image: image44.jpg]


                                                                                                           [image: image45.jpg]



Name of Research Institute: NATIONAL HORTICULTURAL RESEARCH INSTITUTE (NIHORT)
Postal Address: PMB 5432, Idi-Ishin, Jericho, Ibadan

Website:   www.nihort.org                                     

E-mail: info@nihort.gov.ng

Telephone: 













A.   EXTENSION SUPPORT ACTIVITIES

	SN
	Title
	No Proposed
	No Achieved
	Collaborators
	Remarks

	1
	Diagnostic survey
	8
	8
	ADP (Oyo, Osun, Ondo, Ekiti, Kano, Benue, Gombe).

Commodity Association- Badagry and LASU, Lagos state
	100%

	2
	On-Station Research (OSR)
	7
	7
	
	100%

	3
	OFR
	2
	1
	
	100%

	4
	MTRM
	1
	1
	
	100%

	5
	Joint Scientific Field Evaluation
	4
	4
	
	100%

	6
	Field days
	1
	-
	
	

	7
	Zonal REFILS Workshop
	1
	1
	
	100%

	8
	Pre-season training
	Nil
	Nil
	
	

	9
	Post season training
	Nil
	Nil
	
	

	10
	Zonal Steering Committee Meeting
	1
	1
	
	100%

	11
	Zonal Technical Committee Meeting
	1
	1
	
	100%

	12
	In-house Review Meeting/Cropping Scheme Meeting
	3
	3
	
	100%

	13
	National Agricultural Extension Review and Planning Meeting (NAERPM)
	1
	1
	
	100%

	14
	Adopted Village (Established)
	2
	Nil
	
	

	15
	Training Workshop (Participated)
	3
	3
	
	100%

	16
	Training Workshop (Organized)
	20
	6
	
	

	17
	Training Workshop (As Resource Person attended)
	3
	3
	
	100%

	18
	Agric. Research & trade Fair
	       2
	2
	
	100%

	19
	Research Institute Field day
	1
	1
	
	100%

	20
	World food day
	1
	Nil
	
	

	21
	Wet & dry season evaluation
	Nil
	Nil
	
	

	22
	National Agric. Shows, State, NGOs and others
	4
	2
	
	50%


B1.    TECHNOLOGY DEVELOPMENT

	S/No
	Technology Developed within the Year Under Review 
	Month Released
	Level of Acceptance (If any)
	Identified Areas Requiring Improvements

	1
	HORTIPEP 1
	APRIL 2025
	Not yet ascertained
	

	2
	HORTIPEP 2
	APRIL 2025
	Not yet ascertained
	

	3
	HORTITOM 4
	  APRIL             2025
	Not yet ascertained
	

	4
	HORTITOM 5
	 APRIL    2025
	Not yet ascertained
	


B2.    CLIMATE RESILIENT TECHNOLOGY DEVELOPMENT

	S/No
	Climate Resilient Technology Developed within the Year Under Review 
	Month Released
	Level of Acceptance (If any)
	Identified Areas Requiring Improvements

	1
	HORTIPEP 1
	APRIL 2025
	Not yet ascertained
	

	2
	HORTIPEP 2
	APRIL 2025
	Not yet ascertained
	

	3
	HORTITOM 4
	    APRIL         2025
	Not yet ascertained
	

	4
	HORTITOM 5
	APRIL 2025
	Not yet ascertained
	


C.        EXTENSION PUBLICATIONS PRODUCED IN 2025
	SN
	Title
	Copies Targeted
	Copies Achieved
	Collaborators

	1
	Bulletins

1. Guide to Post Harvest Handling and Processing of Tomato

2.

3.
	1,000
	1,000
	

	2
	Guides

1. Mushroom Production Guide

2. Telfairia Production Guide


	5,000

5,000
	5,000

5,000
	

	3
	Posters

1. Posters on NIHORT Institutional Seminar programmes


	7
	7
	

	4
	Others (Horticultural Calendar)

Calendar of Field operations and Agro-techniques for ornamental plants 

Fliers for radio programme

NIHORT Newsletter


	5,000

26

2
	5,000

26

1
	


D.     RADIO PROGRAMMES
	SN
	Programme Title
	Proposed

Episodes
	No. Achieved 
	Number aired
	Collaborators
	Channels 

	1
	Agbe Loba
	26
	26
	26
	-
	96.7FM

	2


	HORTI TALKS
	2
	2
	2
	HORTINIGERIA
	105.5FM


E     TELEVISION PROGRAMMES

	SN
	Programme Title
	Proposed

Episodes
	No. Achieved 
	Number aired
	Collaborator
	Channels 

	1
	Special Television Programme for World Food Day Celebration
	2
	2
	2
	-
	NTA Ibadan


F.    TRAINING WORKSHOP
	SN
	Title
	Category of trainees
	No of trainees
	Collaborators
	Duration

	1
	HortiFair 2025 Capacity-building Sessions
	Farmers, Researchers, Entrepreneurs, Youths,
	  35
	HORTINIGERIA
	1 day

	2
	Mushroom Production Technology- A Pathway to Income Generation and Improved Livelihood
	Male, female vegetable farmers
	    7
	   --
	2 days

	3
	Orange Juice Production
	Farmers, youths, Food entrepreneurs
	25
	 --
	3 days

	4
	Vegetable Value Addition and Crop Residue Utilization
	Farmers, Entrepreneurs, Youths, 
	56
	 HortiNigeria, Makfem Farms, Eweko Aggregate and Ecotutu
	1 day

	5
	Africa Agriculture Adaptation AAA Atlas
	Male, female researchers
	35
	 Policy Innovation Laboratory of Africa (PILAF), University of Ibadan
	1 day

	6
	Banana Seed Certification Training
	Farmers, Entrepreneurs, Youths,
	45
	 National Seed Council (NASC), Program for Seed System Innovation for Vegetatively Propagated Crops (PROSSIVA), International Institute of Tropical Africa (IITA)
	1 day

	7
	Pineapple Juice Production
	Youths and Women pastoralists 
	50
	 Value  4 Dairy (V4D)
	1 day

	8
	Okra Market Segmentation Validation Training
	Students, Farmers, Researchers,
	61
	Vision for Adapted Crops (VACs)
	2 days

	9
	Improved Tomato Production Techniques, Disease Management and Post-Harvest Handling
	Tomato farmers
	81
	Korea-Africa Food and Agriculture Cooperation Initiative (KAFACI)
	1 day

	10
	Tomato (Breeder and Foundation Seeds) Training and Demo on Nursery
	South west Tomato Farmers
	941
	Tomatoes and Orchard Producers Association of Nigeria (TOPAN)
	7 days


G.    ADOPTED VILLAGES AND SECONDARY SCHOOLS
	SN
	Activities
	No. Proposed
	No. conducted
	Technologies Promoted
	Remarks

	1
	Promotion of fruit and leafy vegetables in Onidoko, Koguo and Awaye villages


	4
	3
	Production of improved vegetables
	75.0%

	2
	Promotion of NIHORT activities in adopted villages to showcase and disseminate NIHORT technologies
	2
	2
	Rapid multiplication techniques of plantain, Banana, Pineapple, citrus and mango. Soap from plantain and banana waste 
	100.0%

	3
	Promotion of horticultural activities in NIHORT adopted schools
	4
	4
	Good Agricultural Practices in leafy vegetables and fruits
	100.0%


CONSTRAINTS: 

Lack of facilities for E-extension for wider coverage and dissemination

Name of Contact Person: Dr. Oluyemisi M. ADEWALE

Post/Rank: Assistant Director (Research)/Head Extension Programme

Phone Number: 07054057515
ADP REPORTS

                                                           ADP REPORT

[image: image139.png]


State

Abia

Adamawa Akwa Ibom Anambra Bauchi Bayelsa Benue Cross River Delta Ebonyi
Edo Ekiti Enugu FCT
Gombe Imo Jigawa

Kaduna
Kano

Katsina Kebbi Kogi Lagos Nassarawa Niger Ogun Ondo Osun Plateau Sokoto Taraba Yobe Zamfara

Name of ADP: ABIA

Postal address:

Email:






Telephone_______________________

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	NIL
	Lack of funding

	2
	FNTs
	24
	20
	

	3
	OFARs
	5
	NIL
	No protocol

	4
	No. of Farm Families
	650,000
	650,000
	

	5
	No. of SPATs established 
	1120
	494
	

	6
	No. of MTPs
	112
	36
	Lack of funding

	7
	No. of Field days
	22
	NIL
	Lack of funding

	8
	No. of Agric Shows
	2
	NIL
	

	9
	No. of group formed
	70
	56
	

	10
	No. of Pre-season training per year
	6
	NIL
	Lack of funding

	11
	No. of Post-season training per year
	6
	NIL
	Lack of funding

	12
	Extension publications produced (No. of Titles)
	
	
	

	
	Bulletins 
	2
	NIL
	Lack of funding

	
	Guides
	2
	NIL
	Lack of funding

	
	Leaflets
	2
	NIL
	Lack of funding

	
	Posters
	2
	NIL
	Lack of funding

	
	Others
	2
	NIL
	Lack of funding

	13
	Zonal Steering Committee Meeting
	4
	NIL
	Lack of funding

	14
	Zonal Technical Committee Meeting
	4
	NIL
	Lack of funding

	15
	Zonal REFILS workshops
	1
	NIL
	Lack of funding

	16
	No of Extension Workers (VEAs)
	280
	70
	

	17
	No of Extension workers (BESs)
	38
	22
	

	18
	EA/Farmer ratio in the state
	1:800
	1:9,286
	


B. DETAILS OF EXTENSION PUBLIC1ATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins

1. Extension bulletin on poultry production 

2. Extension Bulletin on Orange Flesh Sweet potato

3. 

4.

5.
	500

500
	NIL

NIL
	ABIA ADP

ABIA ADP

	2
	Guides

1. Extension Guide on fall Army worm infestation on maize

2. Extension Guide on Die-back Disease of cassava 

3.

4.

5.
	500

500
	NIL

NIL
	ABIA ADP

ABIA ADP

	3
	Leaflets

1.  Extension Posters 

2.

3.

4.
	200
	NIL
	ABIA ADP


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4

5
	NIL


	NIL


	NIL


	NIL


	NIL


	NIL




D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2
	NIL


	NIL


	NIL


	NIL


	NIL


	NIL




E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1

2

3

4

5
	Training of farmers, Extension Agents, women cooperative, farmers and youths on cassava virus disease

Training of Extension Agents on climate smart Agriculture 

Training of Extension Agents on seed yam multiplication

Training of tractor operators
	ABIA ADP

ABIA ADP

IITA

NCAM
	Extension Agents, farmers, women and youths

Extension Agents

Extension Agents

Tractor Drivers
	50

50

50

5
	ABIA ADP, NCAM

ABIA ADP

IITA

NCAM


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	Cassava/Maize/Sweet potato
	NRCRI
	Adopted 
	

	2
	Cassava/Maize/Telfairia
	NRCRI
	Adopted
	

	3
	Yam minisett/Maize f6 coupea
	NRCRI 
	Adopted
	

	4
	Poultry production
	NRCRI 
	Adopted
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	CSS-Trained Farmers
	2024
	Ongoing 
	Fisheries

	2
	Project 
	
	
	Poultry agro-processing, cassava

	3
	
	
	
	

	4
	
	
	
	

	5
	
	
	
	

	6
	
	
	
	

	7
	
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Ministry of Agriculture is in charge

	2
	Credit
	Ministry of Agriculture is in charge

	3
	Agro-chemical
	Available in the open market but costly 

	4
	Tractor/Animal Traction
	Ministry of Agriculture is in charge

	5
	MTRM situation Report 
	MTRM has not held this year due to lack of funding


Name of ADP: Adamawa Agricultural Development Programme 

Postal address: PO BOX 956 Yola

Email:
 adamawaadp@gmail.com





Telephone_07037679978

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	5
	Achieved by NGOs

	2
	FNTs
	26
	-
	-

	3
	OFARs
	42
	-
	-

	4
	No. of Farm Families
	450000
	No VLS since
	1998

	5
	No. of SPATs established 
	1210
	950
	By NGOS 

	6
	No. of MTPs
	46
	25
	By NGOS 

	7
	No. of Field days
	1256
	1320
	By NGOS 

	8
	No. of Agric Shows
	4
	2
	Seed fair by NGOS 

	9
	No. of group formed
	100
	450
	

	10
	No. of Pre-season training per year
	1
	6
	By NGOS 

	11
	No. of Post-season training per year
	1
	4
	NGOS

	12
	Extension publications produced (No. of Titles)
	
	
	

	
	Bulletins 
	
	
	

	
	Guides
	
	
	

	
	Leaflets
	
	
	

	
	Posters
	
	
	

	
	Others
	
	
	

	13
	Zonal Steering Committee Meeting
	1
	-
	

	14
	Zonal Technical Committee Meeting
	536
	56
	

	15
	Zonal REFILS workshops
	1
	-
	No funding 

	16
	No of Extension Workers (VEAs)
	536
	35
	

	17
	No of Extension workers (BESs)
	46
	46
	

	18
	EA/Farmer ratio in the state
	1/800
	1/10000 and above
	Retirement, Dead and unemployment 


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4

5
	Agri digest

Hadari Malafan Duniya

Noma tushen arziki

Ina Matasa


	
	Yes

Yes

Yes

Yes
	Weekly

Weekly

Weekly 

Weekly 
	Usaku FM 90.5

Gotel FM 91.1

Weekly Fombina FM 101.5

NAS FM 89.9
	45min

1hour

1hour

1hour


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4

5
	My koma gona


	
	Yes 
	ATV
	ATV Yola
	1hour 


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1

2

3

4

5
	Pre- FBS

In- season

Post harvest 

Dry season 

Processing and market linkages 


	Helen keller

FAO

FMARD

SCL

UNDP


	EAs, Farmers 

Leaders 

N- Agro

Stake holders 


	1680

1322

342

2500
	ADP

ADP

FMARD 

SCL




F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	Fertilizer micro dosen
	
	Adopted 
	Climate smart

	2
	Used and handling of aflasate 
	
	Adopted 
	Control of afflotoxing 

	3
	Composting organic fertilizer 
	
	Adopted 
	Soil conservation and nutrition 

	4
	Bio pesticide formulation and application 
	
	Adopted 
	Environmental friendly 

	5
	Half moon (water shed) zai
	
	Adopted 
	Water harvesting 


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	FAO
	2007
	Ongoing 
	Humanitarian and advisory services 

	2
	Oxfarm
	2016
	6years 
	Humanitarian and advisory services 

	3
	GIZ
	2018
	5years
	Humanitarian and advisory services 

	4
	UNDP
	2019
	Ongoing 
	Humanitarian 

	5
	UNDP GEP
	2018
	5years 
	Humanitarian and advisory services 

	6
	Mercy corps 
	2019
	5years 
	Humanitarian and advisory services 

	7
	SCL
	2024
	Ongoing 
	Humanitarian and advisory services 

	8
	IITA
	2019
	5years 
	Humanitarian and advisory services 

	9
	CRS
	2019
	Ongoing 
	Humanitarian and advisory services 

	10
	ADAS
	2022
	Ongoing 
	Humanitarian and advisory services 


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Barn on the procurement of urea

	2
	Credit
	-

	3
	Agro-chemical
	Produce by state government to sell to farmers 

	4
	Tractor/Animal Traction
	-

	5
	MTRM situation Report 
	-


CONSTRAINTS 

1. Lack of funding of ADP and extension services 

2. Un employment of extension workers 

3. Zero release of ADP budget

4. Flood 

5. Dry spell

6. Draught 

7. Insecurity (kidnapping, insurgency and communal clashes)

8. Excessive soil degradation 

9. Pest and diseases (FAW, rice blast)

10. Fuel Subsidy removal 

Name of ADP: AKWA IBOM STATE AGRICULTURAL DEVELOPMENT PROGRAMME (AKADEP)
Postal address: MBIAOBONG ETOI, P.M.B 1089, UYO

Email: akadep@gmail.com



Telephone_______________________

PRESENTER: MR. IMOH U. AKPANNAH (DAES)

A. 2025 EXTENSION SUPPORT INDICATORS 

	SUPPORT ACTIVITIES
	TARGET
	ACHIEVEMENT 
	REMARKS

	MTRMs
	12
	NIL
	Lack of funds

	FNTs/monthly meetings
	26
	24
	

	OFARs
	5
	NIL
	

	No of Farm Families
	685,095
	685,095
	

	No of SPATs established 
	2115
	1800
	

	No of MTPs
	90
	45
	Lack of funds

	No of Field days
	376
	20
	

	No of Agric Shows
	2
	-
	

	No of group formed
	376
	210
	

	No of training per year pre-season
	1
	NIL
	

	No. of post-season training 
	1
	NIL
	

	Extension publication produce 
	
	-
	

	Bulletins, crops, fisher, livestock, A/F
	2,000
	NIL
	

	Guides 
	1,000
	100 (crops)
	Distributed by Helen Keller to Field staff

	Leaflets
	1,000
	NIL
	

	Posters 
	1,000
	NIL
	

	Others (specify)
	-
	
	

	Zonal Steering Committee Meeting
	4
	NIL
	Lack of funds 

	Zonal Technical Committee Meeting
	2
	NIL
	Lack of funds

	Zonal REFILS workshops
	4
	NIL
	Lack of funds

	No of Extension Workers (VEAs)
	274
	47
	State Government is currently recruiting. There is hope

	No of Extension workers (BESs)
	40
	31
	

	EA/Farmer ratio in the state
	1:800
	1:14576
	


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	S/N
	Title
	Target
	Achievement
	Collaborators

	1
	Bulletins

1. Crops 

2. Fisheries 

3. Livestock 

4. Agrofroestry

5. Processing 


	2000
	NIL
	

	2
	Guides

1. Crops 

2. Fisheries 

3. Livestock 

4. Agrofroestry

5. Processing 
	200

200

200

200

200
	100 Crops on home garden establishment 


	Helen Keller International 



	3
	Leaflets

1. Crops 

2. Fisheries 

3. Livestock 

4. Agrofroestry

5. Processing 
	200

200

200

200

200
	NIL 
	

	4
	Posters 

1. Crops 

2. Fisheries 

3. Livestock 

4. Agrofroestry

5. Processing 
	200

200

200

200

200
	NIL
	


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	Programme Title/Topics
	Produced Only (Yes/No)
	Produced and Airing (Yes/No)
	Frequency of airing (e.g Weekly)
	Broadcasting station
	Duration

	Good Agronomic Practices in Tomatoe production
	
	Yes
	1
	Tangsio FM (Vernular)
	5 – 6pm

(Saturday)

	Stocking and water management in fisheries 
	
	Yes
	1
	Heritage FM Eket
	2 – 3pm (Saturday)

	Dry season farming: Land preparation 
	
	Yes
	1
	Comfort FM
	2 – 3pm (Tuesday)

	Cucumber production 
	
	Yes
	1
	Redemption FM Abak
	7:30 – 8:30pm 

	Planting techniques for cassava production
	
	Yes
	1
	Inspiration FM, Uyo
	4 – 5pm

	Maintenance of oil palm
	
	Yes 
	1
	Tangsio FM
	4 – 5pm

	Importance of Vaccination 
	
	Yest 
	1
	AKBC Radio
	4:30-5:30pm


D. TELEVISION PROGRAMMES PRODUCED AND AIRED 
	Programme Title/Topics
	Frequency of airing (e.g Weekly)
	Broadcasting station
	Duration

	1. 

2. 

3.       NIL

4.

5.
	NIL
	
	


E. TRAINING PROGRAMMES

	S/N
	Title
	Organizers
	Date of Training 
	No. of Trainees
	Categories of Trainees
	Collaborators 

	
	Training of extension field workers on the use of E-extension to address farmers field challenges.

National Farmers’ Helpline: 08142398838; 08139889860 were given out to extension field workers to be given to farmers in the rural areas to assist address field problems 
	ADP
	30th Aug. 2025
	47
	Extension field workers
	State Min of Agric & Food sufficiency.

	
	2 Day Training of the Trainers on the techniques of home garden establishment and management 
	Helen Keller Int’l
	29-30th Aug. 2025
	63
	Field Staff
	Akwa Ibom ADP, Vitamin angels 

	
	Online training on seed system innovation for vegetatively propagated crop. Seed yam production 
	IITA
	20th October 2025
	3
	2 Extension staff and Director Ext.
	

	
	Training on Good Agronomic practices for oil palm plantation 
	NPPAN
	10th October 2025
	30
	Farmers
	NPPAN, ADP

	
	TOT on Financial literacy 
	NPCO- Life-Nd
	21st Oct 2025
	10
	Extension Officer
	Life-ND, NDDC, IFAD


F. TECHNOLOGIES BEING PROMOTED IN 2025

	S/N
	Title
	Source 
	Adaption

(Adopted/Not Adopted)
	Comment

	
	CROPS
	
	
	

	
	Cultivation of Tomatoes
	FMAFS, NSPRI
	Adopted
	Demand for fresh tomatoes is on the increase. More farmers are investing in tomatoes production to make profit

	
	Cultivation of forest vegetable (Gnetum Africanan)
	ADP SHELF
	Adopted
	Demand is so high as it is used in making popular Afang soup. Rate of adoption by farmers is high.

	
	Production of Yam flour
	NSPRI
	Adopted
	High cost of yam tubers is a serious challenge

	
	Effective drying and packaging of Fish
	NSPRI
	Adopted
	Fish properly dried are stored and later sold at relatively high price thus making farmers maximize profit. Adoption level is high

	
	Utilization of Orange flesh Potatoes in baking  
	FMAFS
	Adopted
	Farmers have come to embrace orange flesh potatoes due to short cycle of production and high yielding potential. Adoption level is high

	
	Yam mirisett  production
	REFILS
	Adopted
	Seed yam is becoming very expensive.

N1,000. Farmers are planting yam mirikset as a way of generating income.

	
	Swamp Rice Production
	REFIL
	Adopted 
	There is massive increase in rice production due to government band on importation of rice.

	
	Pig fattening 
	SHELF (ADP)
	Adopted
	The use of brewery waste and kitchen waste have made feeding of pigs less expensive 

	
	Processing of cocoyam into confectionaries 
	REFIL
	Adopted 
	The itching effect often experienced from cocoyam is drastically reduced after processing. Highly adopted

	
	LIVE STOCK
	
	
	

	
	Goat/Sheep production
	REFIL
	Adopted 
	Upgrading of local Goats with improved breed is facilitating growth rate. The ratio of adoption is on the high side.

	
	Poultry
	REFIL 
	High level of adoption
	Continuous training of farmers by field extension staff on good management practices in poultry has encouraged farmers investment in the enterprise

	
	Snailery 
	REFILS
	High level of adoption
	The use of tyres and drums has made it very cheap for the technology to be adopted by farmers.


G: SPECIAL PROJECTS:

	S/N
	Project Name
	Year Started
	Duration of Project
	Key Activities

	1
	Transforming lives through Nutrition project by Helen Keller International 
	2024-2025
	Two years
	Training of 848 vulnerable women on the establishment of home garden across the selected five local government areas of Mbo, Ibiono Ibom, Eket, Ikot Ekpene and Itu. Each participant was supported with improved vegetable seeds and farming tools to assist them in the cultivation of dry season vegetable farming for improved nutrition.

174 number of cooking demonstration was carried out to broaden their knowledge on effective method of processing and utilization.

3047 detergents and 13491 soaps were distributed to vulnerable women as an incentive for participation.


H: BRIEF REMARKS ON: 

	S/N
	Input situation 
	Brief Report 

	1.
	Fertilizer
	Green well limited a fertilizer blending company established under public private partnership continues to produce good quality fertilizer of all brands for the farmers in the state.

	2
	Credit
	Farmers groups are linked with financial institutions for credit facility. Government also provides grants to assist farmers in various agricultural enterprises.

	3
	Agro-chemical
	Farmers are sensitized regularly to always patronize reputable agrochemical dealers to avoid buying chemicals that has been banned by the government. 

	4
	Tractor
	Farmers are continuously linked with the Tractor Unit in the ministry of Agriculture where tractor service are provided at subsidized rate.

	6
	Farm Implements
	Local fabricators were sensitized on the need to fabricate agricultural machines that are easily affordable by the small-scale farmers.

	7
	MTRM situation 
	This training was not held during the year due to inadequate funding. However, the Subject Matter Specialist (SMS) continue to select technologies from the SHELF for onward training in the Fortnightly Trainings (FNTs). All in bid to address emerging field challenges from the farmers


GENERAL: COMMENTS ON AGRICULTURAL ACTIVITIES IN THE STATE

Akwa Ibom State Government is focusing on boosting food production and empowering farmers through the ARISE AGENDA PROGRAMME.

Over 500,000 oil palm seedlings are distributed free to over 11,625 farmers across the state under the tree crop revolution to increase oil palm production.

Agricultural extension services is being strengthened by making the state ADP a stand-alone agency (no more under the Ministry of Agriculture) but under the supervision of the Secretary to the State Government. This is done to minimize unnecessary beauracratic bottleneck of the operations of the state ADP and to ensure better funding of the ADP activities.

1st Friday of every month is observed as farm day for every civil servant to encourage massive engagement of food production.

CONSTRAINTS 

Poor funding of extension (ADP) activities.

Lack of vehicles for field monitoring and effective supervision of field activities.

Paucity of extension agents due to retirements of old staff.

Name of ADP: Anambra

Postal address:

Email: maduabuchisachi@gmail.com
Telephone: 08039366162, 08037725172

judenwankwo@rocketmail.com 

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	2
	

	2
	FNTs
	26
	21
	

	3
	OFARs
	
	
	

	4
	No. of Farm Families
	700,000
	535,000
	

	5
	No. of SPATs established 
	
	
	

	6
	No. of MTPs
	300
	200
	

	7
	No. of Field days
	30
	2
	

	8
	No. of Agric Shows
	2
	1
	

	9
	No. of group formed
	600
	430
	

	10
	No. of Pre-season training per year
	1
	1
	

	11
	No. of Post-season training per year
	1
	
	

	12
	Extension publications produced 

(No. of Titles)
	
	
	

	
	Bulletins (ASADEP HERALD)
	12
	
	

	
	Guides
	
	
	

	
	Leaflets
	1,000
	
	

	
	Posters
	
	
	

	
	Others
	
	
	

	13
	Zonal Steering Committee Meeting
	1
	
	

	14
	Zonal Technical Committee Meeting
	1
	
	

	15
	Zonal REFILS workshops
	1
	
	

	16
	No of Extension Workers (VEAs)
	177
	48
	

	17
	No of Extension workers (BESs)
	21
	20
	

	18
	EA/Farmer ratio in the state
	1:100
	1:10,000
	


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins

1. ASADEP HERALD

2.

3.

4.

5.


	12
	
	

	2
	Guides

1. 

2.

3.

4.

5.
	
	
	

	3
	Leaflets

1. 

2.

3.

4.

5.
	
	
	


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2.
	Organic/Regenerative Agriculture 

Popularization 

GAP on Crops,

Livestock, Fishery etc Production  
	
	Yes 

Yes


	Every week

Every week
	ABS 88.5fm

ABS 88.5fm
	9am-10am

9am-10am


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4

5
	
	
	
	
	
	


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1

2

3

4

5
	International organization for good Leadership and Agriculture Devt (10GLAD) Training.

Training on RiceAdvice App for Android to improve Rice yield.

Cassava production and viral disease control for Higher yield productivity.

Youths for Apiculture  

Sustainable Agricultural Extension service Discovery in Nigeria Role or Digital technology 
	NGO

NGO

IITA

NGO

FDAE


	Extension Officers 

Extension Officers

Extension Officers/Famers

Extension Officers/Famers

PMs, DAES other stake holders in Extension 
	50

50

100

100

300
	ADP

ADP

ADP

ADP

ADP


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	GAPS on Organic/Regenerative Agriculture 
	Min. of Agric
	
	Ongoing 

	2
	Planting of Economic Trees 
	Min. of Agric
	Adopted 
	

	3
	Popularization of orange flesh sweet potato
	Min. of Agric
	Adopted
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	IFAD / VC DP
	2014
	11 Years 
	Promotion of Cassava/Rice cultivation in the State.

	2
	
	
	
	

	3
	
	
	
	

	4
	
	
	
	

	5
	
	
	
	

	6
	
	
	
	

	7
	
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Mainly bought in open markets as the State Govt. is promoting regenerative Agriculture  

	2
	Credit
	The ASBA/SACs are providing credit facilities.

	3
	Agro-chemical
	Costly in open market. Organic Agriculture is being promoted.

	4
	Tractor/Animal Traction
	Inadequate tractors, also some lands are not tractorable 

	5
	MTRM situation Report 
	Inadequate funding has reduced MTRMs drastically


CONSTRAINTS

Inadequate Extension officers has continued to militate against Extension Activities in the State.
Lack of mobility for Extension staff.
Paucity of funds to carry out some projects.
Poor monitoring schedules due to inadequate vehicles.
Late release of funds if available.  
[image: image47.jpg]






















[image: image46.jpg]






















                                                                                     
Name of ADP: Bauchi ADP
Postal address: PMB 0050, Dass Road, Bauchi

Email:
bauchistateadp2@gmail.com





Telephone_______________________

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	10
	Success 

	2
	FNTs
	24
	22
	

	3
	OFARs – Rainfed 

Dry 
	120

90
	75

75
	

	4
	No. of Farm Families
	3,250,000
	3,250,000
	

	5
	No. of SPATs established 
	-
	-
	

	6
	No. of MTPs
	1500
	1350
	

	7
	No. of Field days
	24
	24
	

	8
	No. of Agric Shows
	1
	-
	

	9
	No. of group formed
	520
	500
	

	10
	No. of Pre-season training per year
	1
	1
	

	11
	No. of Post-season training per year
	1
	1
	

	12
	Extension publications produced (No. of Titles)
	
	
	

	
	Bulletins 
	600
	
	

	
	Guides
	
	
	

	
	Leaflets
	
	
	

	
	Posters
	
	
	

	
	Others
	
	
	

	13
	Zonal Steering Committee Meeting
	4
	-
	

	14
	Zonal Technical Committee Meeting
	2
	-
	

	15
	Zonal REFILS workshops
	1
	1
	

	16
	No of Extension Workers (VEAs)
	500
	256
	

	17
	No of Extension workers (BESs)
	60
	29
	

	18
	EA/Farmer ratio in the state
	1:000
	12:000
	


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins

1. 

2.
	600
	
	

	2
	Guides

1. 

2.
	600
	
	

	3
	Leaflets

1. 

2.
	600
	
	

	4
	Leaflets

1. 

2.
	600
	
	

	
	
	
	
	


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3


	Akoma Gona

Noma da Raya Karkara


	-

-
	Yes

Yes
	52 weeks

52 weeks
	BRC 2 

Albarka Radio
	30 Mins.

30 Mins.


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3


	Akoma Gona

Noma Tushen Arziki


	-

-
	Yes

Yes
	52 weeks 

52 weeks 
	NTA Bauchi

BATV
	30 Mins.

30 Mins.


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1
	Training on climate resilient for wheat and vegetables production 
	BSADP
	Farmers and Extension agents
	50
	MOA/BSADP

	2
	Emergency training and demonstration on climate resilient on Rice and maize production 
	ATBU
	Farmers and Extension agents
	120
	ATBU/BSADP

	3
	Emergency training and demonstration of climate resilient practices on Millet, Sorghum and Soyabeans.   
	BSADP
	Farmers and Extension agents
	280
	BSADP

	4
	Training on GAP Maize and Rice 
	WOFAN
	Farmers
	420
	WOFAN/BSADP

	5
	Training on Processing, Utilization and nutritional value of Soybeans and Groundnut 
	BSADP
	Farmers
	350
	BSADP

	6.
	Training of farmers on identification of fake, adulterated and sub standard Agro chemicals and fertilizers
	BSADP/Agro Input Dealers Union 
	Farmers and Extension Agents & Agric Stakeholders 
	450
	BSADP/Agro Input Dealers

	7
	Training of extension agents and farmers on Striga control in sorghum , milliet and cowpea.
	BSADP
	Farmers and extension Agents
	256
	BSADP

	8
	Training of Extension Staff on Soil testing  and analysis
	BSADP/OCP Africa
	Extension Staff
	125
	BSADP/OCP Africa

	9
	Training and Campaign on the use of appropriate fertilizers.
	BSADP/OCP Africa
	Farmers
	6000
	BSADP/OCP Africa

	10
	Capacity building on post-harvest loses and storage 
	BSADP
	Farmers 
	400
	BSADP

	11
	Training and support on agronomic practices (Rice, Maize, Soyabeans)
	DEC
	Farmers
	60
	BSADP/DEC

	12
	Pre-season training 
	Extension Staff BSADP
	Extension Staff
	182
	BSADP

	13
	Training of farmers on dry season wheat, Rice and maize production.
	BSADP
	Farmers
	460
	BSADP

	14
	Capacity building on safe handling practices and application of pesticides 
	BSADP
	Farmers/EAS
	256
	BSADP

	15
	Training on management of soil resources and use of soil testing kits
	BSADP
	Extension workers 
	50
	BSADP


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	Promotion of Napier grass for intensive livestock production in the rural communities 
	NASARUN
	Adopted 
	

	2
	Promotion of pod borer resistant cowpea (PBR)
	IAR,
	Adopted 
	

	3
	Promotion of I2 vaccines for control of new castle disease in rural communities to boost poultry production.
	NVRI
	Adopted 
	

	4
	Promotion of orange flesh potatoes for nutritional value
	Kaduna/plateau states
	Adopted  
	

	5
	Promotion of solar drier to the rural communities.
	NSPRI
	Adopted 
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	Agro-climatic Resilience in Semi-Arid landscape (ACReSAL)
	2022
	5 Years
	Community Climate resilience-

Community investment

Community strengthening

	2
	Livestock Productivity and Resilience Support Project (L-PRES)
	2023
	5 years
	Improving livestock productivity and commercialization.

(iii) Supporting Livestock Producer Organizations  and other value chain operators to improve their performance and for promoting inclusive and resilience supply chains.  

	3
	Small Holder Horticulture Empowerment and Promotion(SHEP)
	2022
	Years
	1. Market linkage to vegetable farmers

2. Capacity building on vegetable production and marketing 

	4
	Soil Value Project

 
	2025
	10 Years
	Improving soil fertility

Maximum utilization of water shed in the state

	5
	OCP Africa
	2024
	5 Years
	Improving soil fertility

Soil fertility test

Promoting use of appropriate fertilizer.

	6.
	Women Farmers Advancement Network (WOFAN)
	2024
	10 years 
	Support and empowerment to women groups, Youth and people with special needs.


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Available for sale at BASAC Stores and reputable Agro input dealers

	2
	Credit
	Farmers linked to BOA NIRSAL and other financial institutions.

	3
	Agro-chemical
	Available at BASC Stores and reputable Agro inputs dealers

	4
	Tractor/Animal Traction
	Tractor Hiring Unit, Ministry of Agriculture

	
	
	


CONSTRAINTS 

i. Inadequate qualified man power due to retirement 

Name of ADP: BAYELSA STATE ADP

Postal address:

Email:






Telephone_______________________

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	NIL
	NO FUNDS

	2
	FNTs
	12
	NIL
	ONCE A MONTH

	3
	OFARs
	6
	NIL
	LACK OF FUND

	4
	No. of Farm Families
	95474
	15912
	

	5
	No. of SPATs established 
	1099
	102
	

	6
	No. of MTPs
	29
	NIL
	NO INPUT/FUND

	7
	No. of Field days
	58
	10
	

	8
	No. of Agric Shows
	QUARTELY
	NIL
	LACK OF FUNDS

	9
	No. of group formed
	58
	10
	

	10
	No. of Pre-season training per year
	1
	1
	CONDUCTED

	11
	No. of Post-season training per year
	
	
	

	12
	Extension publications produced (No. of Titles)
	
	
	

	
	Bulletins 
	1000
	NIL
	

	
	Guides
	
	
	

	
	Leaflets
	
	
	

	
	Posters
	
	
	

	
	Others
	
	
	

	13
	Zonal Steering Committee Meeting
	4
	NIL
	

	14
	Zonal Technical Committee Meeting
	4
	NIL
	

	15
	Zonal REFILS workshops
	
	NIL
	

	16
	No of Extension Workers (VEAs)
	174
	23
	

	17
	No of Extension workers (BESs)
	8
	NIL
	

	18
	EA/Farmer ratio in the state
	1:4151
	
	


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins

1. 

2.

3.

4.

5.


	200
	NIL
	

	2
	Guides

1.MACRO PROPAGATION OF BANANA AND PLANTAIN 

2.FISH FARMING

3.RICE PRODUCTION/PROCESSING

4.CASSAVA PRODUCTION

5.
	             300   

150

300

50                                
	NIL
	

	3
	Leaflets

1. 

2.

3.

4.

5.
	
	
	


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4


	MACRO PROPAGATION OF BANANA/PLANTAIN SUCKER MULTIPLICATION

SWAMP RICE PRODUCTION

RABBIT PRODUCTION

ORANGE FLESH SWEET POTATO


	NO

NO

NO

NO
	NO

NO

NO

NO
	QUARTERLY

QUARTERLY

QUARTERLY

QUARTERLY
	97.1 FM

97.1 FM

97.1 FM

97.1 FM
	45 MINS

45 MINS

45 MINS

45 MINS


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2
	PLANTAIN SUCKER MULTIPLICATION

PRODUCTION OF ORANGE FLESH SWEET POTATO


	NO

NO
	NO

NO
	QUARTERLY

QUARTERLY
	NTA BAYELSA

NTA BAYELSA
	30 MINS

30 MINS


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1

2

3


	PRE-SEASON TRAINING

NATIONAL AGRICULTURAL RESEARCH EXTENSION SUMMIT

TRAINING ON CASSAVA DISEASE MANAGEMENT AT NRCRI, UMUDIKE
	ADP

FMAFS

CENTRAL AND WEST AFRICAN VIRUS EPIDEMIOLOGY FOR FOOD SECURITY (WAVE) 
	EAS,SMS,ZM AND DES

PM AND DES

EAS
	25

2

4
	NRCRI


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	PIG FARMING
	NDU
	ADOPTED
	

	2
	POULTRY
	NDU
	ADOPTED
	

	3
	ORANGE FLESH SWEET POTATO
	NRCRI
	ADOPTED
	

	4
	POD BORER RESISTANT (PBR) COWPEA
	NAELS/AATF
	ADOPTED
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	NG-CARES
	2020
	3 YEARS
	EMPOWERMENT 

	2
	LIFE-ND
	2020
	6 YEARS
	EMPOWERMENT OF YOUTH AND WOMEN

	3
	
	
	
	

	4
	
	
	
	

	5
	
	
	
	

	6
	
	
	
	

	7
	
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	FARMERS DEPEND ON THE OPEN MARKET AT A HIGH COST

	2
	Credit
	FARMERS ARE LINKED TO FINANCIAL HOUSES FOR ASSISTANCE

	3
	Agro-chemical
	AVAILABLE AT THE OPEN MARKET AT A HIGH COST

	4
	Tractor/Animal Traction
	TRACTOR IS AVAILABLE FOR HIRE AT THE MINISTRY OF AGRICULTURE, NO ANIMAL TRACTION

	5
	MTRM situation Report 
	LACK OF FUNDS FOR MTRM


CONSTRAINTS  

i. lack of available funds

ii. lack of mobility of extension of extension activities in the state

iii. Shortage of extension officers in the field

iv. limitation in regular training of farmers

Name of ADP: BENUE ADP 

Postal address: PMB 102125

[image: image140.emf]Email:
doomeozer@gmail.com



                           Telephone:08034490767


A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs/QTRM
	4
	3
	IFAD Sponsored

	2
	FNTs/MTN
	        12
	-
	

	3
	OFARs
	        -
	-
	No funds

	4
	No. of Farm Families
	413159
	413159
	1991 VLS

	5
	No. of SPATs established 
	        -
	-
	

	6
	No. of MTPs
	        24
	24
	Sasakawa/ Tourba

	7
	No. of Field days
	        17
	17
	Sasakawa/ Tourba

	8
	No. of Agric Shows
	        1
	1
	Benue State Govt.

	9
	No. of group formed
	
	
	

	10
	No. of Pre-season training per year
	        2
	2
	Sasakawa/ Tourba

	11
	No. of Post-season training per year
	        2
	2
	Sasakawa/ Tourba

	12
	Extension publications produced (No. of Titles)
	   None
	None
	Lack of funds

	
	Bulletins 
	        -
	-
	-

	
	Guides
	-
	-
	-

	
	Leaflets
	-
	-
	-

	
	Posters
	-
	-
	-

	
	Others
	-
	-
	-

	13
	Zonal Steering Committee Meeting
	       1
	-
	Lack of funds

	14
	Zonal Technical Committee Meeting
	       1
	-
	Lack of funds

	15
	Zonal REFILS workshops
	       1
	-
	Funding challenge

	16
	No of Extension Workers (VEAs)
	      500
	270
	Volunteer

	17
	No of Extension workers (BESs)
	      47
	47
	Volunteer

	18
	EA/Farmer ratio in the state
	 1:1000
	1:20,000
	Shortage of staff


E. TRAINING PROGRAMMES

	SN
	Title


	Organizers


	Categories of Trainees
	No of Trainees
	Collaborators 

	1

2

3

4

5
	Tourba Carbon farming

Organic fertilizer formulation
Extension(farmer.chart)

NSA/RA/MOA
	Tourba Jostum

Digital green

Sasakawa
	Ea

Farmers

Eas

Ea/farmers
	8

20

30

75
	Tourba/ bnarda

Bnarda

Bnarda

Bnarda


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	Strip cropping soyabean/sorghum
	Sasakawa
	Adopted 
	Ongoing

	2
	Cassava Maize Intercrop
	”
	”
	”

	3
	Regenerative Agriculture
	Tourba
	Adopted
	Ongoing

	4
	Market Oriented Agriculture
	Sasakawa/SHEP
	”
	”

	5
	Organic fertilizer formulation
	SHEP
	Adopted
	Ongoing


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	Tourba Carbon farming 
	2025
	5
	Carbon sequestration

	2
	Sasakawa Africa
	2024
	5
	Tot/nsa/ra/moa

	3
	Heifer International
	2022
	5
	Tot/empowerment

	4
	Extension Africa
	2022
	5
	Tot/ RSI

	5
	GIZ
	2020
	Close Out
	Tot/rice cultivation

	6
	WOFAN/Palm Valley
	2023
	5
	

	7
	IFAD/VCDP
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	675 Trucks of assorted fertilizer

	2
	Credit
	[image: image141.jpg]




	3
	Agro-chemical
	None

	4
	Tractor/Animal Traction
	25 Tractors

	5
	MTRM situation Report /QTRM
	3 meetings held with very very few staff


CONSTRAINTS 

Acute shortage of Staff in the organization.

Lack of financial support for the organization.

Name of ADP: BORNO STATE AGRICULTURAL DEVELOPMENT PROGRAMME (BOSADP)  

Postal Address: SHEHU LAMINU WAY, OPP. BRTV, MAIDUGURI 

Email: abdulkadirfura@gmail.com

Telephone: 080-29709470, 

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	2
	Lack of fund

	2
	FNTs
	24
	8
	

	3
	OFARs
	4
	1
	

	4
	No. of Farm Families
	470,000
	470,00
	

	5
	No. of SPATs established 
	54
	24
	

	6
	No. of MTPs
	2
	Nil
	

	7
	No. of Field days
	2
	1
	

	8
	No. of Agric Shows
	1
	Nil
	

	9
	No. of group formed
	250
	140
	

	10
	No. of Pre-season training per year
	2
	1
	

	11
	No. of Post-season training per year
	4
	2
	

	12
	Extension publications produced (No. of Titles)
	1000
	440


	

	
	Bulletins 
	0
	0
	

	
	Guides
	600
	300
	

	
	Leaflets
	400
	140
	

	
	Posters
	0
	
	

	
	Others
	
	
	

	13
	Zonal Steering Committee Meeting
	2
	Nil
	

	14
	Zonal Technical Committee Meeting
	2
	Nil
	

	15
	Zonal REFILS workshops
	2
	1
	

	16
	No of Extension Workers (VEAs)
	200
	88
	

	17
	No of Extension workers (BESs)
	20
	6
	

	18
	EA/Farmer ratio in the state
	1;500
	1: 25,000
	


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins

1. 

2.

3.

4.

5.


	
	
	

	2
	Guides

1. Guide on maize production

2.Guide on cowpea production

3.Guide on millet production

4.

5.
	200

200

200
	100

100

100
	IITA

	3
	Leaflets

1. safe & effective use of pesticide

2.

3.

4.

5.
	400
	140
	


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4

5
	FILIN MANOMA

PARASKURAM BAREWUYE
	NO

NO
	YES

YES
	Once in a week

Once in a week
	BRTV

BRTV
	45 mins

45 mins


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2
	BACK TO FARM

NOMA TUSHEN ARZIKI
	NO

NO
	YES

YES
	Once in a week

Once a week
	BRTV


	1 hr

45mins


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	FADAMA NG-CARE
	2023
	 4 yrs
	Livelihood, irrigation farming support & infrastructure

	2
	L- PRES
	2024
	 5 yrs
	Livestock management, small ruminant upgrading  & training

	3
	RAAMP
	2026
	 4 yrs
	Agricultural value chain and marketing linkages

	4
	SAPZ
	2026
	4yrs
	Agro-processing activities


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	High cost of fertilizer

	2
	Credit
	Too much bureaucracy in accessing agric loans 

	3
	Agro-chemical
	

	4
	Tractor/Animal Traction
	Owned by government with few owned by Individual

	5
	MTRM situation Report 
	Lack of fund for conducting it


[image: image142.jpg]


[image: image143.jpg]


                                                                                                                                                   

Name of ADP: Cross River
Postal address: P.M.B. 1178
Email:
cradpcalabar@gmail.com



 Telephone: 08064219782
A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	1
	FAO support

	2
	FNTs
	26
	24
	

	3
	OFARs
	5
	Nil
	No funds

	4
	No. of Farm Families
	-
	481,506
	

	5
	No. of SPATs established 
	500
	Nil
	

	6
	No. of MTPs
	250
	180
	

	7
	No. of Field days
	50
	2
	

	8
	No. of Agric Shows
	1
	Nil
	

	9
	No. of group formed
	320
	135
	

	10
	No. of Pre-season training per year
	2
	1
	FAO Support

	11
	No. of Post-season training per year
	2
	Nil
	

	12
	Extension publications produced (No. of Titles)
	
	
	

	
	Bulletins (Climate Smart Agriculture)
	500
	Nil
	

	
	Guides (FFS and FFBS on Cocoa)
	500
	500
	

	
	Leaflets (CSA Cocoa and oilpalm Prod.)
	500
	500
	

	
	Posters
	500
	Nil
	

	
	Others
	-
	-
	

	13
	Zonal Steering Committee Meeting
	4
	1
	

	14
	Zonal Technical Committee Meeting
	2
	Nil
	

	15
	Zonal REFILS workshops
	1
	1
	

	16
	No of Extension Workers (VEAs)
	144
	46
	

	17
	No of Extension workers (BESs)
	18
	1
	

	18
	EA/Farmer ratio in the state
	1:1000
	1: over 10,000
	


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins

1. 


	500
	Nil
	IFAD LIFE-ND

	2
	Guides

1. FFS and FFBS on Cocoa and Oil palm
2. Crop Prod. Made Easy
	500

500
	2000

1000
	FAO FOLUR

Project Grow

	3
	Leaflets

1.Climate Smart Cocoa and oil palm production

2. Digital tools for Digital Solutions


	500

500
	2000

Nil
	FAO FOLUR

USAID FTF


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4

5
	Farmers Corner


	NO
	NO
	Weekly
	Cross River Broadcasting Corporation (CRBC)
	30Mins.


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1
	Farmers Corner
	NO
	NO
	Weekly
	CRBC
	1 hour


E. TRAINING PROGRAMMES
	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1.

2. 

3

4.

5.
	GAP Training on Cocoa, Rice and Cassava production

MTRM

In-season training 

Formation of Cooperatives and Group dynamics

Mini Tractor Operations and Maintenance
	SAPZ

FAO

FAO

MOA

MOA
	Extension Agents

ZMs, ZEOs SMSs, Sub Prog. Heads

Extension Agents

Farmers

Tractor beneficiaries


	45

25

35

150

108
	SAPZ/CRADP

FAO/NIFOR/CRADP

FAO/CRADP

Ministry of Agric.

Project Grow/MOA


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	ICT Integration in Extension Services Delivery (Use of Agric Videos, Digital Apps.)
	USAID FTF Extension Activity
	Adopted
	

	2
	Complementary fish feeding using Black Soldier Fly(BSF) and Duckweed
	“
	Adopted
	

	3
	Rice Processing using False Bottom Technology
	JICA
	Adopted
	

	4
	Rapid Cassava Stems Multiplication
	NRCRI
	Adopted
	

	5
	Pod Borer Resistant Cowpea
	IAR & T
	Adopted
	

	6
	Seed Yam Multiplication using the Mega sett technology
	NRCRI
	Adopted
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	Livelihood Improvement Family Enterprises (LIFE-ND) Project: Additional Financing

	September 2025
	3 years
	The project is using incubation model for the implementation of her activities

Training of Incubatees on production, processing and marketing options.

Provision of access  feeder road

Distribution of agro inputs and simple farm tools/machinery.

General capacity building

	2
	Special Agro Industrial Processing Zone (SAPZ)
	2023
	5years
	Establishment of processing hubs in component one through crop production in component two

	3
	PROJECT GROW (State Government facilitated)


	2023
	6years
	Focusing on 5 value chains of Rice, Maize, Cassava, Aquaculture and Fodder.

Guaranteeing access to credit and off taking of farmers produce for the ready market.

	4
	Homestead Cowpea Programme
	2025
	2 years
	Procurement, Cultivation and Consumption of Sampea 20T Pod Borer Resistant Cowpea to improve household nutrition

	5
	Food Systems, Land Use and Restoration Impact Program (FAO FOLUR)
	2023
	3
	Transformation of food and Land use systems.


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Seeds
	5.5 metric tons of Pod borer resistant Cowpea procured and distributed to the farmers for cultivation and consumption after harvest.

	2
	Fertilizer
	Ministry of Agric collaborating with FAO is about to distribute seeds and fertilizer to farmers

	3
	Credit
	Farmers and Commodity Associations are linked to Financial Institutions for Credit. Project Grow is bridging the gap too.

	4
	Agro-chemical
	Farmers procure from reputable Agro Input Dealers

	5
	Tractor/Animal Traction
	108 Mini tractors has been procured and 108 farmer cooperatives have subscribed to it. Training on its usage has been done and distribution is ongoing.

	6
	MTRM situation Report 
	One was held through the support of FAO FOLUR


CONSTRAINTS

Poor funding generally affected key extension activities

Inadequate mobility like Motor vehicles for monitoring of field activities (No vehicle for PM and for Extension supervision)

High Extension Agent/Farm Family Ratio (1: over 10,000)

Non-payment of field transport allowance

Dilapidated training halls across the zones

Inadequate training and re-training of Extension Workers.

[image: image144.jpg]


[image: image145.emf]
Name of ADP:
DELTA AGRICULTURE AND RURAL DEVELOPMENT AUTHORITY (DARDA)

Postal Address:
P.M.B. 1006, Ibusa, Delta State.


Email:

mamodeogboru@gmail.com





Telephone:

08032711644, 07038485500

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	1
	

	2
	FNTs
	24
	20
	

	3
	OFARs
	6
	4
	3 OFARS were Sponsored by OCP-Africa

	4
	No. of Farm Families
	545,987
	545,987
	2020 Population Estimate

	5
	No. of SPATs established 
	-
	-
	

	6
	No. of MTPs
	125
	6
	

	7
	No. of Field days
	125
	5
	

	8
	No. of Agric Shows
	2
	1
	World Food Day

	9
	No. of group formed
	200
	73
	

	10
	No. of Pre-season training per year
	1
	1
	

	11
	No. of Post-season training per year
	1
	-
	

	12
	Extension publications produced (No. of Titles)
	12
	-
	

	
	Bulletins 
	3
	-
	

	
	Guides
	3
	-
	

	
	Leaflets
	3
	1
	Sponsored by WAVE Project

	
	Posters
	2
	-
	

	
	Others
	1
	-
	

	13
	Zonal Steering Committee Meeting
	4
	1
	

	14
	Zonal Technical Committee Meeting
	-
	-
	

	15
	Zonal REFILS workshops
	3
	1
	

	16
	No of Extension Workers (VEAs)
	200
	105
	

	17
	No of Extension workers (BESs)
	25
	22
	

	18
	EA/Farmer ratio in the state
	1: 1000
	1:8666
	


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins

1. 

2.

3.

4.

5.


	3
	-
	

	2
	Guides

1. 

2.

3.

4.

5.
	3
	-
	

	3
	Leaflets

Practical Guide on Cassava Brown Streak Disease (CBSD)


	3
	​1


	Central and West African Virus Epidemiology (WAVE) Project


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1

2

3

4

5
	Training of Officers on ICT Software Tools for Data Collection

Advancing Climate Smart Agriculture (CSA) for Enhancing Resilience Productivity and Stability through Effective Extension Service Delivery System

Training of Extension Agents and Farmers on Organic and Agro-ecology at the 3 Zones

National Extension Research Submit

Socio economic and geospatial assessment project on Livestock productivity and resilience

	Ministry of Agriculture and Natural Resources

AESON Webinar Capacity Building 
Environment and Action Aid Nigeria

FME


	Selected Extension Officers from the 3 Zones

Director of Extension Service

2 Extension Agents/Zone and 50 Farmers/Zone

Director of Extension

EXTENSION OFFICERS
	1

156

1

3
	ACTION AID

FS


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	Agro ecology farm practices 
	Action-Aid/ENVIRUMEDIC
	Adopted
	

	2
	Organic farming
	Action-Aid/ENVIRUMEDIC
	Adopted
	

	3
	Homestead fisheries production
	NIOMR
	Adopted
	

	4
	Best management practices for poultry 
	NARIs
	Adopted
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Delta Agricultural Procurement Agency (DAPA) is saddled with the responsibility of procurement and sales of Agricultural inputs in the state.

The FMA&FS also provided maize seeds to beneficiaries of the climate resilient practices for maize production.

	
	
	Fertilizers sales are on-going by DAPA. 

Fertilizers were also provided by FMA&FS for the beneficiaries of climate resilient practices for Cassava, Yam and Cowpea productions.

	2
	Credit
	-

	3
	Agro-chemical
	Various agro chemicals are available at DAPA stores for sales to end users.

Agro Chemicals were also provided for the beneficiaries of the emergency training of youth and women on Yam and Cassava productions.

	4
	Tractor/Animal Traction
	Tractor Hiring Agency (THA) makes tractors available to farmers at reduced rate.

Grinding Machines were provided by FMA&FS under the emergency empowerment of youth and women on Yam processing, packaging, value addition and utilization.

	5
	MTRM situation Report 
	Only 1 MTRM was conducted for the year under review


CONSTRAINTS 

Paucity of funds for efficient and effective delivery of Extension Services

Low EA/Farm family ratio of 1:8666

Inadequate project vehicles/motorcycles

[image: image48.jpg]


                                                                                                                                    [image: image49.png]



ANNUAL NATIONAL AGRICULTURAL EXTENSION REVIEW AND PLANNING, MEETING

AGRICULTURAL DEVELOPMENT PROGRAMME REPORT FOR 2025

Name of ADP: EBONYI STATE ADP

Postal address: PMB 040 ABAKALIKI

Email: ebonyistateadp@gmail.com


Telephone: 08066836476

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	10
	

	2
	FNTs
	26
	24
	

	3
	OFARs
	4
	0
	

	4
	No. of Farm Families
	1,500,000
	969,000
	

	5
	No. of SPATs established 
	10,100
	936
	

	6
	No. of MTPs
	500
	462
	

	7
	No. of Field days
	450
	105
	

	8
	No. of Agric Shows
	25
	0
	

	9
	No. of group formed
	9150
	8400
	

	10
	No. of Pre-season training per year
	3
	3
	

	11
	No. of Post-season training per year
	3
	2
	

	12
	Extension publications produced (No. of Titles)
	1200
	200
	

	
	Bulletins 
	300
	0
	

	
	Guides
	300
	200
	

	
	Leaflets
	300
	0
	

	
	Posters
	300
	0
	

	
	Others
	
	
	

	13
	Zonal Steering Committee Meeting
	1
	1
	

	14
	Zonal Technical Committee Meeting
	2
	2
	

	15
	Zonal REFILS workshops
	1
	1
	

	16
	No of Extension Workers (VEAs)
	450
	100
	

	17
	No of Extension workers (BESs)
	36
	23
	

	18
	EA/Farmer ratio in the state
	1/80
	1/8270
	


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins

1. pre-season, in-season and post-harvest management of crop

2. The impart of various Agric intervention in the State


	10,000

10,000


	6,000

5,000


	ADP/Min of Agric

ADP/all Agric development programme



	2
	Guides

1. Rice planting techniques

2. Cassava planting techniques


	10,000

10,000


	6,500

8,750


	ADP/Min of Agric/Indorama

ADP/Min of Agric



	3
	Leaflets

1. Hand leaflet on rice blast management

2. Hand leaflet on the safety and handling management of pesticides


	40,000

40,000


	15,000

10,000


	ADP/Min of Agric

ADP/Min of Agric




C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4


	Ebonyi State Agric Forum

The youth and Agriculture

One on one with Agric expert on how to prevent food scarcity in our society

Embarking on smart farming to close the gap of climate resilience and its effects on farmers


	YES

yes

yes

yes


	YES

yes

yes

yes


	Weekly

Weekly

Monthly

weekly


	EBBC

EBBC

EBBC

Legacy FM


	1HR

1HR

1HR

30 min




D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4
	Oge oru Ubi

Monthly Review of Progress on Agric Activities

Let us know your farming challenges

Why we should go back to farming
	YES

yes

yes

yes
	YES

yes

yes

yes
	2/WEEK

monthly

monthly

twice a month
	NTA ABAKALIKI

EBBC/NTA ABAKALIKI

NTA ABAKALIKI

NTA ABAKALIKI


	30MINS

30MINS

30MINS

30 MINS


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	period/time
	No of Trainees
	Collaborators 

	1

2

3

4

5

6

7


	Pre-season training

In-season and post-harvest training

Stepdown on capacity building on rural farmers in Ebonyi State on Rice value additionStrengthening Agricultural Research innovation and extension service delivery

Reducing malnutrition and improve nutritional security through the improved food system

Stepping down on MIP technologies and GAP for a rapid increase in crops, fisheries, livestock value chain

Reposition agricultural cooperatives as a vehicle for emergency of sustainable cluster

Training on Agro-Ecology to small holders Farmers


	EBADEP

EBADEP

EBADEP

EBADEP

EBADEP

EBADEP

EBADEP


	Extension Agents, ZEOs and Lead Farmers

Extension Agents, ZEOs and Lead Farmers

Farmers

Eas/Farmers (Youth & women

Rural women

Farmers/Extension Agents 

Farmers


	Jan-Feb 2025

June-Sept 2025

April 2025

March, 2025

Feb-Sept 2025

March 2025

Feb 2025


	3000

3,660

1,200

3,195

992

3,630

600
	EBADEP/VCDP/Min of Agric

EBADEP/IFAD VCDP/Min of Agric

EBADEP/UNN

EBADEP/UNN/Min of Agric

EBADEP/Min of Agric/Min of Health/Helen Keller

EBADEP/Min of Agric/L-Press

EBADEP /and State Min of Agric & Natural Resources/NG cares




F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	Dry Season Vegetable Production 
	EBADEP, Hellen keller


	Adopted
	Small holders farmers grow vegetables(Telferia, spinach all the year round 



	2
	Use of certified improved rice seed and pest resistance and flood tolerant varieties 


	EBADEP, Strategic Seed Companies and IFAD VCDP


	Adopted
	High yielding, mature early, resistance to pest and diseases, taste and command market price



	3
	Processing and utilization of cassava peels into briquettes and animal feed respectively as a waste to wealth


	EBADEP/VCDP


	Adopted
	Smaller holders farmers are targeted for they use it to feed their livestock and organic manure

	4


	Line planting of rice and use of GAP in rice production to get optimum yield.


	EBADEP/VCDP


	Adopted
	Easy management practices and higher yield due to optimum plant population



	5
	Digital E-extension service delivery using rice advice tools. Area calculator for farm measurement
	EBADEP/VCDP/UNN


	Adopted
	Farmers will optimally utilize their android phones for farming activities




G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	IFAD VCDP 


	2014/2015
	On-going
	to enhance on a sustainable basis Incomes and food security of poor rural households engaged in the production, processing and marketing of rice and cassava value chain


	2
	ZERO HUNGER PROJECT 


	2021
	On-going
	Promotion on GAP in Rice Production, processing and value addition 



	3
	Nigeria Covid Action Recovery Economic Stimulus (NG-CARES
	2020
	On-going
	Empowering rural farmers through support of agricultural inputs, fertilizers, herbicides, seeds, poultry, piggery, cassava cuttings etc 


	4
	SPAC PROJECT


	2006


	On-going
	Agro-Ecology promotion, Educational support and Health



	5
	HELEN KELLERS INTL


	2024


	On-going
	Transformation of life through Nutrition and Agricultural products



H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	The State Government distributed over 49,200 bags of fertilizers to farmers in the State in 2025 farming season across the 13 LGAs. The cost of organic and inorganic fertilizers are on the increase daily. 



	2
	Credit
	The State Government gave out 2 million naira each to over 500 Ebonyi youths to enable them embark on aggressive Agric production and some were sent to Songhai for 6 months training.



	3
	Agro-chemical
	Integrated farm management was adopted in Ebonyi because of high increase of agro-chemical. State Government distributed over 16,000 cartons of selective and non-selective herbicides to farmers across the 13 LGA of the State between 2025 farming season



	4
	Tractor/Animal Traction
	The State Government Procured tractors and other small implements like power tillers through NG-Cares and distributed to farmers to reduce the cost of labour which is on the very high side since 2024 to 2025 while animal traction was not used in Ebonyi State.



	5
	MTRM/QTRM


	The MTRM and QTRM in the three zones of the State are consistence and remarkable and progressive report had been achieved over the years. There are also feedback reports from the staff which had guided the programme in overall programme implementation and documentation.



	6
	Poultry


	Revival of Ebonyi State Government poultry farm, Nkaliki Rd which had been moribund for over 16 years. Distribution of 600 livestock starter packs to youths and women across the 13 LGA in the State to promote youth/women entrepreneurship 

	7
	Livestock Farming 


	The L-press activities is ongoing in Ebonyi State. They have trained livestock farmers across the 13 LGAs in Ebonyi State



	
	
	


      CONSTRAINTS 

None funding of ADP by State Government

Inadequate Staff both at the Zonal and Headquarter

Lack of mobility for both field, zonal and Headquarter Staff for field activities, monitoring and supervision

Problem of annual Budget approval without releasing of the fund to ADP by the State Government.

Lack of fund in conducting regular MTRM, and invitation of research Institutes and universities.

Dilapidated infrastructure both at the headquarters and zonal Ebonyi State ADP.

Lack of fund to partner with research institute and universities

Incidence of flood in rice farms in the Sta

Name of ADP: EDO ADP
Postal address: P.M.B.1698 oko, Ogba Road, Benin city

Email:
edostateadp@gmail.com

Telephone 08054499997

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	2
	

	2
	FNTs
	26
	23
	

	3
	OFARs
	 2
	-
	

	4
	No. of Farm Families
	>300,000
	>300,000
	

	5
	No. of SPATs established 
	690
	2,876
	

	6
	No. of MTPs
	184
	297
	

	7
	No. of Field days
	1
	0
	

	8
	No. of Agric Shows
	1
	0
	

	9
	No. of group formed
	250
	513
	

	10
	No. of Pre-season training per year
	1
	0
	

	11
	No. of Post-season training per year
	1
	0
	

	12
	Extension publications produced (No. of Titles)
	
	
	

	
	Bulletins 
	
	
	

	
	Guides
	4
	4
	

	
	Leaflets
	.
	-
	

	
	Posters
	.
	-
	

	
	Others
	.
	-
	

	13
	Zonal Steering Committee Meeting
	4
	1
	

	14
	Zonal Technical Committee Meeting
	2
	0
	

	15
	Zonal REFILS workshops
	1
	1
	

	16
	No of Extension Workers (VEAs)
	288
	26
	

	17
	No of Extension workers (BESs)
	36
	12
	

	18
	EA/Farmer ratio in the state
	1:800
	1:7895
	


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins

1. 


	.
	-
	.

	2
	Guides

1. PRODUCTION OF CASSAVA

2. PRODUCTION OF MAIZE

3. PRODUCTION OF BROILER

4. PRODUCTION OF YOUR     

     FARMILY FISH.
	1,000

1,000

1,000

1,000
	500

500

500

500
	


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1


	Cassava production
	
	Yes
	Weekly
	EBS
	30Min

	2
	Record keeping in farming
	
	Yes
	Weekly
	EBS
	30Min

	3
	Land preparation
	
	 Yes
	Weekly
	EBS
	30Min

	4
	Cassava stem multiplication
	
	Yes
	Weekly
	EBS
	30Min

	5
	Stress management in fish
	
	 Yes
	Weekly
	EBS
	30Min

	6
	Crop protection and weed control II
	
	Yes
	Weekly
	EBS
	30Min

	7
	Plantain production I
	
	Yes
	Weekly
	EBS
	30Min

	8
	Disease in ruminants, poultry and piggery I
	
	Yes
	Weekly
	EBS
	30Min

	9
	Selective weed spraying (weed control)
	
	Yes
	Weekly
	EBS
	30Min

	10
	Mange in sheep/goats
	
	Yes
	Weekly
	EBS
	30Min

	11
	Cowpea production
	
	Yes
	Weekly
	EBS
	30Min

	12
	Turkey production
	
	Yes
	Weekly
	EBS
	30Min

	13
	Weed control
	
	Yes
	Weekly
	EBS
	30Min

	14
	Ogbono and coconut production
	
	Yes
	Weekly
	EBS
	30Min

	15
	Yam production
	
	Yes
	Weekly
	EBS
	30Min

	16
	Plantain production
	
	Yes
	Weekly
	EBS
	30Min

	17
	Broiler production
	
	Yes
	Weekly
	EBS
	30Min

	18
	Fertilizer application
	
	Yes
	Weekly
	EBS
	30Min

	19
	Disease in goat
	
	Yes
	Weekly
	EBS
	30Min

	20
	Disease in poultry
	
	Yes
	Weekly
	EBS
	30Min

	21
	Input distribution
	
	Yes
	Weekly
	EBS
	30Min

	22
	Maize production
	
	Yes
	Weekly
	EBS
	30Min

	23
	Sorting of fish
	
	Yes
	Weekly
	EBS
	30Min

	24
	Pig production
	
	Yes
	Weekly
	EBS
	30Min

	25
	Vaccination in poultry
	
	Yes
	Weekly
	EBS
	30Min


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1
	Strengthening capacity for M/E enhanced project performance and organization.
	MAFS
	M/E officers
	5
	Edo ADP.


	2
	Monthly technology review/meeting
	Edo ADP
	Extension officers
	54
	NIFOR and Ministry of Science and Technology.

.


	3
	Capacity building on comprehensive business model 
	LPRES
	Extension officers
	15
	Edo ADP

	4
	Documentary production on project achievement and impact 
	LPRES
	Extension officers
	10
	Edo ADP

	5
	Create digital content, communication and collaborate online

	EDSG
	Planning officer
	2
	Edo ADP

	6
	Public speaking and speech writing 
	EDSG
	Admin officers
	2
	Edo ADP

	7
	Occupational health and safety on livestock

	EDSG
	Evaluation officer, Agroforestry officer Subject matter specialists (livestock, women in agriculture), Block extension supervisors and Extension agents 
	20
	Edo ADP

	8
	Training on livestock business development and investment plan for farmers and MSME in Edo state

	L-PRES


	Extension officers
	15
	Edo ADP

	9
	 Women in agriculture training 

	IFAD LIFE-ND


	Women farmers 
	18
	Edo ADP

	10
	Sensitization workshop for project implementation unit and selected stakeholders on GBV/PSEAH 

	IFAD LIFE-ND


	Extension officers
	15


	Edo ADP

	11
	Adoption / development and production of extension training manual from the NCO

	 IFALIFE-ND


	Extension officers
	15
	Edo ADP

	12
	Capacity building of 60 State level Extension agent on GAHP
	L-PRES
	Extension officers
	60
	Edo ADP

	13
	Adoption and Review of Extension training manual from the NCO
	 L-PRES
	Extension officers
	25
	Edo ADP

	14
	Training on Socially inclusive capacity building for state level Extension agent on emerging Trend in GAPHS
	 L-PRES
	Extension officers 
	78
	Edo ADP

	15
	Training on Capacity building workshop for Master trainers/Facilitators on establishment of farmer field school and management
	L-PRES
	Extension officers
	80
	Edo ADP

	16
	Training on Business Model for pasture development
	 L-PRES
	Extension officers
	75
	Edo ADP

	17
	Registry Admin and management.
	EDSG
	Director and Evaluation Officer
	2
	Edo ADP

	18
	leadership development programme
	EDSG
	Directors
	2
	Edo ADP

	19
	Livestock policy development and implementation process
	EDSG
	Extension officers
	30
	Edo ADP

	20
	High level dialogue and summit on agricultural and rural development for national transformation and economic freedom in Nigeria
	ARMTI.
	Programme manager
	1
	Edo ADP

	21
	Knowledge sharing session on AI -powered farmer chat. for Extension  officers.
	IFAD LIFE-ND.
	Extension, Agents
	16
	Edo ADP, LG, etc.

	22
	Training of Trainers (TOT) workshop on real-time transboundary and migratory agricultural pests’ information management system.


	FMAFS
	Technical officers
	10
	Edo ADP


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	Pyramidal Staking in yam production 
	IITA/Umudike
	Adopted
	60%

	2
	Seed yam production through yam minisett technology
	IITA
	Adopted
	45%

	3
	Intensification of Cocoyam production
	Umudike
	Adopted
	30%

	4
	Intensification of Cowpea production 
	IAR&T
	Adopted
	45%

	5
	Intensification of Soybean production
	IAR&T
	Adopted
	20%

	6
	Bio-fortified crops (sweet potato, cassava)
	IITA/Umudike
	Adopted
	40%

	7
	Post-harvest handling of rice and use of false bottom in rice par-boiling
	JICA
	Adopted
	55%

	8
	Cassava Base crop mixture 
	IITA/Umudike
	Adopted
	75%

	9
	Yam Based Crop mixture
	Umudike
	Adopted
	60%

	10
	Sole maize production
	NCRI
	Adopted
	50%

	11
	Cassava Sole
	IITA/Umudike
	Adopted
	50%

	12
	Oil palm Production
	NIFOR
	Adopted
	50%

	13
	Good animal husbandry practices
	NAPRI
	Adopted
	40%

	14
	Good water quality and stock density in fishery
	NIFFR
	Adopted
	50%


G. SPECIAL PROJECTS.

	S/N
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	 EDO-CARES (FADAMA)
	2021
	7rs
	-Provision of Agricultural Input such as cassava, maize, vegetable seeds, fertilizers, poultry and fish.

-Provision of small irrigation facilities and rehabilitation of feeder roads,

-Provision of Agricultural Assets such as cassava mill. Rice mill, power tiller. Defeathering and generators

-Upgrading of wet market with water and sanitation facilities.

	2
	IFAD LIFE-ND
	2020
	3yrs
	-Establishment of sustainable Agribusiness Enterprises.

-Training of Incubators and incubates

-Conduct of survey Baseline in selected Local government Areas and communities.

-Establishment of Agribusiness- Driven infrastructure (Earthen farm roads, land development etc.)

Financial inclusion support to Agribusiness.

-Rural Institution strengthening

-Project management and coordination.


	


               H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Distribution of foliar fertilizer to 20 farmers and farmer groups in collaboration with FMAFS. 

Training and empowerment of 30 Farmers with foliar fertilizer in collaboration with FMAFS.

296 NPK fertilizer were distributed to farmers in collaboration with EDO- CARES (FADAMA), 

	2
	Credit
	Linkages to financial institution

	3
	Agro-chemical
	Farmers were empowered with 296 liters of pre-emergence herbicides and 296 packets of post-emergence herbicides respectively in collaboration with EDO- CARES (FADAMA).

	
	Farm implement 
	Training and empowerment of 30 Farmers with Knapsack sprayer in collaboration with FMAFS.

EDO- CARES (FADAMA) empowered 437 beneficiaries with 6 Cassava processing mill (8-ton capacity) each, 6 Tricycles,11 Power Tillers (13hp capacity),5 De-feathering Machines and Generators (6.5hp),11 Multipurpose Grinder,10 Motorized Sprayers (4 stroke engine)


	4
	Tractor/Animal Traction
	5 Tractor with implement by state government 

	5
	MTRM situation Report 
	 2 MTRM held because funds were not released.  


Constraints

Shortage in the number of extension agents.
Poor funding for extension activities etc.
High cost of land development.
Name of ADP: EKITI STATE AGRICULTURAL DEVELOPMENT PROGRAMME

Postal address: P.M.B. 5016, Ikole-Ekiti.

Email: - ekadep@yahoo.com


                 Telephone: 08064460268, 08062147247 

A. 2025 EXTENSION SUPPORT INDICATORS 

	S/N
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	5
	MTRM in Ekiti is supported by the Local Governments with venue and refreshment for participants by the hosting LGA.

	2
	FNTs
	24
	12
	FNTs were observed once a month during the year due to paucity of fund

	3
	OFARs
	9
	1
	No fund release for execution.

	4
	No. of Farm Families
	235,000
	235,000
	Reach out to farmers through Radio, TV, Village meeting

	5
	No. of SPATs established 
	16
	0
	Inputs support from supporting Institutions used to establish SPATs.

	6
	No. of MTPs
	16
	0
	Support from collaborative Institutions – IAR&T, IITA, etc.

	7
	No. of Field days
	16
	0
	Non availability of fund.

	8
	No. of Agric Shows
	2
	0
	Not done due to paucity of f und

	9
	No. of group formed


	60
	14
	Support by farmers groups

	10
	No. of Pre-season training per year
	1
	0
	No fund release

	11
	No. of Post-season training per year
	1
	0
	No fund release

	12
	Extension publications produced(No. of Titles)
	10,000
	
	No fund release

	
	Bulletins 
	2,000
	0
	No fund release

	
	Guides
	5,000
	0
	No fund release

	
	Leaflets
	3,000
	0
	No fund release

	
	Posters
	
	
	

	
	Others
	
	
	

	13
	Zonal Steering Committee Meeting
	4
	0
	Non was held

	14
	Zonal Technical Committee Meeting
	1
	0
	Non was held

	15
	Zonal REFILS workshops
	1
	1
	Held at IAR&T, Ibadan

	16
	No of Extension Workers (VEAs)
	177
	24
	Reduction by retirement

	17
	No of Extension workers (BESs)
	16
	16
	One BES per block

	18
	EA/Farmer ratio in the state
	1:1000
	1: 5,875
	The EA/Farmers’ ratio was on high side


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	S/N
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletin 

1. improved Yam production techniques.

2. Good Agricultural Practices (GAP) in maize production
	1,000

1,000
	 0

0
	To boost yam production for income generation of farmers in the State.

To boost and promote maize production in the State

	2
	Guide 

Yam multiplication techniques

Cassava Brown Streak Disease (CBSD) in Ekiti State.

Rapid multiplication of plantain.
	1000

5000

1000
	0

0

0
	In collaboration with IAR&T.

WAVE Project

Do-

	3
	Leaflets 
	5,000
	0
	            -

	4
	Training manual by WAAPP on maize, rice, cassava, poultry and aquaculture.
	5,000
	0
	In collaboration with WAAPP and NAERLS.


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	S/N
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1


	Agbeloba 
	
	  Yes
	Daily (Monday-Saturday)
	BSES 91.5 FM
	5.40 – 5.50am


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	S/N
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1


	Lahere 
	
	Yes
	Weekly (Monday)
	EKTV Ch. 41.
	5.30 – 6.00pm


Comment – Agbeloba and Lahere programme were used for various ADP programmes e.g.

Dissemination of various extension messages to farmers on improved production practices in crops, livestock, fisheries, Agro processing, Apiary, etc. 

E. TRAINING PROGRAMMES

	S/N
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1

2.


	OCP Training for Extension Agents and Farmers.

Monitoring for Cassava Viral Disease
	OCP Africa

Covenant University
	Extension Agents/ & Farmers

Extension Agents
	20

3
	OCP AFRICA/EKADEP

Covenant University


F. TECHNOLOGIES BEING PROMOTED IN 2025.

	S/N
	Title 
	Source 
	Level of adoption
	Remark 

	
	Yam multiplication techniques (yam minisett. Tech.)
	IITA & IAR&T
	68% adoption had been achieved
	

	2
	Popularization of New cocoa varieties (TCN 1-8)
	CRIN
	70%
	Farmers whose cocoa farms were affected by fire due to prolonged dry season were mobilized to replant while youths were encouraged to go into cocoa establishment.

	3
	Popularization of vitamin A cassava and high quality starch cassava e.g. TME 419.
	INCRI, IITA
	65%
	

	444
	Cassava utilization- production of cassava flour, high quality gari, odourless  fufu etc.
	IITA, IAR&T
	50%
	To key –in into the ATA programme of cassava flour for bread. 

	5
	Popularization and Utilization of Orange Flesh sweet potato(OFSP) into various recipes
	ARMTI
	55%
	To boost income generation of rural women, improve nutritional intake of farmers.


G: SPECIAL PROJECTS: No special project during been reported.   
H. GENERAL: BRIEF REMARKS ON:

	
	Input Situation
	

	1
	Fertilizer 
	  OCP Fertilizer company introduces OCP fertilizers to the farmers and was made available to farmer for purchase but the price was still on high side. 

	2
	Credit 
	Credit assistance to farmers was very low in the year because fund was not made available to the Ekiti State Micro-credit Agency responsible for granting credit facilities to farmers.

Farmers were linked to Agricultural Banks, though the responses was poor

	3
	Agro-chemicals
	These were available at the Government Agency (Fountain Agric. Marketing Agency –FAMA) and the open market but the price was on the high side all the year round due to high exchange rate. Also State Ministry for Agriculture and Food Security sells to farmers at subsidized prices.

	4
	Tractor/Mechanization
	The tractor hiring service was at the lowest ebb during the year. Mechanization / Tractorization units of State Ministry of Agriculture and Food Security help in land preparation at 50% subsidized price.

	5
	MTRM/QTRM Situation Report.
	List of constraints on attendance and delivery by Resource Person

Contributions from the Local Government Authorities. 

MTRM is rotated among the 16 Local Governments in the State. They usually provide venue and refreshment for farmers. 


CONSTRAINTS 

Shortage of Extension field Officers

Inadequate mobility for Headquarters staff visits and monitoring

Inadequate mobility for the Extension Agents (Motorcycles)

Inadequate funds for project execution.

Name of ADP: ENUGU STATE AGRICULTURAL DEVELOPMENT PROGRAMME (ADP)

Postal address: NO1 GARDEN AVENUE

Email:






Telephone___07038032000____________________

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	8
	

	2
	FNTs
	24
	24
	

	3
	OFARs
	-
	-
	

	4
	No. of Farm Families
	80,000
	80,000
	

	5
	No. of SPATs established 
	140
	78
	

	6
	No. of MTPs
	12
	6
	

	7
	No. of Field days
	6
	3
	

	8
	No. of Agric Shows
	6
	6
	

	9
	No. of group formed
	250
	200
	

	10
	No. of Pre-season training per year
	17
	17
	

	11
	No. of Post-season training per year
	17
	17
	

	12
	Extension publications produced (No. of Titles)
	-
	-
	

	
	Bulletins 
	280
	280
	

	
	Guides
	
	
	

	
	Leaflets
	
	
	

	
	Posters
	20
	20
	

	
	Others
	
	
	

	13
	Zonal Steering Committee Meeting
	4
	-
	

	14
	Zonal Technical Committee Meeting
	2
	-
	

	15
	Zonal REFILS workshops
	-
	-
	

	16
	No of Extension Workers (VEAs)
	360
	13
	

	17
	No of Extension workers (BESs)
	17
	-
	

	18
	EA/Farmer ratio in the state
	1:500
	1:5000
	


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins

1. 280

2.

3.

4.

5.


	280
	280
	ENADEP(ADP)


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4

5
	2025 per farming season

Dream FM ENADEP on GAP

Weather pedocetor


	
	
	2

1

1
	Family 99.9

Energy FM 105.5 FM

DEARM 92.5
	30mins

30mins


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1

2

3

4

5
	Tomatoes and okra farming in collaboration with Kinjeric Agro. 

Streptical for unlocky cassava yields

Rapid multiplication of improved cassava and yam set

National wide montoring for cassava disease
	ADP

ADP

ADP

ADP
	KINJERIC

SMS, ZEO and EAs

SMS,ZEO,EAs

FMARD
	250

100

50
	KINJERIC

NRCRI

NRCRI


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	GAP in crop production
	Research
	Adopted
	

	2
	GAMPS in livestock
	L-Press
	Adopted
	

	3
	
	
	
	

	4
	
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	40,000

	2
	Credit
	

	3
	Agro-chemical
	40,000

	4
	Tractor/Animal Traction
	1032

	5
	MTRM situation Report 
	Current


                                                CONSTRAINTS

Lack of fund to host programmes like radio and TV

Lack of release of state allocation.

Lack of mobilition for field staff.

Lack of Extension Agents 

[image: image146.jpg]


[image: image147.png]


         

Name of ADP: FCT Agricultural Development Project (FCT ADP)

Postal address: P.M.B 165, Gwagwalada, Abuja.

Email:
fctadp1990@yahoo.com



Telephone 08065977756

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	2
	Lack of fund

	2
	FNTs
	24
	9
	Inadequate funding

	3
	OFARs
	8
	
	Inadequate funding

	4
	No. of Farm Families
	170,000
	-
	Lack of fund

	5
	No. of SPATs established 
	
	
	Not applicable.

	6
	No. of MTPs
	24
	-
	Lack of fund

	7
	No. of Field days
	12
	-
	“

	8
	No. of Agric Shows
	6
	-
	Lack of fund

	9
	No. of Group formed
	200
	-
	

	10
	No. of Pre-season training per year
	2
	-
	Lack of fund

	11
	No. of Post-season training per year
	2
	-
	,,

	12
	Extension publications produced (No. of Titles)
	-
	-
	Lack of fund

	
	Bulletins 
	10,000
	No
	‘’

	
	Guides
	5,000
	No
	,,

	
	Leaflets
	5,000
	No
	,,

	
	Posters
	10,000
	No
	,,

	
	Others
	-
	-
	  

	13
	Zonal Steering Committee Meeting
	4
	
	,,

	14
	Zonal Technical Committee Meeting
	4
	
	Funds not available

	15
	Zonal REFILS workshops
	1
	
	No funds to attend

	16
	No of Extension Workers (VEAs)
	131
	 
	Inadequate staffing

	17
	No of Extension workers (BESs)
	26
	
	Some blocks are vacant

	18
	EA/Farmer ratio in the state
	1:800
	
	Need to recruit more EAs.


C: RA.DIO PROGRAMMES PRODUCED AND AIRED 
	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4

5
	       Nil

        “

         “

         “

         “
	   Nil

     “

      “

      “

      “
	    Nil

     “

      “

     “

     “
	    Nil

       “

      “

      “

     “
	      Nil

        “

        “

         “

         “
	  Nil

    “

     “

      “

       “


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1.

2.

3.

4.

5.

6.

7.

8.
	Good Agricultural practices (GAP) for crop farmers & livestock field officers.

Use of Organic Pesticides & Fertilizers for Dry Season Farmers.

Production of Insecticide & Organic Fertilizer.

Good Agronomic Practice of Maize and Rice.

Training for technology transfer in good and safe use of starter pack (value kit) good agronomy practices of farmer for increase in maize yield in the North central 

Training on harmful effect of burning and improper handling of Plastic Rubber on health of farmers & reduction of yelled of Agricultural Production. 

Fish Management: Healthy fish production for food security.

Training on Port Harvest handing of Maize & Rice.

Training on Smart Agriculture and Access to Farm input. 
	SAPZ

Contec Global

SWOFON

WOFAN

FMA&FS

CITAD & ACTION AID

FMA&FS

WOFAN

DEEN Initiative &  People power
	Crop & livestock field offices

Farmers

Farmers & EAs

Women Farmers & Youth

Farmers & EAs 

Women & Youth

Farmers

Women Farmers & Youth

Youth &Women
	26

20

80

200

30

100

30

300

60
	SAPZ/FCT ADP

ADP/SAPZ

SWOFON

FCT ADP & WOFAN

FMA&FS/ADP

FCT ADP CITAD ACTION AID

FMA&FS&ADP

FCT ADP & WOFAN

FCT ADP & DEEN Initiative & People Power


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption (Adopted/Not Adopted)
	Comment



	1
	Demonstration on the use of Organic Product. 
	Contec Global
	Adopted 
	On going

	2
	Preparation and Production of Organic Fertilizer.
	SWOFON
	Adopted
	On going




G: SPECIAL PROJECTS:
	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1.


	ACRESAL
	2023
	6 Years
	Restoration of degraded landscapes and soils with planting Agro-forestry seedlings and drought resilient crops established as a pilot scheme Project in some selected Area Councils of FCT.

	2.
	SAPZ
	2023
	5 Years
	To concentrate Agro processing activities within areas of high agricultural potentials to boost productivity and integrate production, processing, and marketing of selected commodities.


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	The FCT Administration procured and distributed 1,000 Metric Tons of Assorted Fertilizers to farmers at 50% subsidized rate. 

	2
	Credit
	Farmers were mobilized to form savings groups in order to access credit.

	3
	Agro-chemical
	The FCT Administration procured and distributed 20,000 litres of assorted Agrochemicals to farmers at 50% subsidized rate.

	4
	Tractor/Animal Traction
	Inadequate tractor hiring service for farmers.

	5
	Irrigated Farming 
	The Administration procured and distributed 10,000 pieces of water pumping machines to farmers to boost dry season farming.

	6
	Livestock Farming
	Livestock production is hampered by high cost of feed and veterinary drugs.


CONSTRAINTS

Insecurity such as kidnapping affected Agricultural Production and extension services in the Territory.
Farmers/herders clashes limited access to farmlands thereby affecting Agricultural production. 

Inadequate Extension agents is posing a serious challenge to effective agricultural extension service delivery to farmers.

Lack of fund/ late fund release affected most activities such as MTRMs, FNTs and MTPs in the year.

Inadequate mobility and logistics to carryout extension activities and effective monitoring & supervision of staff and projects.

Inadequate working tools and office facilities.

Fuel subsidy removal had its multiplier effect on the scope of coverage of activities

Inadequate training of Extension workers due to fund paucity.

Late release of farm inputs to farmers.

Name of ADP: GOMBE STATE ADP

Postal address: P.M.B 0046

Email:
gombeadp@yahoo.com


Telephone_______________________

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	NIL
	LACK OF FUNDS

	2
	FNTs
	24
	NIL
	LACK OF FUNDS

	3
	OFARs
	NIL
	NIL
	LACK OF FUNDS

	4
	No. of Farm Families
	1,000,000
	511,160
	

	5
	No. of SPATs established 
	160
	30
	LACK OF FUNDS

	6
	No. of MTPs
	24
	NIL
	LACK OF FUNDS

	7
	No. of Field days
	40
	2
	LACK OF FUNDS

	8
	No. of Agric Shows
	24
	NIL
	PAUCITY OF FUNDS

	9
	No. of group formed
	500
	200
	--

	10
	No. of Pre-season training per year
	3
	2
	-

	11
	No. of Post-season training per year
	4
	2
	-

	12
	Extension publications produced(No. of Titles)
	
	
	-

	
	Bulletins 
	200
	NIL
	-

	
	Guides
	150
	75
	-

	
	Leaflets
	1,000
	80
	-

	
	Posters
	NIL
	NIL
	-

	
	Others
	-
	-
	-

	13
	Zonal Steering Committee Meeting
	4
	NIL
	-

	14
	Zonal Technical Committee Meeting
	2
	NIL
	-

	15
	Zonal REFILS workshops
	4
	NIL
	

	16
	No of Extension Workers (VEAs)
	600
	50
	-

	17
	No of Extension workers (BESs)
	1,200
	50
	-

	18
	EA/Farmer ratio in the state
	1:300
	1:11,112
	-


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins

1. HOME GARDENING

2.COMPOST MAKING
	1,000

500


	250

100
	SAA, ANRiN

RICOWAS, SAA


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4
	NOMA DON RIBA

DON MANOMA

FILIN MAKIYAYA

SASAKAWA TAKE KIRA
	YES

YES

YES

YES
	YES

YES

YES

YES
	TWICE/WEEK

TWICE/WEEK

TWICE/WEEK

TWICE/WEEK
	AMANA FM

GMC FM

VISION FM

JEWEL FM/PROGRESS F
	15 MIN

30 MIN

15 MIN

15 MIN


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2
	NOMA DA KIWO

HIMMA MANOMA


	NO

NO
	YES

YES
	ONCE/WEEK

ONCE/WEEK
	NTA

NTA
	15 MIN

15 MIN


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1

2

3

4

5
	CLIMATE CHANGE

PRE-SEASON TRAINING

MID-SEASON TRAINING

POST HARVEST

SRI
	SAA

SAA

SAA

SAA

RICOWAS
	EAs & FARMERS

EAs

EAs

EAs

FARMERS
	30

40

40

21

35
	GSADP

GSADP

GSADP

GSADP

GSADP


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	SRI TECHNOLOGY
	RICOWAS
	ADOPTED
	SATISFIED

	2
	HOME GARDENING
	SAA
	ADOPTED
	SATISFIED

	3
	COMPOST MAKING
	SAA
	ADOPTED
	SATISFIED

	4
	MIXED CROPPING
	SAA
	ADOPTED
	SATISFIED


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	RICOWAS
	2024
	2
	SRI

	2
	JICA-SHEP APPROACH
	2022
	4
	MARKET SURVEY, RECORD KEEPING, NUTRITION

	3
	SAA
	2019
	26
	REGENERATIVE AGRICULTURE, MARKET ORIENTED AGRICULTURE & NUTRITION SENSITIVE AGRICULTURE

	4
	
	
	
	

	5
	
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	GOVERNMENT, OPEN MARKET

	2
	Credit
	BANKS

	3
	Agro-chemical
	OPEN MARKET

	4
	Tractor/Animal Traction
	PRIVATE OWNERS

	5
	MTRM situation Report 
	NIL-LACK OF FUNDS


CONSTRAINTS 

High cost of inputs

Poor prices of produce

Dilapidated existing infrastructure

Inadequate extension personnel

Lack of mobility for extension workers

Inadequate funding for extension activities

Insecurity

Name of ADP: IMO

[image: image148.jpg]T o
<



Postal address: P. Box 1977

Email:
oliviachinagorom2018@gmail.com
Telephone_______________________

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	-
	Lack of funds

	2
	FNTs
	24
	22
	92%

	3
	OFARs
	4
	0
	No fund

	4
	No. of Farm Families
	303,533
	303,303
	

	5
	No. of SPATs established 
	1000
	800
	67%

	6
	No. of MTPs
	1200
	1000
	83.3%

	7
	No. of Field days
	150
	110
	73&

	8
	No. of Agric Shows
	3
	-
	No fund

	9
	No. of group formed
	200
	150
	75%

	10
	No. of Pre-season training per year
	3
	-
	No Fund

	11
	No. of Post-season training per year
	3
	-
	No fund

	12
	Extension publications produced (No. of Titles)
	5000
	-
	No fund

	
	Bulletins 
	1000
	-
	No fund

	
	Guides
	1000
	-
	No fund

	
	Leaflets
	1000
	-
	No fund

	
	Posters
	1000
	-
	No fund

	
	Others
	1000
	-
	No fund

	13
	Zonal Steering Committee Meeting
	2
	-
	No fund

	14
	Zonal Technical Committee Meeting
	2
	-
	No fund

	15
	Zonal REFILS workshops
	1
	-
	No fund

	16
	No of Extension Workers (VEAs)
	306
	108
	32.1%

	17
	No of Extension workers (BESs)
	27
	27
	100%

	18
	EA/Farmer ratio in the state
	1.5000
	1:10,000
	200%


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins
	1000
	Nil
	-


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4
	Oil palm production

Fish production in 

Homestead farm 

Cassava production
	No

No

No
	No

No

No
	
	
	


 E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1
	Nigeria on climate smart Agriculture for Cassava Disease Management 
	FMAFS
	Youth & Women
	50
	FMAFs/ADP


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	Homestead Fish Farming 
	Imo ADP
	Adopted
	Effective

	2
	Dry Season Farming 
	Imo ADP
	Adopted
	Effective

	3
	Bee Keeping
	Imo ADP
	Adopted
	Effective

	4
	Cassava production using improved variety 
	Imo ADP
	Adopted
	Effect


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	Fingerling to fork Project
	2023
	6 months
	Fingerling & fish Processing

	2
	Fingerling to fork Project
	2024
	6 months
	Fingerling & fish Processing

	3
	Fingerling to fork Project
	2025
	6 months
	Fingerling & table fish

	4
	NG CARES
	
	4 years
	 Input distribution production/advisory services


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	High cost/low quality fertilizers

	2
	Credit
	High interest rate

	3
	Agro-chemical
	High cost of chemicals 

	4
	Tractor/Animal Traction
	Some terrain inaccessible 

	5
	MTRM situation Report 
	Lack of funds


CONSTRAINTS

 Lack of funds

Lack of mobility for effective supervision/visits

Reduced workforce due to retirement and death

High cost of agro inputs 
[image: image149.jpg]


[image: image150.jpg]


 

Name of ADP:  JIGAWA

Postal address:  JARDA PMU, Dutse, opposite SAHAD Store Kiyawa Road, Jigawa State

Email:
mhabib010@gmail.com
Telephone____07039772123___________________

A. 2024 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	7
	

	2
	FNTs
	24
	10
	

	3
	OFARs
	20
	11
	

	4
	No. of Farm Families
	900,000
	720,000
	

	5
	No. of SPATs established 
	0
	0
	

	6
	No. of MTPs
	0
	0
	

	7
	No. of Field days
	20
	9
	

	8
	No. of Agric Shows
	5
	2
	

	9
	No. of group formed
	800
	400
	

	10
	No. of Pre-season training per year
	2
	2
	

	11
	No. of Post-season training per year
	2
	2
	

	12
	Extension publications produced (No. of Titles)
	NIL
	NIL
	

	
	Bulletins 
	
	
	

	
	Guides
	
	
	

	
	Leaflets
	
	
	

	
	Posters
	
	
	

	
	Others
	
	
	

	13
	Zonal Steering Committee Meeting
	NIL
	NIL
	

	14
	Zonal Technical Committee Meeting
	NIL
	NIL
	

	15
	Zonal REFILS workshops
	1
	0
	

	16
	No of Extension Workers (VEAs)
	1667
	1667
	

	17
	No of Extension workers (BESs)
	60
	45
	

	18
	EA/Farmer ratio in the state
	1:500
	1:431
	


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4

5
	Jagoran manoma


	No
	Yes
	WEEKLY
	RADIO JIGAWA
	30 Minutes


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4

5
	Naduke


	NO
	YES
	WEEKLY
	NTA DUTSE
	30 Minutes


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	   1

   2

   3

   4

   5

  6

  7

  8

  9

10

  
	M&E Data verification work shop.

Training of enumerators on dry seasoned survey.

 Seasonal climate production (SCP)and annual flood outlook (AFO) 
 Training of youth on climate 

 smart Agriculture and sustainable land and water management.
TOT of extension workers from Jigawa and Yobe state on climate smart Agriculture.
Workshop on governance and conflict sensitivity in project implementation.
Farmers training on gender family goal setting, food stock, cash management and farm planning.

 TOT to EAS and farmers on sorghum production technologies.
TOT to EAS and farmers on rice 

production technologies.
Advance TOT on SRI in west Africa.
TOT on backyard garden for nutrition improvement.
MID SEASON TRAINING OF EAS
TRAINING OF EAS ON POST HERVEST, PROCESSING AND HANDLING TECHNIQS.

	SASAKAWA AFRICA. 

AGRA  

NIMET, GATE Foundation

Sahel consult Save the children project. 

CARE Project

Soil value project 

   SAAJSG   

SAA/JSG

   SAA/JSG 

RICOWAS PROJECT

SAVE THE CHILDREN

SAA/JSG

SAA/JSG

SAA/JSG
	Farmers & EAs

“

“

“


	42

18

49

 100

16

60

42

30

15

70

26

26


	SAA/JSG

FMAFS/

JARDA

Save the children project

CARE Project.

Soil value project

SAA and JSG partnership project.

SAA/JSG 

SAA/JSG 

RICOWAS

MASAKI MULTI SECTORAL

SAA

SAA/JSG




F. TECHNOLOGIES BEING PROMOTED IN 2024/2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	DIGITAL FARM INPUT DISTRIBUTION TECHNOLOGY
	JSG
	Adopted
	EAS, BES, ZEOS AND STORE KEEPERS


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	J-CARE
	2022
	3 YEARS
	- Input support

- Rehabilitation of feeder roads and Tube wells Drilling

	2
	SHEP-JICA Project
	2021
	5 YEARS
	-Empowerment of small holder Horticultural farmers

	3
	OCP
	2025
	1 YEAR
	SOIL ANALYSIS AND TARAINIG OF EAS

	4
	SASAKAWA
	1992
	TO DATE
	 Training and demonstration

	5
	MASAKI 2.0/774
	2025
	
	Save the children project.


GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	15,000 MT and sell to farmers.

	2
	Credit
	Thousand of farmers were benefited with farm inputs on credit and pay back during harvesting period (cash or kind) with the named CLUSTER program

	3
	Agro-chemical
	10,000 Litres of different types.

	4
	Tractor/Animal Traction
	About 300 units of tractors/farm implements distributed to different part of the state. 

	5
	MTRM situation Report 
	 NIL


CONSTRAINTS 

Inaduate funding

Inadquate training and capacity building

[image: image151.jpg]


[image: image50.jpg]


                                                                                              

Name of ADP: Kaduna State Agricultural Development Agency KADA

Postal address: No. 1 Aliyu Makama, by Gashash Road, Barnawa GRA, Kaduna

Email:
kadphq@yahoo.com
             Telephone: 08062513652, 08143436031.

A. 2021 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	12
	

	2
	FNTs
	0
	24
	

	3
	OFARs
	 120
	90
	

	4
	No. of Farm Families
	1,322,226
	1,322,226
	

	5
	No. of SPATs established 
	Nill
	22
	

	6
	No. of MTPs
	800
	1,175
	

	7
	No. of Field days
	24
	31
	

	8
	No. of Agric Shows
	1
	NIL
	

	9
	No. of group formed
	700
	93
	

	10
	No. of Pre-season training per year
	1
	3
	

	11
	No. of Post-season training per year
	1
	2
	

	12
	Extension publications produced (No. of Titles)
	
	
	

	
	Bulletins 
	300
	0
	

	
	Guides
	500
	0
	

	
	Leaflets
	400
	0
	

	
	Posters
	600
	0
	

	
	Others
	
	
	

	13
	Zonal Steering Committee Meeting
	4
	0
	

	14
	Zonal Technical Committee Meeting
	2
	0
	

	15
	Zonal REFILS workshops
	1
	1
	

	16
	No of Extension Workers (VEAs)
	1,024
	171
	

	17
	No of Extension workers (BESs)
	59
	23
	

	18
	EA/Farmer ratio in the state
	1-1500
	1: 7,700
	


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins

1. 

2.

3.

4.

5.


	10,000


	0
	

	2
	Guides


	5,000


	0


	

	3
	Leaflets

1. 

2.

3.

4.

5.
	5,000


	0
	


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2


	Kusaurara Manoma

Noma Baban


	Yes

Yes
	No

No
	
	
	


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1

2

3

4

5

6

7


	Technical session on climate change policy implementation for holistic climate action

Pre-season ToT for home garden

Climate smart Agriculture
Marketing systems Development

Enterprise development, Effective Communication value Addition and Innovative initiatives

Integrated pest Management and control

Establishment of good Home Garden

Improved Livestock Production

Improved tomatoes Production

	Partnership for Agile Governance for climate Engagement (PACE)

GAIN/DDI

GAIN/DDI

WOFAN

World trade Center

Gain

KADLPRES

FAO
	Deputy Director

EAs

EAs

HWIA

CP Officers

Extension /Lead Farmers

Liv EAs/Farmers

EAs/Farmers
	1

20

20

1

18

542

52


	MoA/KADA

MoA/KADA

MoA/KADA

Prospect Development Services

STDF/IPM Nigeria

DDI/GAIN/KADA

LPRES/KADA




F. TECHNOLOGIES BEING PROMOTED IN 2022

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	Strengthening Nutrition on Priority Staple Crops
	GAIN/ENDSAND 2.0
	Adopted
	Promote the production and consumption of VIT A Maize

	2
	Recipe Training on consumption of VIT A Maize
	HARVEST PLUS
	Adopted
	Technology adopted by Women Farmers


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	AGRA/EXAF Kaduna Consortium/NAERLS.
	2022
	3 Years
	Value addition on Maize, Rice, Soybean, Cowpea and Tomato.

	2
	GAIN SNIPS: Gain in partnership with the green innovation Centre for Agriculture and food Sectors (GIC) delivered in Nigeria by Deutsche Gesell/schaft for international zusammerbet (GIZ) gave birth to SNIPS aimed at strengthening priority value chains and improving the nutritional content of stable crops (Maize, Rice, Wheat, Cassava and Sweet potato.
	2021
	5 Years
	Promoting the production and consumption of vitamin A maize in four (4) LGAs (Lere, Kauru, Chikun & Giwa)

	3
	WOFAN

Women Farmers Advancement Network: is to empower Women in rural communities through the provision of embedded support services and improved access to markets for the women and youth.

Target: 65,000 farmers to be trained.
	2022
	5 Years
	- Capacity           building and      Training.

- Access to market and Finance.

- Advocacy and policy influence.

- Agriculture productivity enhancement.

	4
	NCARES. 2 Covid-19 action recovering and Economic stimulus aimed to restore the access to livelihood to support  the poor  and vulnerable, maintaining food security  and facilitating recovery of  MSEs
	2021
	Extended to 2027
	- Distribution of inputs and service provision

- Labor intensive public works (LIPW) opportunities to improve agricultural infrastructure

- Provision of agricultural Assets for mitigating food loss and waste.

	5
	SAPZ PROGRAMME
	2023
	4 years
	To increase household incomes, foster job creation in rural agricultural communities, especially for youth and women, and enhance food and nutritional security in Nigeria.

	6
	Deliver Nigeria 

is a transformative project designed to enhance the livelihoods of smallholders vegetable farmers in Kaduna and Kano State. This initiative will addresses key challenges such as low yield, limited market access, high postharvest losses, and inadequate finance. The Project is led by the Global Alliance for improved Nutrition (GAIN) in partnership with East-West seed knowledge transfer Foundation (EWS-KT) and Wageningen University and Research (WUR).
	July 2024 At preparatory stage
	3 Years
	 Key  Activities
Establishing 1200 Pilot Demo to show case Advance Agricultural Technics.

To Train 25,000 Farmer in GAP.

Enhancing Business and Market Planning Skills for 25,000 Trained Farmers.

Facilitating  Access Finance for 500 Farmers to boost commercial Production.

Training of 100 Sector Professionals and 40 Input Suppliers  provide technical and extension support to SHF.



	7
	- Capacity building for health care workers.

- Community based Nutrition intervention.

Policy Advocacy and State holder engagement.

-Monitoring and Evaluation.
	
	
	

	8
	Livestock Productivity & Resilience Support (L-PRES)
	2022 Preparatory stage


	5 years
	-Conflict Resolution

- Justice and Peace

- Humanitarian Relief & Early Recovery

- Human Capital Development

- Cross outing Issues

- Economic Investment


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Fifteen Thousand MT (15,000 MT) of fertilizer (NPK/UREA) was Procured to be Distributed to 150,000 Smallholders farmers free by the State Government as Support. Out of which 4,140 MT were distributed to 41,400 wet season smallholder Farmers.  While the remaining will be distributed to dry season farmers.

	2
	Credit
	Nil

	3
	Agro-chemical
	NILL

	4
	Tractor/Animal Traction
	NILL

	5
	MTRM Situation Report 
	11 TRM were carried out

	6
	Farm Implements
	NILL

	7
	Irrigated Farming
	NILL

	8
	Poultry
	NILL

	9
	Fisheries/Aquaculture
	NILL

	10
	Livestock Farming
	NILL

	11
	Others (Specify)
	


                                CONSTRAINTS 

Flooding

Hijack/duplication of activities by the state ministry.

High cost of input due inflation.

Lack of cash Backing of Approved Budget.

Staff Retirement without recruitment.

[image: image152.png]


[image: image51.jpg]


                                                                                                                       

Name of ADP: Kano State Agricultural and Rural Development Authority (KNARDA)  

Postal address: Km 9 Hadejia Road, P.M.B. 3130 Kano

Email:
Knarda2010@gmail.com




Telephone: - 08066020043
A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	2
	Nil
	

	2
	FNTs
	12
	Nil
	

	3
	OFARs
	6
	Nil
	

	4
	No. of Farm Families
	1,620,000
	1,620,000
	

	5
	No. of SPATs established 
	1,200
	Nil
	

	6
	No. of MTPs
	44
	Nil
	

	7
	No. of Field days
	48
	48
	

	8
	No. of Agric Shows
	2
	1
	

	9
	No. of group formed
	200
	125
	

	10
	No. of Pre-season training per year
	4
	4
	

	11
	No. of Post-season training per year
	4
	4
	

	12
	Extension publications produced (No. of Titles)
	
	
	

	
	Bulletins 
	500
	500
	

	
	Guides
	3,000
	2,000
	

	
	Leaflets
	1,200
	1,050
	

	
	Posters
	2,000
	2,000
	

	
	Others (News letters)
	2,000
	2,000
	

	13
	Zonal Steering Committee Meeting
	3
	Nil
	

	14
	Zonal Technical Committee Meeting
	3
	Nil
	

	15
	Zonal REFILS workshops
	3
	Nil
	Yet to be conducted as at the compiling the report

	16
	No of Extension Workers (VEAs)
	2,300
	2,001
	

	17
	No of Extension workers (BESs)
	176
	107
	

	18
	EA/Farmer ratio in the state
	1:800
	1:769
	


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins

1. KNARDA-KSADP Bulletin


	500
	500
	KSADP

	2
	Guides

1. Cowpea Production Techniques 

2. Soybeans Production Techniques

3. G/nut Production Techniques

4.
	1000

1000

1000
	660

660

680
	KSADP, ICRISAT and IITA

	3
	Leaflets

1. Cowpea Production Tips 

2. Soybeans Production Tips

3. G/nut Production Tips

4.
	1000

500

500
	1000

500

500
	KSADP, ICRISAT and IITA


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1


	Noma da Hukumar KNARDA


	
	Yes
	98.5 FM

&

89.3 FM
	Nasara Radio

&

Radio Kano
	30 minutes


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1
	Mu Koma Gona


	
	Yes
	
	ARTV Kano
	30 minutes


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1

2

3

4

5
	Pre- season training for Seed producers (CBSM) and EA’s

Pre- season training for lead farmers (DEMO)

Contract spraying training

Hematic storage using PICS bags

Pre-season training for Extension agents
	KNARDA-KSADP

KNARDA-KSADP

KNARDA-KSADP

KNARDA-KSADP

KNARDA-KSADP
	Farmers

EAs

Farmers

Farmers

Farmers

Extension agents
	836

25

1100

580

550

95
	KSADP

KSADP

KSADP

KSADP

KSADP


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	Parabolic Vegetable Dryer
	NISPRI
	Adopted
	

	2
	Aerated Onion Storage
	NISPRI
	Adopted
	

	3
	Hematic Storage using Metal Silo & Drums
	NISPRI
	Adopted
	

	4
	Hematic Storage using PICS bags
	NISPRI
	Adopted
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	KSADP
	2020/21
	5 Years
	Agro-pastoral development

	2
	GIZ
	2025
	5 Years
	Soil Health

	3
	THRIVES
	2025
	10 Years
	Vegetables

	4
	NSAND
	2025
	2 Years
	Nutritious Diet

	5
	SAPZ
	2024
	5 Years
	Agro-processing development.

	6
	HORTI-NIGERIA
	2025
	5 Years
	Vegetables

	7
	DELIVER NIGERIA
	2025
	5 Years
	Prod. & Consumption of Healthier Vegetables


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	7,236 of 50kg Bags were procured and distributed for both dry and wet seasons.

	2
	Credit
	KNARDA links farmers with credit sources.

	3
	Agro-chemical
	10,384 Litres were procured and distributed for both dry and wet seasons

	4
	Tractor/Animal Traction
	Tractor services are available in the state but mostly on private ownership.

	5
	MTRM situation Report 
	MTRM/QTRM not conducted.


CONSTRAINTS 

Inadequate funding from the state government

Inadequate mobility to extension agents.

Dry spell

Flood

Pest and diseases

Name of ADP: KATINA STATE (KTARDA)

Postal address: KM 4 KANO ROAD, KATSINA PMB2006

Email:
ktardakatsina@gmail.com

Telephone_______________________

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	-
	Lack of funding

	2
	FNTs
	12
	12
	

	3
	OFARs
	-
	-
	

	4
	No. of Farm Families
	100,000
	800,000
	

	p5
	No. of SPATs established 
	 3610
	2707 
	722 EAs have 5 no each not all established due to insecurity

	6
	No. of MTPs
	34
	28
	Due to insecurity not all BEAs are able to establish the MTRs

	7
	No. of Field days
	34
	28
	Due to insecurity not all are able to conduct

	8
	No. of Agric Shows
	2
	2
	State and National Agric. Shows

	9
	No. of group formed
	500
	271
	Issue of insecurity in some of local government only 271 group were formed within this year

	10
	No. of Pre-season training per year
	6
	3
	

	11
	No. of Post-season training per year
	6
	
	To be conducted in November/December

	12
	Extension publications produced (No. of Titles)
	
	-
	

	
	Bulletins 
	
	
	

	
	Guides
	
	
	

	
	Leaflets
	
	
	

	
	Posters
	
	
	

	
	Others (Radio and TV)
	Radio 48

TV     48 
	48

48
	Radio programme with (repeat).

Weekly TV Programme Sponsored by KTARDA

	13
	Zonal Steering Committee Meeting
	-
	-
	-

	14
	Zonal Technical Committee Meeting
	-
	-
	-

	15
	Zonal REFILS workshops
	-
	-
	-

	16
	No of Extension Workers (VEAs)
	722
	722
	Due to recruitment from state Government

	17
	No of Extension workers (BESs)
	34
	34
	One in each of the 34 L.G.As of the state

	18
	EA/Farmer ratio in the state
	1:800
	1:2000
	Expecting more EAs Employment from state Govt.


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4

5
	Kartau Sarkin Noma

Repeat


	
	Yes


	9.70


	Katsina State Radio


	30 Minutes



	
	
	
	
	
	
	


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1


	Naduke
	
	Yes
	Channel 22
	Kttv
	30 Minutes

Weely




E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1

2

3

4


	An Update Training Of Extension Staff On Good Agricultural Practices To Meet Emerging Challenges Revolving Around Climate Chage For The Production Of Eight Major Crops Value Chain (Rice, Millet,Surghum, Maize,Cowpea,Soya Bean, Seasame, Groundnute And Cotton)

Training Of Extension Staff On Integrated Pest Management For The Prevention And Control Of Emergency Pest And Disease Outbreak In Katsina State

Training Of Women On Backyard Farming Technique

Basic Conceling Need For Successful Livestock Produnction In Katsina State. 

Climate Smat Agriculture 


	Katsina State Agricultural And Rural Development Authority

(KTARDA)

KTARDA

KTARDA

KTARDA

KTARDA
	BEAs/ EAs

EAs

Farmers

BEAs

EAs

BEAs/LGAD


	34 

722

102

340

34

722

450
	Ministry Of Agriculture And Livestock Development (MOALD)

(MOALD)




F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	Technology On Climate Resillent Of Eight Major Crops Value Chain
	KTARDA
	Adopted
	Successfuly Conducted

	2
	Integrated Pest Management For The Prevention And Controlofemergency Pest Disease Outbreak
	KTARDA
	Adopted
	Successfully

Conducted

	3
	Backyard Farming Technology
	KTARDA
	Adopted
	Successfully

Conducted

	4
	Basic Councelling On Livestock Production
	KTARDA/DEPT OF LIVESTOCK DEVELOPMENT
	Adopted
	Successfully

Conducted

	5
	Climate Smat Agriculture4
	KTARDA
	Adopted
	Successfully

Conducted


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	FADAMA NG-CARES
	2022
	2 YEARS
	INCREASING CASH TRANSFERS AND LIVELIHOOD SUPPORT TO POOR AND VULNERABLE HOUSEHOLD.

INCREASING FOOD SECURITY AND SAFE FUNCTIONING OF FOOD SUPPLY CHAIN FOR POOR HOUSEHOLD.

PREVENTING COLLAPES AND FACILITATING RECOVERY OF HOUSEHOLD/MICRO ENTERPRICES AND STRENGTHENING INSTITUTIONAL SUPPORT FOR COORDINATION AND DELIVERY.

	2
	
	
	
	

	3
	
	
	
	

	4
	
	
	
	

	5
	
	
	
	

	6
	
	
	
	

	7
	
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input Situation

	1
	Fertilizer
	20,000 METRICTONES PROCURED AND SOLD TO FARMERS AT SUBSIDY BY KATSINA STATE GOVERNMENT

	2
	Credit
	FARMER ASSES CREDIT THROUGH SOME COMMODITY ASSOCIATIONS

	3
	Agro-Chemical
	KATSINA STATE EMPOWERED FARMERS WITH AGRO CHEMICALS

	4
	Tractor/Animal Traction
	400 TRACTORS, 2000 POWER TILER MACHINES, 10 CONBINE HARVESTERS, 1000 PLTANTERS PROCURED AND SOLD TO FARMERS FOR HEARING SCHAME INTRODUCE. BY KATSINA STATE GOVERNMENT

PROCURED OF 2000 SOLA PUMPING MACHINE WITH SUBSIDY TO FARMERS, BY KATSINA STATE GOVNT

	5
	MTRM Situation Report 
	REVIVAL OF THE PROGRAMME IN PROGRESS




Name of ADP: KEBBI 

Postal address: KM 11 Kalgo Junction Birnin Kebbi, Kebbi State.

Email:
sulemanhamisu1@gmail.com





Telephone_____08036750482__________________

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	6
	Training Conducted

	2
	FNTs
	26
	22
	Training Conducted

	3
	OFARs
	20
	14
	

	4
	No. of Farm Families
	950,000
	
	

	5
	No. of SPATs established 
	1,984
	1,488
	

	6
	No. of MTPs
	8
	8
	

	7
	No. of Field days
	10
	6
	

	8
	No. of Agric Shows
	5
	3
	

	9
	No. of group formed
	2500
	1850
	

	10
	No. of Pre-season training per year
	10
	6
	

	11
	No. of Post-season training per year
	10
	7
	

	12
	Extension publications produced (No. of Titles)
	Nil
	
	

	
	Bulletins 
	4000
	0
	

	
	Guides
	4500
	0
	

	
	Leaflets
	1000
	1000
	

	
	Posters
	3000
	0
	

	
	Others
	
	
	

	13
	Zonal Steering Committee Meeting
	2
	1
	

	14
	Zonal Technical Committee Meeting
	4
	1
	

	15
	Zonal REFILS workshops
	4
	0
	

	16
	No of Extension Workers (VEAs)
	248
	32
	

	17
	No of Extension workers (BESs)
	64
	
	

	18
	EA/Farmer ratio in the state
	1: 800
	1 : 7,040
	


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4

5
	Sallama Manoma

Don Manoma

Na Duke


	Yes  

Yes

yes


	Yes

Yes

yes
	Weekly 

Weekly

2 time a week


	KB Radio

KB Radio

KB Radio
	30 min

30 min

30 min


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4

5
	Mutum da Muhallin  sa 


	Yes
	yes
	Weekly 
	KB TV
	30 min 


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1

2

3

4

5
	Transforming Lives through Nutrition


	Helen Keller
	EA& Farmers
	12 months

Pre-season and in season 
	Helen Keller 


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	NONE
	
	
	

	2
	
	
	
	

	3
	
	
	
	

	4
	
	
	
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	ATASP 1
	2016
	7 YEARS
	Infrastructure Development  ,capacity building , Rice value chain . 

	2
	RAMP 
	2021
	6
	Agro –logistics hubs and Rehabilitations of Rural roads.

	3
	SAPZ
	2024
	5
	Yet to commence activities 

	4
	
	
	
	

	5
	
	
	
	

	6
	
	
	
	

	7
	
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	:

SN

Input situation

1

Fertilizer

State Government has procured Fertilizer and Distribute to Farmers free of Charge

2

Credit

No credit facility this year 

3

Agro-chemical

State Government has procured Agro Chemicals and Distribute to Farmers free of Charge

4

Tractor/Animal Traction

3 Tractor hiring services was provided at one per Senatorial zone .



	2
	Credit
	

	3
	Agro-chemical
	

	4
	Tractor/Animal Traction
	

	5
	MTRM situation Report 
	


Name of ADP: KOGI  

Postal address: PMB 1067

Email:
 kogiagridev2000@yahoo.com



Telephone: 08065705713

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	0
	No fund

	2
	FNTs
	24
	24
	Effort of EAs

	3
	OFARs
	12
	0
	No funds

	4
	No. of Farm Families
	560,000
	480,000
	Good

	5
	No. of SPATs established 
	24
	0
	No funds

	6
	No. of MTPs
	40
	0
	No funds

	7
	No. of Field days
	12
	0
	No funds

	8
	No. of Agric Shows
	6
	0
	No funds

	9
	No. of group formed
	60
	40
	Good

	10
	No. of Pre-season training per year
	1
	0
	No funds

	11
	No. of Post-season training per year
	1
	0
	No funds

	12
	Extension publications produced (No. of Titles)
	
	
	

	
	Bulletins 
	1,500
	0
	No funds

	
	Guides
	1,000
	0
	No funds

	
	Leaflets
	1,000
	0
	No funds

	
	Posters
	3,000
	0
	No funds

	
	Others
	
	
	

	13
	Zonal Steering Committee Meeting
	3
	0
	No funds

	14
	Zonal Technical Committee Meeting
	2
	0
	No funds

	15
	Zonal REFILS workshops
	1
	0
	No funds

	16
	No of Extension Workers (VEAs)
	180
	56
	Retirement of EAs

	17
	No of Extension workers (BESs)
	30
	6
	Retirement

	18
	EA/Farmer ratio in the state
	1:1000
	1:7000
	No funds


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins

1. Farmers information guide on modern farming technologies


	2000
	0
	No collaboration

	2
	Guides

1. Production of guides to farmers on improved crop, livestock and fish production
	2000
	0
	No collaboration

	3
	Leaflets

1. Production of leaflets on guide to farmers on improved crops, livestockandfish production
	2000
	0
	No collaboration


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4


	Management of NCD

NIMET prediction for 2025

Temperaturemanagement in Poultry

Land management & clearing
	No

No

No

No
	Yes

Yes

Yes

Yes
	Twice

Twice

Twice

Twice


	Radio Kogi/Fm94.5

Radio Kogi/Fm94.5

Radio Kogi/Fm94.5

Radio Kogi/Fm94.5
	30 minutes

30 minutes

30 minutes

30 minutes


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1
	Nil


	Nil
	Nil
	Nil
	Nil
	Nil


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1

2

3

4
	Extension Training

Building Agricultural system resilience in Nigeria

Maximizing Effective Climate Resilience Methodologies

Training on the use of Miracle 1 Organic Inputs

	ADP

FMOA&FS/ADP

ADP

ADP
	EAs, Farmers&Agro Input dealers

Farmers&Agro Input dealers & EAs

Livestock farmers & EAs

EAs, Farmers&Agro Input dealers


	130

150

500

120
	VCDP

SAHEL Consulting

L-PRES

AAC-MIRACLE 1


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	Crop resilience to climate change
	ACRESAL
	Adopted
	

	2
	Use of Organic Manurein Crop Production
	KOGI  ADP
	Not adopted
	No fund for demonstration

	3
	Use of ‘Dusa’ as a source of carbohydrate in poultry production
	KOGI ADP
	Not adopted
	Farmers are skeptical


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	L-PRES
	2023
	6 years
	Livestock Development

	2
	ACRESAL
	2023
	6 Years
	Reduction in land degradation

	3
	VCDP
	2020
	
	Cassava Value Chain Development


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Available for farmers through State Government

	2
	Credit
	Not available for farmers. farmers are discouraged

	3
	Agro-chemical
	Available for farmers through Kogi State Government

	4
	Tractor/Animal Traction
	Available for farmers through State Government

	5
	MTRM situation Report 
	Not held due to lack of funds


CONSTRAINTS

No funds to attend REFILS, ZSCM, ZTCM and to conduct MTRM

Inadequate number of Extension Agents workers

Mobility for Extension Agents is inadequate

No incentives for Agricultural Extension Agents to effectively carry out their activities

Name of ADP: Kwara State Agricultural Development Project 

Postal address:Ministry of Agric &Rural Development 

Email:kwadp2@gmail.com 

Telephone__07036013443_____________________

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	2
	Lack of fund

	2
	FNTs
	24
	8
	

	3
	OFARs
	0
	0
	

	4
	No. of Farm Families
	470,000
	470,00
	

	5
	No. of SPATs established 
	0
	0
	

	6
	No. of MTPs
	0
	0
	

	7
	No. of Field days
	0
	0
	

	8
	No. of Agric Shows
	0
	0
	

	9
	No. of group formed
	0
	0
	

	10
	No. of Pre-season training per year
	0
	0
	

	11
	No. of Post-season training per year
	0
	0
	

	12
	Extension publications produced (No. of Titles)
	5000
	0


	

	
	Bulletins 
	0
	0
	

	
	Guides
	0
	0
	

	
	Leaflets
	0
	0
	

	
	Posters
	0
	
	

	
	Others
	
	
	

	13
	Zonal Steering Committee Meeting
	0
	
	

	14
	Zonal Technical Committee Meeting
	1
	
	

	15
	Zonal REFILS workshops
	1
	
	

	16
	No of Extension Workers (VEAs)
	120
	120
	

	17
	No of Extension workers (BESs)
	38
	8
	

	18
	EA/Farmer ratio in the state
	2:800
	1:5000
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	

	2
	Credit
	

	3
	Agro-chemical
	NIL

	4
	Tractor/Animal Traction
	

	5
	MTRM situation Report 
	


Name of ADP: LAGOS

Postal address: Old Abeokuta Road, Oko-Oba, Agege

Email:

ronketojutubi@gmail.com




Telephone__08023201282_____________________

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	11
	11
	

	2
	FNTs
	26
	21
	Others fell on public holidays

	3
	OFARs
	7
	7
	Ongoing

	4
	No. of Farm Families
	650,000
	420,400
	

	5
	No. of SPATs established 
	50
	45
	The SPATs were in collaboration with the Farmers

	6
	No. of MTPs
	2
	2
	Ongoing

	7
	No. of Field days
	72
	56
	The Field days were in collaboration with farmers and  LGAs

	8
	No. of Agric Shows
	3
	2
	

	9
	No. of group formed
	500
	235
	

	10
	No. of Pre-season training per year
	1
	1
	

	11
	No. of Post-season training per year
	0
	0
	

	12
	Extension publications produced (No. of Titles)
	
	
	

	
	Bulletins 
	10
	6
	

	
	Guides
	10
	3
	

	
	Leaflets
	10
	4
	

	
	Posters
	3
	1
	

	
	Others
	
	
	

	13
	Zonal Steering Committee Meeting
	1
	1
	

	14
	Zonal Technical Committee Meeting
	2
	0
	

	15
	Zonal REFILS workshops
	1
	1
	

	16
	No of Extension Workers (VEAs)
	128
	49
	Redeployment and retirement of staff members.

	17
	No of Extension workers (BESs)
	16
	16
	

	18
	EA/Farmer ratio in the state
	1:1000
	6,468
	Inadequate number of extension staff


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins

1. Improved sack farming techniques for urban farmers

2. Integrated pest management for poultry farmers.

3.Safe use and handling of agrochemicals

4.Fish farming in ponds and tanks

5.Value addition and post-harvest handling of Cassava

6. Organic fertilizer production and use.


	5000

5000

5000

5000

5000

5000
	2000

2000

2000

2000

2000

2000
	

	2
	Guides

1. Guide on poultry production 

2.Guide on catfish production and management

3.Guide on climate smart agricultural practices in Lagos State

4.

5.
	2000

2000

2000
	500

500

500
	

	3
	Leaflets

Grow Cucumber in sacks

2.Cultivating Waterleaf and Ugwu for daily income

3.Raising broilers and layers in small spaces

4.Goat and Sheep management for beginners

5.
	2000

2000

2000

2000
	500

500

500

500
	


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4

5

6

7

8
	Sustainable snail farming business in dry season

Preparations for early season planting

Rabbit production

Tomato puree processing

Odourless fufu production

Orange Flesh Sweet Potato (OFSP),value addition and benefits

Broiler Chicken production

Drying methods in Agricultural processing

Management and prevention of diseases in fish production
	Yes

Yes

Yes

Yes

Yes

Yes

Yes
	Yes

Yes

Yes

Yes

Yes

Yes

Yes
	Weekly, Friday

;;

;;

;;

;;

;;

;;
	Radio Lagos Eko 107.5FM

;;

;;

;;

;;

;;

;;
	30 Mins.

;;

;;

;;

;;

;;

;;


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3
	NO PRODUCTION OR AIRING OF TELEVISION PROG. DUE TO FUND CONSTRAINTS
	
	
	
	
	


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1

2

3

4

5
	Training on Cassava Brown Streak Disease (CBSD)

Strengthening Farming 

Communities through Financial Management, Agricultural Insurance, group dynamics and sustainability strategies

Empowering Extension agents through modern extension methods, technology uptake and performance uptake.

Unlocking Agricultural Products Potentials for Export

Financial literacy and Agric business accounting
	WAVE

NPFS

NPFS

RID

RID
	Extension Agents

Farmers

Extension agents

Farmers

Farmers


	10

270

65

100

150


	LSADA, Covenant University

LSADA

LSADA

LSADA

LSADA


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	Popularization of backyard cultivation cultivation  of Murano F1 Cucumber variety in sacks
	IAR&T
	Adopted
	

	2
	Introduction of improved maize variety (PVA Synthetic 2 protein and vit. A fortified), for yield and growth performance in Lagos state
	IAR&T
	Adopted
	

	3
	Use of Cassava Peels leaf meal (CPLM) pelleted feed for growth performance in the diet goat.
	IAR&T
	Adopted
	

	4
	Introduction of WESAFU ecotype cichlids to earthen pond culture system of Lagos state.
	NIOMR
	Not Adopted
	

	5
	Replacement of Soya bean meal with moringa leaf on the performance of broiler chicken
	IAR&T
	Adopted
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	National Program for Food Security (NPFS)
	2007
	Till date
	Monitoring and Supervisory visits to all sites by management team.

Conduction of sensitization visits on loan repayment by the NPFS management.

	2
	APPEALS Project
	2017
	2023
	The Project has empowered 1,200 women and youths as well as vulnerable in the state.

It has also rehabilitated 155 rural roads in the state.

	3
	LCARES (FADAMA)
	2021
	Till date
	Empowering small holder farmers and households in Lagos state with inputs and production assets.

	4
	
	
	
	

	5
	
	
	
	

	6
	
	
	
	

	7
	
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Agro input service centers now abound in the state.

	2
	Credit
	Still low as credit organizations still charge high interest and demand collateral from farmers in the state

	3
	Agro-chemical
	As stated in fertilizer column but adulteration still persist

	4
	Tractor/Animal Traction
	The State e-tractor booking though still low.

Animal traction is not available in the state.

	5
	MTRM situation Report 
	MTRM was held (10) times in 2025 with technical messages delivered by competent resource persons from various research institutes. The review meetings were anchored by thestate”s team leader Dr Samuel Olanipekun from IAR&T, Ibadan. In addition, pre –MTRM which involves field visits to farms with either success stories or problems were usually embarked on in order to be abreast of the challenges faced by farmers on the farms and discussions on how to proffer solutions at the MTRM the following day. The attendance by both technical officers as well as resource persons was excellent.


                             CONSTRAINTS 

            i.  Inadequate number of Extension agents.     

            ii. Inadequate number of utility vehicles for field monitoring and supervision.

            iii. Inadequate and late release of fund.

            iv. Inadequate infrastructure and office facilities.

Name of ADP: NASARAWA ADP

Postal address: Agyaragu Tofa Road, PMB 36, Lafia

Email: nasarawaadp@gmail.com 


Telephone: 08036216599

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	-
	Lack of Fund

	2
	FNTs
	26
	23
	

	3
	OFARs
	10
	-
	Lack of fund

	4
	No. of Farm Families
	284,000
	252,606
	2019 village listening survey

	5
	No. of SPATs established 
	
	
	

	6
	No. of MTPs
	102
	22
	Lack of fund

	7
	No. of Field days
	4
	14
	Sassakawa (2mega & 12 mini)

	8
	No. of Agric Shows
	1
	1
	

	9
	No. of group formed
	15
	15
	

	10
	No. of Pre-season training per year
	1
	1
	Sassakawa

	11
	No. of Post-season training per year
	1
	-
	

	12
	Extension publications produced (No. of Titles)
	
	
	

	
	Bulletins 
	1000
	-
	

	
	Guides
	1000
	40
	GAIN

	
	Leaflets
	1000
	600
	Aflatoxin/Climate change

	
	Posters
	1000
	-
	

	
	Others
	
	
	

	13
	Zonal Steering Committee Meeting
	4
	-
	

	14
	Zonal Technical Committee Meeting
	2
	-
	

	15
	Zonal REFILS workshops
	1
	-
	No contact

	16
	No of Extension Workers (VEAs)
	376
	102
	Retirement & no employment

	17
	No of Extension workers (BESs)
	47
	24
	Retirement & no employment

	18
	EA/Farmer ratio in the state
	1:1000
	1: 14,210
	Inadequate no. of EAs


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins
	1000
	Nil 
	

	2
	Guides

1. Profitable production & Aflatoxin management for extension workers in Nigeria
	1000


	20


	WOFAN



	3
	Leaflets

1.
	1000
	Nil
	


C: RADIO PROGRAMMES PRODUCED AND AIRED

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4

5

6
	Wealth alternative

Mukoma Gona

Arziki na Gona

Noma Shinkafa Jari

Arziki Na Gona

Farmer’s World
	Yes

Yes

Yes

Yes

Yes

Yes
	Yes

Yes

Yes

Yes

Yes

Yes
	Once a week

Once a week

Once a week

Twice a week

Once a week

Once a week
	NBS 97.1FM

NBS 97.1FM

Precious FM 102.5

NBS 97.1FM

NBS 97.1FM

Precious FM 102.5
	30mins

30mins

30mins

1hour

30mins

30mins



D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1


	Noma Tushi Arziki
	Yes
	Yes
	Once a week
	NBS TV
	30mins


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	
	Training on GAP
	VCDP
	Rice and cassava farmers
	200
	IFAD/VCDP

	
	Training on environment and climate change adaptation
	VCDP
	Rice and cassava farmers
	16
	IFAD/VCDP

	
	Refresher training for entrepreneurs 
	VCDP
	Rice and cassava farmers
	10
	IFAD/VCDP

	
	Training on processing orange-flesh sweet potatoes (OFSP) into Garri 
	VCDP
	Women processors
	15
	IFAD/VCDP

	
	Training on sustainable practice emphasizing climate resilient technology
	VCDP
	Farmers
	143
	IFAD/VCDP

	
	Training on financial action learning system (FALS)
	VCDP
	Farmers
	98
	IFAD/VCDP

	
	Training on personal hygiene of processing plant workers, work place and water sanitation and hygiene (WASH)
	VCDP
	Processors
	155
	IFAD/VCDP

	
	Training of VC operators on branding and packaging
	VCDP
	Processors and Marketers
	100
	IFAD/VCDP

	
	Training of VC operators on food processing system including GMP, GHP & HACCP Principles
	VCDP
	Processors
	125
	IFAD/VCDP

	
	Training of trainers (TOT) on system of rice intensification (SRI) for extension institutions
	RICOWAS
	Extension workers
	14
	NADP

	
	Training of extension agents and farmers on cassava seed production and the six steps to cassava weed management tool kit (BASICS II)
	Sassakawa Africa
	EAs and Farmers
	42
	NADP

	
	Training of rice community based seed multiplication (CBSM) farmers’ group leaders
	Sassakawa Africa
	Farmers
	6
	NADP

	
	Training of family business garden members of College of Agric Science and Tech. Lafia (Capacity Building Activities)
	Sassakawa Africa
	Farmers
	30
	NADP

	
	Training of extension agents on development of technologies for long-term carbon sequestration (BIOCHER PRODUCTION)
	Sassakawa Africa
	Extension agents
	22
	NADP

	
	TOT pre-season training for SC, ZCS, SMS, EAs CBFs and CATs
	Sassakawa Africa
	Extension agents
	33
	NADP

	
	Communication training for extension agents
	Sassakawa Africa
	Extension agents
	29
	NADP

	
	Field data verification workshop for frontline extension agents
	Sassakawa Africa
	Extension agents
	32
	NADP

	
	BASICS II Project social media influencers actors’ workshop and skit making (Makurdi-Benue State)
	Sassakawa Africa
	Extension agents
	35
	NADP

	
	Practical demonstration on preparation of balanced diet using locally available food materials
	Sassakawa Africa
	Processors
	55
	NADP

	
	Training of youths and Agro-dealers on spray techniques, safe use and product knowledge
	Sassakawa Africa
	Farmers
	11
	NADP

	
	Training of farmers on gender family goal setting, food stock, cash mgt and farm planning
	Sassakawa Africa
	Farmers 
	17
	NADP

	
	Training of farmers group on nutrition, hygiene and family budgeting
	Sassakawa Africa
	Farmers group
	50
	NADP

	
	Training of farmers organizations on group formation, dynamics mgt and collective action
	Sassakawa Africa
	Farmers group
	26
	NADP

	
	Mid-season training for EAs, CBFs, CATs, ZCs and SC
	Sassakawa Africa
	Extension Agents
	31
	NADP

	
	TOT for EAs, CBFs, and CATs on postharvest handling, grain quality and storage mgt
	Sassakawa Africa
	Extension Agents
	33
	NADP

	
	Training community based seed multiplication farmers on seed enterprise 
	Sassakawa Africa
	Farmers 
	19
	NADP

	
	2 mega and 12 mini green farmers field days conducted in 14 communities
	Sassakawa Africa
	Farmers 
	755
	NADP


F. TECHNOLOGIES BEING PROMOTED IN 2024

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	Good Agricultural practice (GAP) for sustainable rice platform
	EU/GIAE/BMZ
	Adopted
	Completed

	2
	Farmers Business School (FBS) on rice
	EU/GIAE/BMZ
	Adopted
	Completed 

	3
	Good Animal Husbandry Practice (GAHP) in cattle production
	EU/GIAE/BMZ
	Adopted
	Completed

	4
	Improve rice parboiling technology and paddy quality grading
	JICA/FMAFS/ NADP
	Adopted
	Improve quality rice

	5
	Building resilience on climate change among smallholder farmers
	UNDP/GEF/ FMAFS/NADP
	Adopted
	Almost ended

	6
	Commodity value chain development programme
	IFAD/FMAFS/ NADP
	Adopted
	Processor and farmers testified the impact

	7
	Smallholder Horticulture Empowerment Promotion (SHEP)
	JICA/FMAFS/ NADP
	Adopted
	Completed

	8
	Formation of three zonal implementation teams (ZIT) made up of four (4)members each for three zones (Obi, Akwanga & Keffi)
	JICA/FMAFS/ SHEP
	Adopted
	To improve formation at three (3) zones

	9
	Training of zonal implementation team (ZIT) members on SHEP approach for three days
	JICA/FMAFS/ SHEP
	Adopted


	Waiting for further directives

	10
	Selection of farmers groups for implementing SHEP approach
	JICA/FMAFS/ SHEP
	Adopted
	To improve group formation

	11
	Training of farmers on organic fertilizer and compost production
	RICOWAS ARCN
	Adopted
	To improve soil condition and health

	12
	Determination of carbon emission through installation of greenhouse chambers
	IITA
	Not Adopted
	On-going

	13
	Soyabean/ maize inter, strip and diversified strip croppings
	SAA
	Being Adopted
	On-going

	14
	Improved method of rice parboiling using false bottom
	SAA
	Adopted 
	Widely in use

	15
	Hermetic grain storage (PICS bags)
	IITA
	Adopted
	Adopted

	16
	Drying of grains by solarization 
	SAA
	Not yet adopted
	Not yet adopted

	17
	Determination of moisture content of grains by salting
	SAA
	Being adopted
	On-going 


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	Integrated Approach to Climate Change (InACC)
	2021
	3years
	Good Agricultural practice, Farmers business school, Good animal husbandry practice, distribution of Agro-forestry trees, complicit resolution, feed formulation of livestock and compose making.

	2
	Fadama NG-Cares
	2021
	2years and renewed
	Promoting livelihood of poor vulnerable farmers.

Enhance agriculture sustainability in the food supply chain

Climate smart technology in growing climate problem.

Provide inputs such as fertilizer, herbicides and seeds (maize, sesame, rice and cassava stems) to poor and vulnerable farmers

Wet market, we provide sanitary facilities (toilets) and also provide water supply (boreholes)in rural markets

Provide productive and processing assets such as knapsack sprayers, maize sheller, rice shellers rice milling machines, power tillers cassava graters etc.

Provide rural roads in various communities in the state, linking communities to their farms and communities to markets for free flow of food supply and people.

	3
	Value Chain development programme (VCDP-AFI) FGN/LFAD Assisted.
	2020
	5years
	Profiling (registration of beneficiaries – rice/cassava producers, processors and marketers for VCDP support.

Support to value addition & market linkage 0-1 processors and marketers through MoU signing,

Support to climate resilient value chain infrastructure through construction of road, bridges, culvert, solar power borehole, market storages statles, processing center &processing agricultural equipment eg Tricycles, power tiller reapers, water pump/thrashers etc

Capacity building of beneficiaries (producers, processors & marketers)

Farm inputs support to farmers through matching grants for wet & dry season e.g fertilizer, seeds, agro-chemicals.

	4
	WOFAN-ICON 2
	2022
	5years
	Training and empowerment of youth and women.

Establishment of demonstration plots and processing center.

	5
	Sassakawa Africa
	2021
	5 years
	Soybean, maize regenerative agriculture, cassava, maize intercrop etc.

	6
	Smallholder Horticulture Empowerment Promotion (SHEP) (JICA/FMAFS/NADP)
	2017
	6years
	Market oriented agriculture, nutrition and hygiene, gender awareness, family budget etc.

	7
	Building Resilience to climate change among smallholder farmers (GEF/UNDP/NADP)
	2018
	5years
	Knowledge diffusion of climate smart agriculture, monitoring erosion control mechanism, establishing Agro-forestry system to increase vegetation cover.


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	VCDP/IFAD 384 bags (urea) 1, 408 NPK supported to 352 farmers.

ACReSAL support community interest group (CIGs) NPK 15:15:15 within the catchment area of Doma & Toto

Sassakawa – 8 bags of Golden fertilizer NPK, 10 bags of (10kg) USG, support to one cooperative group.

	2
	Credit
	VCDP/IFAD linked 15 farmers association to accessed credit worth of 20 million naira from LAPO Microfinance bank

ACReSAL support 20 communities interest groups (CIGs) through the disbursement of $250 USD per group. This loan facility is structure under the community revolving fund (CRF) model.

	3
	Agro-chemical seeds
	VCDP/IFAD; 2 Nos Herbicide (selective &non selective) support to 352 farmers each

VCDP/IFAD; Rice seed (FARO 44) 9, 600kg (9.6MT) support to 352 farmers

VCDP/IFAD; 8,000 bundles of cassava cutting support to 160 farmers

ACReSAL support (CIGs) with herbicide within the catchment area of Doma & Toto

ACReSAL also support with improved seed to (CIGs) within the catchment area of Doma and Toto LGAs.

	4
	Sprayer
	Sassakaa: 2 Nos sprayers support each to 5 farmers’ cooperative group.

ACReSAL support with sprayer, rain boot, hand gloves, Nose masks and overall jackets to (CIGs) within the catchment area of Doma and Toto LGAs

	5
	Tractor/Animal Traction
	ACReSAL: Support with 25 Nos tractors attached with plough, harrow, ridger and farm trailer to the 13 LGA of the state.

ACReSAL supports with: Power tillers, planters, rice reapers, solar powered irrigation pumps to (CIG) within the catchment areas of Doma and Toto LGAs

VCDP/IFAD: 9 Nos of tricycles with trailers support to 9 youth farmers (after payment of matching ground)

	6
	MTRM situation Report 
	No fund to conduct.


CONSTRAINTS 

Shortage of staff especially Extension Agents to meet up with the standard EA Ratio in the state.

No funding to finance the MTRMs, Pre and Post Season training.

No support for NG-Cares due to late release of fund.

Difficulty in loan recovery from farmers by ACReSAL

[image: image153.jpg]


[image: image154.jpg]



Name of ADP: Niger State Agricultural & Mechanization Development Authority (NAMDA)

Postal address: P.M.B 132, Maitumbi, Minna, Niger State

Email:
nigeradp.namda@yahoo.com

Telephone: 08188727911 (M.D/PM)

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	2
	Funded by IFAD/VCDP

	2
	FNTs
	24
	4
	,,

	3
	OFARs
	28
	Nil
	Lack of fund

	4
	No. of Farm Families
	open
	1,097,409
	

	5
	No. of SPATs established 
	Nil
	NA
	Not applicable

	6
	No. of MTPs
	15
	Nil
	Lack of fund

	7
	No. of Field days
	135
	12
	Funded by One Acre Fund 

	8
	No. of Agric Shows
	5
	Nil
	Funds not available

	9
	No. of group formed
	65
	58
	Satisfactory

	10
	No. of Pre-season training per year
	1
	0
	Funds not available

	11
	No. of Post-season training per year
	1
	Nil
	Not yet time

	12
	Extension publications produced(No. of Titles)
	4,000
	Nil
	Lack of funds

	
	Bulletins 
	1,000
	Nil
	‘’

	
	Guides
	1,000
	,,
	,,

	
	Leaflets
	1,000
	,,
	,,

	
	Posters
	1,000
	,,
	,,

	
	Others
	
	
	  

	13
	Zonal Steering Committee Meeting
	4
	,,
	,,

	14
	Zonal Technical Committee Meeting
	2
	,,
	Funds not available

	15
	Zonal REFILS workshops
	1
	‘’
	No  invitation from NARIS

	16
	No of Extension Workers (VEAs)
	210
	176
	EAs to be recruited by the Government 

	17
	No of Extension workers (BESs)
	46
	46  
	Satisfactory

	18
	EA/Farmer ratio in the state
	1:800
	1:3,000 
	More EAs needed to be recruited


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins

1. Sustainable Cowpea production and pest management.

2.  Seed selection, treatment and storage for quality harvest. 

3. 4. Soil erosion control

5.  Shea tree plantation and its economic value.
	1.000
	 Nil 
	NAMDA & NAERLS 

	2
	Guides

1. Good Agricultural practices for rice production. 

2. Cassava production and improved methods of processing. 

3. Yam processing and value addition.

4.  Improved maize production techniques for higher yield.

5. Best practices for vegetable farming.
	 1,000 
	 Nil 
	NAMDA & NAERLS 

	3
	Leaflets

.  Impact of Agricultural cooperatives on farmers’ output. 

2. Improved methods of fish preservations 

3. Principles and practices of grafting.

4. Efficient irrigation and water harvesting techniques 

5 Principle of yam minisett technology
	 1,000 
	 Nil 
	NAMDA & NAERLS 

	4.
	Posters

Adopt good agricultural Practices for higher yields.

Use certified seeds for improved productivity.

Control pests and diseases to protect your crops.

Reduce post-harvest losses through proper storage.

Adopt mechanized farming to increase efficiency.
	1,000
	Nil
	NAMDA & NAERLS


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4

5
	 Effect of climate change on Agriculture.

Common livestock diseases and their prevention

Groundnut production and value addition for rural farmers 

Record keeping and financial management for farmers.

Fish pond management and fingerlings production techniques.


	Yes

‘’

‘’

‘’

‘


	No

‘’

‘’

‘’

‘’
	Weekly

‘’

‘’

‘’

’’
	Crystal FM, Minna

‘’

‘’

‘’

‘’
	25 Minutes

‘’

‘’

‘’

‘’


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4

5
	Goat and sheep management for meat production

Effect of climate change on farming activities.

Post-harvest loss reduction through Hermetic storage technology.

Integrated pest management for sustainable crop protection.

Feeds formulation using locally available ingredients.


	Yes

‘’

‘’

‘’

‘’
	No

‘’

‘’

‘’

‘’
	Weekly

‘’

          ‘’

          ‘’

‘’
	NTA, Minna

‘’

             ‘’

           ‘’

            ‘’
	25 Minutes

         ‘’

           ‘’

           ‘’

            ‘’


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1

2

3

4

5

6
	Youth and women empowerment on cowpea production in Niger State.
 
Bringing all women cooperative groups together.
Agricultural sector coordination meeting
 
Youth empowerment on improved methods of rice processing.
 
 International budget partnership in collaboration with smallholder women farmers’ organization of Nigeria (SWOFON)  

Annual policy dialogue on soil degradation, fertilizer use, climate smart practices & agricultural sustainability.


	FMA&FS
IFAD/VCDP
AGRA
 
 
 

IFAD/VCDP

 
 
 SWOFON

Proxylogics


	EAs
 
EAs & CBS
 
 
EAs & CBS
 
 EAs
 
 BES (WIA)
EAs


	15

60

25

150

30

35
	FMA&FS & NAMDA
 
 
IFAD/VCDP&NAMDA
 
 
AGRA & NAMDA
 

IFAD/VCDP & NAMDA
 
 

SWOFON & NAMDA

 
Proxylogics & NAM


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	Improved rice production technology (planting at 20 cm x 20 cm).
	AGRA
	Adopted
	Adoption in progress

	2
	Burying  of fertilizer using spot application.
	AGRA
	‘’
	‘’

	3
	Improved rice processing technology using false bottom.
	NAMDA
	‘’


	‘’

	4
	Enhanced use of organic fertilizer
	NAMDA
	‘’


	‘’



	5
	Hermetic storage technologies (e.g., PICS bags)
	Lela Agro Industry, Kano
	‘’


	‘’




G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	Agricultural Inputs Based Support by Niger Foods Security Systems and Logistics Limited
	2023
	4 years
	Loan support on inputs/ power tillers to small-scale farmers

	2
	One Million  Banana Suckers Project  
	2024
	3 Years
	Supplying of Banana Suckers to One Million House hold

	3
	ACRESAL
	2023
	6 Years
	Restoration of degraded landscapes and soils across the state

	4
	 Farm On Wheels 
	 2015 
	 on-going 
	 Supply of inputs on loan to rice and soybeans farmers.

	6
	Commercialization of  Bio-fortified crops  
	 2022 
	 4 years

 (on- going)
	 Promoting Cassava,  Maize and orange flesh Potato vitamin A 


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	The State Government procured and distributed 1,542.5 metric tons of fertilizer to Farmers at subsidized rate and also provided enabling environment for Agro-dealers to sell inputs at affordable prices to farmers.

The state Government also monitored the sale of fertilizer and chemicals to checkmate malpractices

	2
	Credit
	Farmers were linked with banks to access loan.

	3
	Agro-chemical
	The Ministry of Agriculture and Rural Development constituted a task force to monitor the sales of adulterated chemicals.

	4
	Tractor
	Tractor hiring scheme at subsidized rate was introduced by the state Government through the Niger Foods Security Systems and Logistics Limited.

	5
	MTRM situation Report 
	Only two (2) MTRM was conducted due to paucity of funds


CONSTRAINTS 

Inadequate Extension agents is affecting agricultural extension service delivery to farmers.

Targeted activities such as MTRM, FNTs, MTPs, OFARs, Supervision etc were hampered due to lack of funds.

Inadequate vehicles and logistics to carryout effective monitoring and supervision of staff and projects.

Inadequate working tools and office facilities.

Inadequate training

 incessant cases of banditry and kidnapping which is affecting general agricultural production and effective extension service delivery in the state.

[image: image52.jpg]


                                                                                                                                    [image: image53.png]



Name of ADP: OGUN STATE 
Postal address: OLABISI ONABANJO WAY, IDI-ABA, P.M.B 2122 ABEOKUTA

Email:
ogunadp@gmail.com

Telephone: - 08139714266

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	10
	2
	

	2
	FNTs
	24
	20
	

	3
	OFARs
	2
	2
	

	4
	No. of Farm Families
	360,000
	53,680
	

	5
	No. of SPATs established 
	
	
	

	6
	No. of MTPs
	488
	374
	

	7
	No. of Field days
	20
	18
	

	8
	No. of Agric Shows
	2
	2
	

	9
	No. of group formed
	207
	426
	

	10
	No. of Pre-season training per year
	1
	1
	VCDP Support

	11
	No. of Post-season training per year
	2
	1
	Support from VCDP

	12
	Extension publications produced (No. of Titles)
	
	
	

	
	Bulletins 
	2,500 copies
	NIL
	

	
	Guides
	
	
	

	
	Leaflets
	
	
	

	
	Posters
	
	
	

	
	Others
	
	
	

	13
	Zonal Steering Committee Meeting
	4
	
	

	14
	Zonal Technical Committee Meeting
	2
	1
	

	15
	Zonal REFILS workshops
	1
	1
	

	16
	No of Extension Workers (VEAs/BEAs)
	146
	69
	

	17
	No of Extension workers (BESs)
	20
	13
	

	18
	EA/Farmer ratio in the state
	1:5,217
	1:1000
	


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins

1. 

2.

3.

4.

5.


	2,500
	Nil
	


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1
	Banned Chemicals
	NO
	YES
	Weekly
	OGBC 2
	15min

	2
	Land Clearing
	NO
	YES
	
	
	

	3
	Basin preparation and stocking 1
	NO
	YES
	
	
	

	4
	Basin preparation and stocking 2
	NO
	YES
	
	
	

	5
	Yam Planting
	NO
	YES
	
	
	

	6
	Heat Stress in Livestock 1
	NO
	YES
	
	
	

	7
	Heat Stress in Livestock  2
	NO
	YES
	
	
	

	8
	Planting of Vegetables 1
	NO
	YES
	
	
	

	9
	Planting of Vegetables  2
	NO
	YES
	
	
	

	10
	Planting of Vegetables  3
	NO
	YES
	
	
	

	11
	Newcastle Diseeas in poultry
	NO
	YES
	
	
	

	12
	NIMET Prediction 1
	NO
	YES
	
	
	

	13
	NIMET Prediction 2
	NO
	YES
	
	
	

	14
	L and  Prepartion and Cassava varieties 1
	NO
	YES
	
	
	

	15
	Land Preparation and Cassava Varieties 2
	NO
	YES
	
	
	

	16
	Flood Control in fish Farming
	NO
	YES
	
	
	

	17
	Activities of produce services 1
	NO
	YES
	
	
	

	18
	Activities of produce services 2
	NO
	YES
	
	
	

	19
	Activities of produce services 3
	NO
	YES
	
	
	

	20
	Activities of produce services 4
	NO
	YES
	
	
	

	21
	Activities of produce services 5
	NO
	YES
	
	
	


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees expected
	No of Trainees
	Collaborators 

	1
	Pre- season training
	Ogun ADP
	Extension Officers
	120
	VCDP

	2
	Monthly Training
	Ogun ADP
	Extension Officers
	120
	

	3
	Training of Vulnerable Smallholder Farmers (Poultry)
	MOA
	Farmers
	350
	FMAFS  

	4
	Training on SHEP approach
	ADP
	Farmers
	400
	VCDP

	5
	Capacity building on Global Export Standard for Farmers and processors
	Ogun ADP
	Farmers and processors
	30
	FMOA&FS

	6
	Training of State NDE beneficiaries on GAP
	Ogun ADP
	
	40
	National Directorate of Employment

	7
	Training of 120 Extension officers on new farming technologies( precision farming, backyard farming etc)
	Ogun ADP
	Extension Officers
	120
	


TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	Modern fish smoking Tech
	NIOMR
	Adopted
	50%

	2
	Use of good quality seed in planting
	ADP, NSS
	Adopted
	70%

	3
	Sourcing seed in reputable companies
	ADP, NSS
	Adopted
	70%

	4
	Seed treatment before planting
	NSS
	Adopted
	60%

	5
	Germination test before planting
	ADP
	Adopted
	

	6
	Seed Yam production through miniset techniques
	IITA
	Adopted
	40%

	7
	Storage grains with pics bags/ hermetic drums
	NISPRI/IITA
	Adopted
	30%

	8
	Effective Cassava weed Management
	IITA
	Adopted
	65%

	9
	Method of fertilizer application to maize
	
	Adopted
	70%

	10
	Maize/Potato intercrop
	Ogun ADP
	Adopted
	45%

	11
	PPR vaccination for sheep & goat
	VOM
	Adopted
	80%

	12
	Biosecurity in Livestock production
	OGADEP
	Adopted
	80%

	13
	Housing in sheep & goats/ Raised platform
	IAR&T
	Adopted
	80%

	14
	Climate smart livestock production practices
	OGADEP/FUNAAB
	Adopted
	60%

	15
	Cassava peel utilization and processing
	IAR&T
	Adopted
	45%

	16
	Backyard planting using Bags,Plastics etc
	OGADEP
	Adopted
	Awareness is increasing

	17
	Low cost formulation of rations
	Livestock research institute
	Adopted
	70%

	18
	Upgrading of local sheep& goat
	Livestock research institute
	Gradual
	35%


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	Value Chain Development Programme) VCDP
	2015
	Will end tentatively by 2026
	Ongoing with Cassava and Rice Value Chain and Nutrition

	2
	NIGERIA COVID-19 ACTION RECOVERY AND 

ECONOMIC STIMULUS PROGRAM- NIGERIA CARES

(OG-CARES)
	2021
	On going
	Efforts to mitigate the impacts of COVID19 pandemic on the livelihoods of poor and vulnerable households and micro enterprises in the country

	3
	Smallholders Horticultural Empowerment Promotion (SHEP)
	2022
	
	Promotion of Market Oriented Agricultural Extension System for Livelihood Improvement in Nigeria

	4
	ZERO HUNGER
	2021
	
	Good Agricultural practices in crop production and processing

	5
	Ogun State Economic Transformation Project
	2021
	5 years
	Improving business enabling environment, strengthening agri-food value chain and upgrading skills.

	6
	Special Agro-Indrustrial Processing Zone( SAPZ)
	2024
	
	Increase Agrcultural Productivity, promote agribusiness, and improve food security

	7
	Ogun State Farmers Information Management System(OGFIMS)
	
	Own by the State MOA&FS
	Digital platform designed to register, profile, and manage farmer data across all local government areas. Goal is to reach smallholder farmers with localized content on climate-smart agriculture, home garden promotion, input access, pest management, market information, and financial literacy.


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	1.Available at the Accredited input dealers outlets across the state.

	2
	Credit
	Available for farmers at the financial institutions

	3
	Agro-chemical
	Available at the Accredited input dealers outlets across the state and also at the Government centres. 

	4
	Tractors
	Just a few available for farmers at the State and Government centers. The state Government recently procured 40 new tractors to boost farming activities. We also have private commercial owners of tractors available for farmers to leverage on. Although, the cost is on the high side.

	5
	MTRM situation Report 
	Two(2) MTRM held in the year 2025 due to paucity of funds


CONSTRAINTS  

Dilapidated office buildings across the zones

 Poor mobility status across the zones

Vacancies in some designated circles

Paucity of funds to continue with the Television Agricultural Programme (Agbelere) as well as other activities at the ADP.

None payment of LT&T is affecting effective extension service delivery.

Unavailability of farm labour for smallholder farmers that makes up about 90% farming population.

Under staffed front-line extension agents (aftermath of statutory retirement and disengagements)

High cost of Farm inputs and machinery for farm mechanization.

Climate change (Unpredictable weather situation currently being experienced due to climate change).

Very high cost of fuel for day-to-day activities.

[image: image155.jpg]



                                                                                                        [image: image54.png]


                                                               

Name of ADP: Ondo State Agricultural Development Project.

Postal address: 88, Obafemi Awolowo Avenue, Alagbaka, Akure.

Email:
ondostateadp@yahoo.com.      Telephone: 08032499486.

A. 2024 EXTENSION SUPPORT INDICATORS 

	S/N
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	        2
	Lack of fund. The MTRM held so far was achieved with one of them being sponsored by FAO GEF7 FOLUR-IP. While the second was sponsored by ADP management

	2
	FNTs
	      24
	       20
	Good achievement

	3
	OFARs
	       42
	         -
	Lack of fund

	4
	No. of Farm Families
	180,000
	120,000
	

	5
	No. of SPATs established 
	300
	240
	

	6
	No. of MTPs
	6
	4
	i)Plantain production

ii)Cassava Varieties Demo 

iii)Maize Demo and iv)Cowpea Demo

	7
	No. of Field days
	10
	1
	Fall Armyworm field day conducted for Maize farmers with the distribution of improved varieties of maize and insecticides to the participating farmers.

	8
	No. of Agric Shows
	2
	1
	Agric show during the celebration of World Food Day. Organized by  State Min .of Agric.

	9
	No. of group formed
	450
	349
	Inadequate fund and poor mobility

	10
	No. of Pre-season training per year
	2
	1
	Lack of fund. The only one achieved was sponsored by FAO GEF7 FOLUR-IP

	11
	No. of Post-season training per year
	1
	0
	Lack of fund

	12
	Extension publications produced (No. of Titles)
	
	
	

	
	Bulletins 
	5,000
	0
	Lack of fund

	
	Guides
	5,000
	0
	Lack of fund

	
	Leaflets
	10,000
	10,000
	With the support of FAO GEF7 FOLUR-IP

	
	Posters
	1,800
	0
	Lack of fund

	
	Others: Diaries for EAs & BESs 
	500
	300
	Good

	13
	Zonal Steering Committee Meeting
	4
	0
	

	14
	Zonal Technical Committee Meeting
	1
	0
	

	15
	Zonal REFILS workshops
	1
	1
	Attended at IAR&T, Ibadan

	16
	No of Extension Workers (VEAs)
	144
	29
	115 Needed

	17
	No of Extension workers (BESs)
	18
	16
	

	18
	EA/Farmer ratio in the state
	1:1,000
	        1:6,206
	Very low number of  EA to Farmers.


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins

1. 

2. 

3. 

4.

5.


	2000
	Nil
	

	2
	Guides

1. 

2.

3.

4.

5.
	2000
	Nil
	

	3
	Leaflets

1. 

2.

3.

4.

5.
	10,000

  8,000
	10,000

 Nil
	FAO GEF7 FOLUR-IP.




C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2


	Kaje Kayo Radio Programme

Jingle Production


	None

None
	None

None
	None

None
	None

None
	None

None


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3
	Obalagbe Technology Transfer

Documentary on ADP Activities

Jingle production English & Yoruba


	None

None

None
	None

None

None
	None

None

None
	None

None

None
	None

None

None


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1

2

3

4

5
	Training & Empowerment of Youths and Women on Climate Resilient Practices in Rice Production, Processing and Marketing.

Pre-Season Training

FFBS & WOMEN Group Training

Identification of Cassava Mosaic (CMD) and Cassava Brown Streak (CBSD)

Training of Farmers on Climate Smart Agriculture(CSA) on Cocoa &Oil Palm/Mapping
	FMARD

FAO GEF7 FOLUR-IP

‘’

WAVE

FAO GEF7 FOLUR-IP
	EAs,/Farmers 

EAs & BEAs

EAs & BEAs

EAs & BEAs

Farmers
	60

68

10

5

11,023
	ADP

ADP

ADP

ADP

ADP


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	Yam Mini Sett Techniques
	Ondo ADP
	80% Adopted
	Boost Income and livelihood

	2
	Popularization of Onion Production
	Ondo ADP
	55% Adopted
	Need  more training and awareness

	3
	Popularization of Tomatoes
	Ondo ADP
	65% Adopted
	Need more training


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	FAO GEF7 FOLUR-IP
	March 2024
	5 years
	Development of Integrated land scape management, Training of Farmers on Climate Smart Agriculture(CSA) on Sustainable Cocoa and Oil Palm Value Chain ,Restoration of Degraded Forest Eco-System and Polygon Mapping on EURD Compliance.



	2
	L-Press
	Preparatory was year 2020,

Officially was year 2022
	6 years
	 Training of Farmers on Poultry ,Pigs ,Goat & Sheep through Farmer Field School (FFS). This Value Chain also includes :Producers ,Marketers & Processors. We also offer capacity Building in the Three Value Chains, We assist Farmers in the Three Senatorial  District in the Construction of Veterinary Clinics for the treatment of farm animals. We also help the farmers in the construction of Livestock market in the state.



	3
	IFAD LIFE-ND
	Phase 1 From:2020

Phase 2 From:2025
	5years

3 years
	Livelihood Improvement Family Enterprise Project in the Niger Delta (LIFE-ND) is being implemented in the nine (9) Niger-Delta States. The project enhances income, food security and job creation for rural youths and women through agribusiness development on a sustainable basis. The first set of beneficiaries; known as Incubatee (coordinated by an incubator) have been selected & trained on their chosen enterprises and empowered by the project. No of beneficiaries engaged is 4,563 and the number empowered is

4,283



	4
	WAVE
	2024
	On-going
	To detect Cassava Mosaic Disease (CMD) and Cassava Brown Streak Disease (CBSD).

	5
	SPAC/ACTION AID NIG
	2023
	 3 years 
	The mandate of the programme is to improve food and nutrition security and enhance agroecological skills of 120,000 smallholder women farmers and young people by facilitating access to early maturing seeds, seedlings, livestock and poultry, thus supporting agroecological practices, indigenous seeds and agrobiodiversity preservation for increased farm yields.

	6
	FADAMA CARES(N-CARES)
	2021
	On-going
	 The programme addresses food security and challenges in food supply chains in Nigeria and also mitigates the effect of COVID-19 in Nigeria in order to protect livelihood & food security of poor & vulnerable families. Activities include provision of inputs for crop & livestock farmers, construction of feeder roads, aggregation centres & processing centres for value addition e.t.c. 

The programme is gradually coming to a close.



	7
	TRACE (Traceability and Resilience in Agriculture and Cocoa Ecosystem)
	2022
	5 Years
	 To build the capacity of farmers through trainings. Linkage of Farmers with exporters. Empowerment of farmers with cocoa seedlings. Training of extension agent on the usage of “Corus 3D App”.




H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Ondo State Government/Federal Government distributed few tones of fertilizer in year 2024. But for this year nothing of such have been recorded, we are still expecting.

	2
	Credit
	Ondo State Government provide credit facilities to farmers

	3
	Agro-chemical
	The Agro-chemical procured were sold to farmers at subsidized rate

	4
	Tractor
	There are few numbers of tractors in the state. Not enough to go round the farmers.



	5
	MTRM situation Report 
	The meeting was held twice due to paucity of fund.


CONSTRAINTS 

 1.Shortage of EAs and none provision of extension materials for field activities.
       2.Poor funding of ADP and Extension services

 3.Most project proposals were not approved in this year 2025.

             4.Poor access roads.

             5. Lack of mobility for extension workers

             6.Insecurity (Kidnapping, farmer header clashes in some communities)

             7.Pest and diseases infestation 

             8. High cost of farm inputs like: fertilizers, agrochemical, improved seed etc.

Name of ADP: OSUN STATE ADP 

Postal address: P O BOX 724, IWO.

Email:






Telephone___08033798881____________________

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	1
	

	2
	FNTs
	        26
	24
	Public holidays

	3
	OFARs
	          8
	1
	Nihort okra market segmentation.

	4
	No. of Farm Families
	       256
	180
	

	5
	No. of SPATs established 
	      700
	20
	

	6
	No. of MTPs
	80
	NIL
	

	7
	No. of Field days
	        30
	1
	

	8
	No. of Agric Shows
	          5
	2
	

	9
	No. of group formed
	        140
	110
	

	10
	No. of Pre-season training per year
	            1
	0
	

	11
	No. of Post-season training per year
	            1
	0
	

	12
	Extension publications produced(No. of Titles)
	
	
	

	
	Bulletins 
	        20000
	8000
	

	
	Guides
	15000
	2000
	

	
	Leaflets
	        5000
	2500
	

	
	Posters
	        6000
	2000
	

	
	Others
	
	
	

	13
	Zonal Steering Committee Meeting
	               1
	1
	

	14
	Zonal Technical Committee Meeting
	               1
	1
	

	15
	Zonal REFILS workshops
	               1
	1
	

	16
	No of Extension Workers (VEAs)
	            240
	18
	

	17
	No of Extension workers (BESs)
	             30
	18
	

	18
	EA/Farmer ratio in the state
	    1:1000
	1:13000
	


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins

1. Farming operations calendar 
	5000
	1000
	ADP 

	2
	Guides

1. GAP in cocoa production 

2.Practical Guide on Cassava Brown Streak Disease (CBSD)
	4000

5000
	2000

3000
	TRACE/ADP

WAVE/ADP

	3
	Leaflets
	5000
	0
	ADP


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1.
	AGBELOBA
	No
	No
	Weekly 
	OSBC 104.5
	30Mins


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1
	EREAGBE
	No
	No
	Weekly 
	OSBC TV.
	30Mins 


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1.

2.

3.

4.

5.

6.

7.

8.

9.

10.


	Dry season farming baseline and feasibility survey stakeholder meeting for South west zone 

The National Agricultural Research Extension Summit 

Nigeria 1st SHEP Committee meeting .

Galileo -Midgal/AIR&T Farm hive Digital 

Train the Trainer Workshop on Cassava Viral Disease Surveillance 

Smart soil Project Evaluation and Close out.

LOC meeting

Flag Off and Distribution of imput to Smallholder Cassava Farmers in Ayedire Local Government of Osun State.

Sensitisation of Safe Agrochemical Use Among Farmers in Iwo, Osogbo,Ilesa and Ile Ife.

Training on Digital Adaptive Agriculture for Cocoa (Trace Project)


	Optimum seeds/NADF/NAERLS 24-28 Feb.2025.

FMAFS 

FMAFS 16th April,2025

AIR&T Moor Plantation, Ibadan 

May,2025

WAVE by Covenant University,Ota.

18th to 20th June 2025.

FUNNAB, Held at Envoy Hotel, Abuja 

11th to 10th July 2025.

AIR&T Ibadan.

CATO FOODS GLOBAL CONCEPT and BRITISH AMERICAN TOBACCO NIGERIA FOUNDATION.

Held on Thursday 28th August,2025

At Olupo Palace, Oluponna.

JUBAILI AGROTECH 

23rd September, 13th,14th &15th October,2025 Respectively.

Lutheran World Relief (Trace)

At Royal Continental Hotel, Osogbo.

On 29th October,2025.
	PMs/DAES

DAES and others 

Extension Officer,

Online meeting 

Extension Officers

DAES/South west.

ADPs and Others

Small holder farmers 

Cassava Farmers 

All categories of Farmers 

Farmers,Agro dealers & Extension Officers.
	25

100

60

40

60

30

100

150 is each location.

60.
	Optimum seeds NADF, NAERLS 

FMAFS 

FMAFS 

AIR&T

Covenant University by WAVE.

FUNNAB.

AIR&T.

Cato foods/British American Tobacco Foundation, Nigeria.

JUBAILI AGROTECH/ ADP

Lutheran World Relief (Trace Project)


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	Smallholder horticultural empowerment Program (SHEP)
	JICA
	Adopted 
	The activity is is still on going.

	2
	The West African Virus Epidemiology on Cassava 
	WAVE 

Covenant University Ota.
	Adopted 
	The activity is still in place.

	3
	
	
	
	

	4
	
	
	
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	SHEP (Small holder horticultural empowerment Program)
	2021
	10yrs
	To increase farmers income level.

	2
	Nigeria for women project 
	2023
	1Month
	Improving the standard of living for women through input given..

	3
	Trace Project on Cocoa Production.
	2022
	5 yrs
	Improving the GAP in Cocoa production.


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Not available in ADP, farmers depend on open market.

	2
	Credit
	Propose linkage between farmers and financial institutions.

	3
	Agro-chemical
	Available at open market.

	4
	Tractor
	Readily available through the state government of Osun State.

	5
	MTRM situation Report 
	Paucity of fund hinders the MTRM.


CONSTRAINTS

Paucity of fund 

 Lack of mobility for Extension workers.

Inadequate training of extension workers.

No motivation for extension workers like hazard allowance.

Climate change you cannot predict time of raining and dry seasons.

Bad situation of our training halls in the three zones of ADPs in the State.

Name of ADP: PLATEAU

Postal address: Dogon Dutse, Jos

Email:






Telephone: 

A. 2025 EXTENSION SUPPORT INDICATORS
	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	              -
	Lack of funds

	2
	FNTs
	78
	             72
	Holidays, lack of funds

	3
	OFARs
	5
	             4
	 

	4
	No. of Farm Families
	4,942,10
	4,840,00
	ongoing

	5
	No. of SPATs established 
	NA
	NA
	

	6
	No. of MTPs
	370
	340
	

	7
	No. of Field days
	40
	32
	Ongoing

	8
	No. of Agric Shows
	NIL 
	NIL
	

	9
	No. of group formed
	1000
	9000
	Ongoing

	10
	No. of Pre-season training per year
	3
	NIL
	Lack of funds

	11
	No. of Post-season training per year
	3
	NIL
	Lack of funds

	12
	Extension publications produced(No. of Titles)
	
	
	

	
	Bulletins 
	
	
	

	
	Guides
	
	
	Lack of funds

	
	Leaflets
	
	
	

	
	Posters
	
	
	

	
	Others Extension Field Diaries 
	1000
	600
	Ongoing 

	13
	Zonal Steering Committee Meeting
	4
	NIL
	

	14
	Zonal Technical Committee Meeting
	4
	NIL
	

	15
	Zonal REFILS workshops
	1
	1
	

	16
	No of Extension Workers (VEAs)
	1200
	368
	Retirement

	17
	No of Extension workers (BESs)
	90
	67
	

	18
	EA/Farmer ratio in the state
	1:800
	1:6000
	Lack of man power


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins

1. Wheat Production 

2. 

3.

4.

5.


	1000
	370
	PADP

	2
	Guides

1. Doing Good Business Quality Potato 

2. Farms Financial Cycle 

3.

4.

5.
	1000

1000
	600

700
	GIZ

GIZ


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2
	Exploring Avenue for peace building through Agric potato production


	Yes 

Yes 
	Yes 

Yes 
	Once weekly

Once weekly
	J.FM

PRTVC
	45

45


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1
	Home Garden
	Yes 
	Yes 
	Once weekly
	PRTVC
	1Hour


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1

2
	Seed potato Production

General Crop Production
	TETFUND

MAFS
	Youth 

Youth
	80

230
	PADP

PADP


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	Demo on East-west seed (Tomato, Okro, Pawpaw)
	East-west seed 

Company
	Adopted
	Adopted

	2
	Forage crop (Desmodium hardeh egg) Green, Gram Sudam Grass, Leuane, Bracharia
	Zaria Shika
	Adopted
	Ongoing

	3
	Oil palm coconut
	PADP
	Adopted
	Ongoing

	4
	Use of simter organic Fertilizer
	Simter concept
	Adopted
	Ongoing


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	National Refugee Council
	2021
	Ongoing
	Training & distribution of input for refugees

	2
	Secdco
	2016
	Ongoing
	Demo on maize

	3
	C.IP (Internation Potato Centre)
	2021
	Ongoing 
	Demo on  potato

	4
	GIZ
	2016
	Ongoing 
	New Technologies

	5
	Gospel Health
	2023
	Ongoing
	Input and tech empowerment 


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	MAFS/ Plateau Government

	2
	Credit
	NIL

	3
	Agro-chemical
	Large quantity distributed

	4
	Tractor/Animal Traction
	200 units subsidized farming school programmes

	5
	MTRM situation Report 
	NIL


Name of ADP: Sokoto Agricultural Development Project 

Postal address: Abdullahi Fodio Road, PMB 2245. Sokoto 

Email:
sokotoadp@yahoo.com




Telephone_______________________

Name of ADP: 
	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	              -
	Lack of funds

	2
	FNTs
	78
	             72
	Holidays, lack of funds

	3
	OFARs
	5
	             4
	 

	4
	No. of Farm Families
	4,942,10
	4,840,00
	ongoing

	5
	No. of SPATs established 
	NA
	NA
	

	6
	No. of MTPs
	370
	340
	

	7
	No. of Field days
	40
	32
	Ongoing

	8
	No. of Agric Shows
	NIL 
	NIL
	

	9
	No. of group formed
	1000
	9000
	Ongoing

	10
	No. of Pre-season training per year
	3
	NIL
	Lack of funds

	11
	No. of Post-season training per year
	3
	NIL
	Lack of funds

	12
	Extension publications produced(No. of Titles)
	
	
	

	
	Bulletins 
	
	
	

	
	Guides
	
	
	Lack of funds

	
	Leaflets
	
	
	

	
	Posters
	
	
	

	
	Others Extension Field Diaries 
	1000
	600
	Ongoing 

	13
	Zonal Steering Committee Meeting
	4
	NIL
	

	14
	Zonal Technical Committee Meeting
	4
	NIL
	

	15
	Zonal REFILS workshops
	1
	1
	

	16
	No of Extension Workers (VEAs)
	1200
	368
	Retirement

	17
	No of Extension workers (BESs)
	90
	67
	

	18
	EA/Farmer ratio in the state
	1:800
	1:6000
	Lack of man power


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins

1. Wheat Production 

2. 

3.

4.

5.


	1000
	370
	PADP

	2
	Guides

1. Doing Good Business Quality Potato 

2. Farms Financial Cycle 

3.

4.

5.
	1000

1000
	600

700
	GIZ

GIZ

	3
	Leaflets

1. 

2.

3.

4.

5.
	
	
	


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4

5
	Exploring Avenue for peace building through Agric potato production


	Yes 

Yes 
	Yes 

Yes 
	Once weekly

Once weekly
	J.FM

PRTVC
	45

45


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1
	Home Garden
	Yes 
	Yes 
	Once weekly
	PRTVC
	1Hour


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1

2
	Seed potato Production

General Crop Production
	TETFUND

MAFS
	Youth 

Youth
	80

230
	PADP

PADP


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	Demo on East-west seed (Tomato, Okro, Pawpaw)
	East-west seed 

Company
	Adopted
	Adopted

	2
	Forage crop (Desmodium hardeh egg) Green, Gram Sudam Grass, Leuane, Bracharia
	Zaria Shika
	Adopted
	Ongoing

	3
	Oil palm coconut
	PADP
	Adopted
	Ongoing

	4
	Use of simter organic Fertilizer
	Simter concept
	Adopted
	Ongoing


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	National Refugee Council
	2021
	Ongoing
	Training & distribution of input for refugees

	2
	Secdco
	2016
	Ongoing
	Demo on maize

	3
	C.IP (Internation Potato Centre)
	2021
	Ongoing 
	Demo on potato

	4
	GIZ
	2016
	Ongoing 
	New Technologies

	5
	Gospel Health
	2023
	Ongoing
	Input and tech empowerment 

	6
	
	
	
	

	7
	
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	MAFS/ Plateau Government

	2
	Credit
	NIL

	3
	Agro-chemical
	Large quantity distributed

	4
	Tractor/Animal Traction
	200 units subsidized farming school programmes

	5
	MTRM situation Report 
	NIL


CONSTRAINT
Name of ADP: RIVERS STATE ADP

Postal address:

Email:





Telephone______08064237227_________________

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	30
	20
	

	2
	FNTs
	58
	41
	

	3
	OFARs
	
	
	

	4
	No. of Farm Families
	562,000
	368,000
	

	5
	No. of SPATs established 
	59
	59
	

	6
	No. of MTPs
	36
	25
	

	7
	No. of Field days
	56
	44
	

	8
	No. of Agric Shows
	5
	5
	

	9
	No. of group formed
	10
	10
	

	10
	No. of Pre-season training per year
	32
	32
	

	11
	No. of Post-season training per year
	31
	31
	

	12
	Extension publications produced(No. of Titles)
	15
	11
	

	
	Bulletins 
	12
	7
	

	
	Guides
	3
	3
	

	
	Leaflets
	1
	1
	

	
	Posters
	_
	_
	

	
	Others
	_
	_
	

	13
	Zonal Steering Committee Meeting
	12
	8
	

	14
	Zonal Technical Committee Meeting
	12
	8
	

	15
	Zonal REFILS workshops
	6
	3
	

	16
	No of Extension Workers (VEAs)
	25
	14
	

	17
	No of Extension workers (BESs)
	18
	12
	

	18
	EA/Farmer ratio in the state
	1:3048
	56
	


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1

2

3

4

5
	YAM ministry technology 


	ADP Technical department 
	Junior and senior staff 
	20
	Ministry of Agriculture and ADP


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	Use of improved cassava stems
	IITA
	Adopted
	NIL

	2
	
	
	
	

	3
	
	
	
	

	4
	
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Use of fertilizer improve crop yield in the state

	2
	Credit
	No credit facilities 

	3
	Agro-chemical
	It also improve crop yield 

	4
	Tractor/Animal Traction
	None available 

	5
	MTRM situation Report 
	It encourage decision making in ADP


Name of ADP: 
Taraba 

Postal address: 
PMB: 1037 

Email:


robiayoila6@gmail.com 

Telephone: 08146555972 

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	2
	Fund paucity 

	2
	FNTs
	24
	-
	Fund paucity

	3
	OFARs
	5
	-
	Fund paucity

	4
	No. of Farm Families
	288,000
	288,000
	Update required

	5
	No. of SPATs established 
	-
	-
	Nil

	6
	No. of MTPs
	40
	10
	Fund paucity

	7
	No. of Field days
	6
	3
	Fund paucity

	8
	No. of Agric Shows
	2
	-
	Fund constraint 

	9
	No. of group formed
	200
	4
	Fund constraint 

	10
	No. of Pre-season training per year
	2
	-
	Fund constraint  

	11
	No. of Post-season training per year
	2
	-
	Fund constraint

	12
	Extension publications produced (No. of Titles)
	
	-
	

	
	Bulletins 
	Open 
	35
	Commendable 

	
	Guides
	Open 
	115
	Commendable 

	
	Leaflets
	Open 
	-
	

	
	Posters
	Open 
	Stack 
	Commendable 

	
	Others
	Open 
	-
	

	13
	Zonal Steering Committee Meeting
	4
	-
	Fund paucity 

	14
	Zonal Technical Committee Meeting
	2
	-
	Fund paucity 

	15
	Zonal REFILS workshops
	1
	-
	Fund paucity 

	16
	No of Extension Workers (VEAs)
	288
	160
	Need of urgent attention 

	17
	No of Extension workers (BESs)
	30
	15
	Need of urgent attention

	18
	EA/Farmer ratio in the state
	1:1000
	1:1800
	Hinder effective dissemination of information 


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins

1. 

2.

3.

4.

5.


	Open
	35
	NAERLS & WAAP 

	2
	Guides

1. 

2.

3.

4.

5.
	Open
	115
	SPAC

	3
	Leaflets

1. 

2.

3.

4.

5.
	Open
	
	


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1
	NA DUKE TSOHON CINIKI: 

Good Agronomic Practices (GAP). (Ingantattun Hanyoyin Noma).
Post-harvest handling (Kula da amfanin gona bayan girbi.)
	NO
	YES 
	4 times 
	TSBS
	1 hour 

	2
	  
	
	
	
	
	

	3
	
	
	
	
	
	

	4
	
	
	
	
	
	

	5
	
	
	
	
	
	


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2

3

4

5
	
	
	
	
	
	


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1
	Communication and extension methodology training.  
	TADP
	VEA
	100
	TADP

	2
	Improving the capacity development of agricultural extension service: 
	TADP/SPAC – WEST AFRICA 
	VEA/Lead farmers 


	150
	TADP/SPAC – WEST AFRICA

	3
	
	
	
	
	

	4
	
	
	
	
	

	5
	
	
	
	
	


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	Market oriented agriculture 
	SHEP
	Adopted 
	Commendable

	2
	Climate smart Agriculture 
	SPAC-West Africa 
	Adopted 
	Commendable 

	3
	
	
	
	

	4
	
	
	
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	SHEP 
	2020
	4 YEARS 
	Market survey  

Nutrition and hygiene

Family budgeting

Training and retraining of extension agent 

Gender awareness 

Infield training on GAP, Land and measurement.  

	2
	SPAC-West Africa
	2025
	4 YEARS 
	Training of EAs on Climate smart agriculture. 

Hand on training on compose making and organic pesticide production 

Establishment of model farm 

Monitoring and evaluation 

	3
	
	
	
	

	4
	
	
	
	

	5
	
	
	
	

	6
	
	
	
	

	7
	
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	720 Mt distributed to farmers group. 

	2
	Credit
	Nil 

	3
	Agro-chemical
	Nil 

	4
	Tractor/Animal Traction
	Distribution of 750 unit of power tillers to the farmers 

Distribution of 1000 unit of cabriotractors of 50HP on loan basis to the farmers

	5
	MTRM situation Report 
	


CONSTRAINTS 

Poor funding

Lack of working materials 

Shortage of extension staffs 

Lack of mobility e.g. Van/Motorcycle

Name of A

DP: Yobe State Agricultural Development Programme 

Postal address: P.B.M 1038, Damaturu

Email:
yosadp32@gmail.com 


Telephone___08036228959____

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	4
	

	2
	FNTs
	24
	8
	

	3
	OFARs
	32
	Nil
	

	4
	No. of Farm Families
	593,228
	593,228
	

	5
	No. of SPATs established 
	32
	Nil 
	

	6
	No. of MTPs
	64
	Nil 
	

	7
	No. of Field days
	2
	1
	

	8
	No. of Agric Shows
	1
	1
	

	9
	No. of group formed
	500
	300
	

	10
	No. of Pre-season training per year
	2
	1
	

	11
	No. of Post-season training per year
	2
	1
	

	12
	Extension publications produced(No. of Titles)
	
	
	

	
	Bulletins 
	500
	Nil 
	

	
	Guides
	500
	Nil 
	

	
	Leaflets
	500
	Nil 
	

	
	Posters
	500
	Nil 
	

	
	Others
	
	
	

	13
	Zonal Steering Committee Meeting
	4
	Nil 
	

	14
	Zonal Technical Committee Meeting
	2
	Nil 
	

	15
	Zonal REFILS workshops
	1
	Nil 
	

	16
	No of Extension Workers (VEAs)
	540
	200
	

	17
	No of Extension workers (BESs)
	50
	20
	

	18
	EA/Farmer ratio in the state
	1:1000
	1:2000
	


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Produced only (Yes/No)
	Produced & Aired

(Yes/No)
	Frequency of airing 
	Broadcasting station
	Duration

	1

2
	Zauran Manoma

Mukoma Gona
	No 

No 
	Yes 

Yes 
	Twice a week
	YBC

YBC
	2 hours 

2 hours 


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	No of Trainees
	Collaborators 

	1

2

3

4

5
	Training on GAP

Training on climate change

Training on back yard gardening 

General training on Gaps 


	MOA/ADP

MCRP

CCDRN

FAO
	EA’s

EA’s

EA’s

EA’s
	200

200

500

200
	LCRI

LCRI/Unimaid

WFP

Unimaid 


F. TECHNOLOGIES BEING PROMOTED IN 2025

	SN
	Title
	Source 
	Adoption

(Adopted/Not Adopted)
	Comment



	1
	Handling & maintenance of equipment
	MARD
	Adopted
	

	2
	Tractor operation @ maintenance 
	MAO/ADP
	Adopted
	

	3
	Fertilizer application methods 
	MAO/ADP
	Adopted
	

	4
	Soil & water mgt technology
	MANR/ADP
	Adopted
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	Intergated Agricultural Development project
	2025
	10 years
	Producetion & processing of agro -product 

	2
	Larva project 
	2024
	8 years 
	Irrigation promotion & support project 


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	200 trucks purchase & distributed 

	2
	Credit
	

	3
	Agro-chemical
	5000 litres purchase & distributed 

	4
	Tractor/Animal Traction
	130 new tractors purchase 

	5
	MTRM situation Report 
	4 MTRM conducted 


CONSTRAINTS 

late onset of rainfall,

erratic distribution of the rain, 

dry spells, incidences of pest and diseases, 

floods and early ceasation of the rainfall, which leads to poor yield in all the agricultural products across the state.

Name of ADP: ZAMFARA STATE 

Postal address:

Email:






Telephone_______________________

A. 2021 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	ACHIEVED 
	REMARKS

	1
	MTRMs
	12
	
	

	2
	FNTs
	24
	
	

	3
	OFARs
	120
	
	

	4
	No. of Farm Families
	688,045
	
	

	5
	No. of SPATs established 
	1800
	
	

	6
	No. of MTPs
	400
	
	

	7
	No. of Field days
	4
	
	

	8
	No. of Agric Shows
	4
	
	

	9
	No. of group formed
	1,100
	
	

	10
	No. of Pre-season training per year
	2
	
	

	11
	No. of Post-season training per year
	2
	
	

	12
	Extension publications produced (No. of Titles)
	
	
	

	
	Bulletins 
	1500
	
	

	
	Guides
	1500
	
	

	
	Leaflets
	200
	
	

	
	Posters
	400
	
	

	
	Others
	-
	
	

	13
	Zonal Steering Committee Meeting
	4
	
	

	14
	Zonal Technical Committee Meeting
	2
	
	

	15
	Zonal REFILS workshops
	1
	
	

	16
	No of Extension Workers (VEAs)
	500
	
	

	17
	No of Extension workers (BESs)
	40
	
	

	18
	EA/Farmer ratio in the state
	1:2000
	
	


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	SN
	Title
	Copies Targeted 
	Copies Achieved
	Collaborators

	1
	Bulletins

1. crops 

2.livestock 

3.fisheries 

4.horticulture 

5.W.I.A


	400

100

200

100

200


	
	NAERLS

	2
	Guides

1. crops

2.fisheries

3.livestock

4.W.I,A

5. horticulture
	500

200

200

100

200
	
	NAERLS

	3
	Leaflets

1. crops

2.fisheries 

3.livestock

4.W,I,A

5.horticulture
	1000

300

200

200

200
	
	NAERLS


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting station
	Duration

	1

2

3

4

5
	Beekeeping production techniques 

Vegetables production techniques 

Silage making for dry season feeding 

Aquaculture 

Wheat production techniques 
	Twice weekly

(Sunday 3:30pm-4pm

Tuesday 11;30-12;30pm)


	Zamfara Radio  
	30 Minutes


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting station
	Duration

	1

2

3

4

5
	Orchard management practices 

Shelterbelt establishment 

Selection of improved seed/seedling

Promoting good agronomic practices on crop production

Commercial poultry production (Broilers &layers)
	Twice weekly

(Sunday 11pm monday 7:30am)
	NTA Gusau
	1 hour


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1

2

3

4

5
	Pre-season training for Extension agents 

Soil testing training 

Orchard layout training 

Fish fund establishment practices 

Maintenance of water pumps  
	ZADP
	Extension Agents and Farmers
	March 

April 

March

January

March 
	IAR/\NAERLS

& SG 2000


F. TECHNOLOGIES BEING PROMOTED IN 2022

	SN
	Title
	Source 
	Comment



	1
	SAMMAZ 14&17
	IAR
	

	2
	FARO 44
	NCRI
	

	3
	SAMSORGH 45&47
	IAR
	

	4
	BROILER& LAYER FARMING
	NAPRI
	

	5
	Aquaculture Using Small TankS
	
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	NG-CARES (Result Area II)
	2022
	4 years
	Support to poor farmers

	2
	ACReSAL Project
	2022
	5 years
	Climate change mitigation/adoption

	3
	SPIN Project
	2025
	5 years
	Irrigation and power generation 

	4
	L-PRESS Project  
	2024
	5 years
	Livestock productivity enhancement 


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Large quantity of fertilizers to procured 

	2
	Credit
	Linkage farmer with NIRSAL

	3
	Agro-chemical
	To be sold to farmer at subsidies rate 

	4
	Tractor/Animal Traction
	Hundred of power tillers to procured to farmers at subsidize price  

	5
	MTRM situation Report 
	Effort are been made to finance the QTRM activities by the Government 


2026 WORKPLAN

NARIs WORKPLAN

[image: image55.jpg]


                                                                                                      [image: image56.png]



Name of Research Institute: Forestry Research Institute of Nigeria (FRIN)
Postal Address: P.M.B 5054, Jericho Hills, Ibadan, Oyo State
Website: www. frin.gov.ng

E-mail:  dgfrin@frin.gov.ng, info@frin.gov.ng
Telephone:
0704760 4000, 08070947851
A.   EXTENSION SUPPORT ACTIVITIES

	SN
	Title
	Proposed No 
	Proposed Date
	Collaborating Institute
	Remarks

	1
	Diagnostic survey
	
	
	
	

	2
	On-Station Research (OSR)
	
	
	
	

	3
	OFR
	
	
	
	

	4
	MTRM
	
	
	
	

	5
	Joint Scientific Field Evaluation
	
	
	
	

	6
	Field days
	
	
	
	

	7
	Zonal REFILS Workshop
	
	
	
	

	8
	Pre-season training
	
	
	
	

	9
	Post-season training
	
	
	
	

	10
	Zonal Steering Committee Meeting
	
	
	
	

	11
	Zonal Technical Committee Meeting
	
	
	
	

	12
	In-house Review Meeting/Cropping Scheme Meeting
	
	
	
	

	13
	National Agricultural Extension Review and Planning Meeting (NAERPM)
	
	
	
	

	14
	Adopted Village to be established
	
	
	
	

	15
	Training Workshop (To Organize)
	
	
	
	

	16
	Training Workshop (To attend) 
	
	
	
	

	17
	Trade Fair
	
	
	
	

	18
	Research Institute Field day
	
	
	
	

	19
	World food day
	
	
	
	

	20
	Wet season evaluation
	
	
	
	

	21
	Dry season evaluation
	
	
	
	

	22
	National Agric. Shows, State, NGOs and others
	
	
	
	


B.    TECHNOLOGY DEVELOPMENT

	S/No
	Technology to be Developed within the Year Under Review 
	Level of Preparedness (%)
	Month to be Released
	Target Audience
	Expected Output/Outcome

	1
	
	
	
	
	

	2
	
	
	
	
	

	3
	
	
	
	
	

	4
	
	
	
	
	

	5
	
	
	
	
	

	6 
	
	
	
	
	

	Etc.
	
	
	
	
	


Name of Contact Person: Dr. Osikabor Benson

Post/Rank: Associate Research Professor

Phone Number: +234 810 410 6631

Name of Research Institute: Institute for Agricultural Research, Ahmadu Bello University, Zaria

Postal Address: P.M.B.1044 ABU Zaria, Kaduna state, Nigeria

Website:     www.iar.gov.ng      
E-mail: aminusharifai@gmail.com

Telephone:  +2348023790983


A.   EXTENSION SUPPORT ACTIVITIES

	SN
	Title
	Proposed No 
	Proposed Date
	Collaborating Institute
	Remarks

	1
	Diagnostic survey
	5
	1st, 2nd & 3rd Quarter
	NARIs
	

	2
	On-Station Research (OSR)
	 40
	1st, 2nd & 3rd Quarter
	NARIs
	

	3
	OFR
	 8
	1st, 2nd & 3rd Quarter
	AVISA, CIMMYT, ICRISAT, ECOWAS, EU, AFD, AATF, PICACC/NB
	

	4
	MTRM
	3
	 3rd Quarter
	NARIs
	

	5
	Joint Scientific Field Evaluation
	3
	1st, 2nd & 3rd Quarter
	NARIs
	

	6
	Field days
	 3
	 3rd Quarter
	NARIs 
	

	7
	Zonal REFILS Workshop
	 1
	1st, 2nd & 3rd Quarter
	ADPs & MOA staff
	

	8
	Pre-season training
	10
	1st, 2nd & 3rd Quarter
	ADPs & MOA staff
	

	9
	Post-season training
	4
	 4th Quarter
	ADPs & MOA staff
	

	10
	Zonal Steering Committee Meeting
	1
	1st, 2nd & 3rd Quarter
	ADPs & MOA staff
	

	11
	Zonal Technical Committee Meeting
	1
	1st, 2nd & 3rd Quarter
	ADPs & MOA staff
	

	12
	In-house Review Meeting/Cropping Scheme Meeting
	 11
	1st Quarter
	NARIs, FMARD etc 
	

	13
	National Agricultural Extension Review and Planning Meeting (NAERPM)
	1
	4th Quarter
	IAR, NAERLS, NAPRI etc
	

	14
	Adopted Village
	 3
	1st, 2nd & 3rd Quarter
	NARIs
	

	15
	Training Workshop (To Organize)
	10
	1st, 2nd & 3rd Quarter
	NARIs
	

	16
	Training Workshop (To attend) 
	 10
	1st, 2nd & 3rd Quarter
	 NARIs
	

	17
	Trade Fair
	4
	1st, 2nd & 3rd Quarter
	 NARIs
	

	18
	Research Institute Field day
	5
	1st, 2nd & 3rd Quarter
	 -
	

	19
	World food day
	 1
	1st, 2nd & 3rd Quarter
	 NARIs
	

	20
	Wet season evaluation
	 1
	4th Quarter
	 NARIs
	

	21
	Dry season evaluation
	1
	 3rd & 4th Quarter
	 NARIs
	

	22
	National Agric. Shows/others, state, NGOs
	 4
	  3rd Quarter
	NARIs
	


B.    TECHNOLOGY DEVELOPMENT

	S/No
	Technology to be Developed within the Review Year 
	Level of Preparedness (%)
	Month to be Released
	Target Audience
	Expected Output/Outcome

	
	
	
	
	
	


C. EXTENSION PUBLICATIONS
	SN
	Title
	Target Copies
	Expected Month of Completion 
	Collaborators

	1
	Bulletins: 
Extension guides on our mandate crops and Machineries 
	500 copies each 


	2nd Quarter
	Programme Leaders / HOUs 



	2
	Guides

1. Crop varieties posters 
2. Institute Brochure 
	50 copies

1000 copies 
	2nd Quarter
	Programme Leaders / HOUs 

	3
	Leaflets

1. Leaflets on newly released crops                       varieties 
2. Technologies for women (Leaflets) 
	2,000 copies 

500 copies 


	2nd Quarter
	Programme Leaders / HOUs 



	4
	Posters

1. Roll-up banners
2. Institute Poster 
3. Institute Year planner 
	12

500

1000 
	2nd Quarter
	Programme Leaders / HOUs 



	5
	Others (Specify)

This Week
News letter 
	52 volumes

4 volumes 
	2nd Quarter
	Programme Leaders / HOUs  




D. RADIO PROGRAMMES
	SN
	Topic
	Channels/Station
	Duration 
	Proposed number of airing 
	Collaborators

	1
	Maize production
	FRCN
	30mins
	13
	

	2
	Agronomic practices for cotton production
	FRCN
	30mins
	13
	


E. TELEVISION PROGRAMMES
	SN
	Topic
	Channels/Station
	Duration 
	Proposed number of airing 
	Collaborators

	1
	Best Cowpea production practices
	NTA
	30 mins
	13
	

	2
	Value addition to Cereal crops
	NTA / Rahama
	30 mins
	13
	


F. TRAINING WORKSHOP
	SN
	Title
	Category of trainees
	No of trainees
	Collaborators
	Duration

	1
	Farmers training
	Farmers, & Extension Agents
	500 


	USAID, CORAF, IAR & PAIRED 


	3 Days

	2
	Product development and design


	Farmers, & Extension Agents
	100
	USAID, CORAF, IAR & PAIRED 


	1 day


G.    ADOPTED VILLAGES AND SECONDARY SCHOOLS ACTIVITIES
	SN
	Activities
	No. Proposed
	Target Audience
	Technologies to be Promoted
	Remarks

	1
	Training of Farmers on how to carry out climate predictions for their own villages.
	2
	Village Farmers
	Climate smart agriculture
	

	2
	Workshops on Agribusiness appreciation to Secondary School students
	3
	Schools
	Agribusiness
	

	3
	Train Farmers on best agronomic practices for some IAR mandate crops
	3
	Village Farmers
	Agronomic practices
	

	4
	To organize a familiarization tour of IAR programmes for Schools and villages.
	2
	Schools & Villages
	-
	

	5
	To establish small vegetable gardens for Schools.
	1
	Schools
	-
	

	6
	To set up demonstration plots in Villages
	2
	Village Farmers
	-
	

	7
	Workshop on how to conduct villages level technology adopted
	1
	Village Farmers
	-
	

	8
	Expansion of Adopted Villages and Schools
	2
	Village & Schools
	There is the need to establish more Adopted village in southern part Kaduna State. One community and one school in each of Kachia, Kafanchan and Jaba LGAs. One community and one school in Kano, Zamfara and Katsina States for a start (2024).


	


Name of Contact Person: Prof. A. Sharifai
Post/Rank: Professor

Phone Number:  08023790983

[image: image57.jpg]


                                                                                                                [image: image58.jpg]



Name of Research Institute: Institute of Agricultural Research and Training

Postal Address: P.M.B. 5029, Moor Plantation, Ibadan

Website: www.iart.gov.ng
E-mail: director@iart.gov.ng
Telephone: 07039394840

EXTENSION SUPPORT ACTIVITIES
	SN
	Title
	No Proposed
	Date Proposed
	Collaborating Institute
	Remarks

	1
	Diagnostic survey
	5
	February –October.
	ADP, SW REFILS, NARIS
	

	2
	On-Station Research (OSR)
	30
	May for early

season, August for late season
	Scientists/ NARIs
	May vary due

to climatic variability

	3
	OFR
	15
	May for early season, August for

late season
	ADP, Farmers, NARIs
	May vary due to climatic

variability

	4
	MTRM
	72
	Every month
	ADP, Farmers, NARIs, Universities
	All things being equal

	5
	Joint Scientific Field Evaluation
	4
	February, June, August, October
	ADP, Farmers, NARIs, Universities
	

	6
	Field days
	10
	February – November
	ADP, Farmers, NARIs, Universities
	

	7
	Zonal REFILS Workshop
	1
	February or April
	All stakeholders in agricultural value

Chain
	

	8
	Pre-post season
	2
	April/ November
	SMS, Scientists, reps
	


	
	Training
	
	
	CBA
	

	9
	Zonal Steering

Committee Meeting
	1
	November
	ADP, IART, ADP,

NARIs, media
	

	10
	In-house Review

Meeting/Cropping Scheme
	1
	February/April
	All stakeholders in

agricultural value chain
	


	11
	Zonal Technical

Committee Meeting
	1
	May
	IAR&T, State ADP

PMs, others NARIs in SWN, Reps of CBAs
	

	12
	National Agricultural Extension Review and Planning 1Meeting (NAERPM)
	1
	December
	NARIS, ADPs,

Farmers groups, Policy makers
	

	13
	Adopted Village
	4
	Jan-Dec
	IAR&T
	

	14
	Training Workshop (To

Organize)
	20
	February – Nov.
	IAR&T
	

	
	Training

Workshop (To attend)
	10
	Jan-Dec
	
	

	15
	Trade Fair
	2
	To be fixed by Organizers
	
	

	16
	Research Institute Field day
	3
	June, Sept, November
	Research institutes
	

	17
	World food day
	1
	October
	
	

	18
	Wet & dry season evaluation
	2
	Wet/ dry season
	NAERLS
	

	19
	National Agric.

Shows/others, state, NGOs
	4
	Determine by organizers
	Stakeholders in agric.
	


TECHNOLOGY DEVELOPMENT

	S/No
	Technology Developed within the Review Year
	Level of Preparedne ss (%)
	Month of Release
	Target Audience
	Expected Output/Outcome

	1
	Improved indigenous meat type chicken
	90%
	March, 2026
	Poultry farmers,

marketers, processors,
	Improved indigenous Meat type chicken

developed, registered and released


	
	
	
	
	Research Institute
	

	2
	Kenaf spinning
	95
	June,
	Farmers,
	Improved product,

	
	and decorticating
	
	2026
	extension
	reduced drudgery in

	
	Machine
	
	
	agents,
	processing

	
	
	
	
	policy
	

	
	
	
	
	makers
	


	3
	Kenaf crop harvester
	75
	Aug. 2026
	Farmers, extension agents,

policy makers
	Reduced time spent of harvesting, reduced drudgery and good fibre quality

	4
	Development of roselle and sunflower technologies
	50
	Oct. 2026
	Farmers, extension agents, policy

Makers
	Enhanced nutrition and income generation

	5
	Improved pigeon pea mix processing
	70
	Nov. 2026
	The Institute (IAR&T),

farmers, farm families, ADPs,

marketers, processors, Small and medium scale Enterprise (SME).
	OUTPUT

Quality pigeon pea mix products from IAR&T

Income generation for use of the technologies by SME and large-scale industries

	7
	Quality based Pigeon pea
	70
	Sept 2026
	Farmers, Students, Researchers and other relevant

stakeholders
	Identification of high quality Pigeon pea seed

	8
	Improved crosses of indigenous breeds of pigs
	40
	Dec. 2026
	Farmers, Students, Farm Families, Extension Agents
	Improved knowledge and practices

	10
	Package on Pigeon Pea Value Addition Technologies
	40
	Dec. 2026
	Farmers, Students, Farm Families,

Extension Agents
	Improved knowledge and practices


	11
	Kenaf green tea
	60
	Sept. 2026
	Farmers, Household, consumers, food vendors, food

industry,
	Healthy green tea for nourishment


	12
	Development of

processing line for sunflower
	40
	Nov. 2026
	Farmers and

sunflower processors
	Well packaged sunflower products

	14
	Development of adoptable cowpea technologies

along value chain
	50
	Sept. 2026
	Farmers and sunflower processors
	-do-


EXTENSION PUBLICATIONS

	SN
	Title
	Target Copies
	Expected Month of Completion
	Collaborators

	1
	Bulletins

1. IART News Bulletin
	20
	Nov
	

	2
	Guides
	
	
	

	
	1. Climatic variability and mitigation
	5
	March
	Climatologist,

	
	2. Management of degraded soils
	5
	April
	Nimet

	
	3.Sheep and goat production
	5
	May
	IAR&T

	
	4. Cattle production
	5
	May
	

	
	5.Piggery/artificial insemination
	5
	June
	IAR&T

	
	6. production and processing of soy
	5
	
	IAR&T

	
	Bean
	
	August
	

	
	7. lima beans processing
	5
	Sept
	

	3
	Leaflets
	
	February March

April

May June
	-do-

	
	1. Fertilizer handling and application
	
	
	

	
	for different soils
	10
	
	

	
	2. Application and handling of
	5
	
	

	
	agrochemicals
	
	
	

	
	4. production of compost and
	5
	
	

	
	Application
	
	
	

	
	5.Good agricultural practices
	10
	
	

	
	6. Disease and pest control on
	15
	
	

	
	different crops
	
	
	

	4
	Posters
	
	June Sept.
	

	
	1. Hybrid maize/popcorn production
	10
	
	

	
	2.Kenaf production and processing
	10
	
	

	
	Lima beans processing

soil and water conservation

methods
	5

5
	July August
	

	5
	Others (Specify)
	
	
	


IO PROGRAMMES

	SN
	Topic
	Channels/Station
	Duration
	Proposed number of airing
	Collaborators

	1
	Agbe Asejere
	Premier FM,
	30mins
	52 weeks
	ADPs,
scientists, media stations


TELEVISION PROGRAMMES

	SN
	Topic
	Channels/Station
	Duration
	Proposed number of

airing
	Collaborators

	2
	Technological Innovations from IAR&T for sustainable

Agricultural Development
	BCOS, FRCN

Paramount FM ,
	1 hour
	4
	Media stations,

Scientist in the institute


TRAINING WORKSHOP

	SN
	Title
	Category of trainees
	No of trainees
	Collaborators
	Duration

	1
	Training on sustainable use of soil

and water management Technologies
	Commodity

farmers and extension officers
	200
	ADPs
	

	2
	Training of stakeholders in kenaf value chain in South West Nigeria on improved technologies and

production technique and Utilization
	Farmers/extension agents, Cottage industries and

artisans in kenaf value chain
	150
	ADPs
	

	3
	Capacity building on IAR&T food processing technologies for

household food security and income generation
	Extension agents, processors, youth
	500
	ADPs
	

	6
	Capacity building on handling of modern processing equipment
	Farmers/extension Agents
	500
	ADPs
	

	8
	Awareness, safe handling and responsible use of agrochemical

among farmers in South West Nigeria
	Farmers/extension agents
	700
	ADPs
	


ADOPTED VILLAGES AND SECONDARY SCHOOLS ACTIVITIES

	SN
	Activities
	No. Proposed
	Target Audience
	Technologies to be Promoted
	Remarks

	1
	Adopted Villages
	4
	Farmers, youth, women in agriculture
	Improved varieties of maize, cowpea and Kenaf; Training on agricultural mechanization;

Processing of underutilized beans;
	

	2
	Adopted schools
	2
	Secondary school students,
	Sustainable soil management; Agricultural mechanization; Processing of agricultural products-production of cassava flour, chin-chin, roselle wine,
	


Name of Contact Person:
Prof. Ajayi Festus Temitope

Post/Rank: Zonal Coordinator, SW REFILS.

Phone Number:       07039394840

[image: image59.jpg]


                                                                                                     [image: image60.wmf]
Name of Research Institute: Lake Chad Research Institute Maiduguri

Postal Address: P.M.B 1293 Maiduguri, Borno State 

Website: www.lcri.gov.ng                  E-mail: infor@lcri.gov.ng

Telephone: 

A.   EXTENSION SUPPORT ACTIVITIES

	SN
	Title
	Proposed No 
	Proposed Date
	Collaborating Institute
	Remarks

	1
	Diagnostic survey
	2
	September
	LCRI
	

	2
	On-Station Research (OSR)
	50
	Nov & July
	LCRI/OLAM/AVISA/CIMMYT/ICARDA
	

	3
	OFR
	150
	Nov & July
	LCRI/OLAM/AVISA/CIMMYT/ICARDA
	

	4
	MTRM
	12
	Decided by the ADPs
	LCRI/ADPs
	

	5
	Joint Scientific Field Evaluation
	2
	July/ Dec
	LCRI/AVISA/NASC/NAGRAB/BREWERIES/OLAM
	

	6
	Field days
	3
	Mar & July and Sep
	LCRI/ADPs
	

	7
	Zonal REFILS Workshop
	1
	June
	LCRI/NARIs/ADPs
	

	8
	Pre-season training
	2
	 May and October   
	LCRI/UNIMAID
	

	9
	Post-season training
	2
	April & Sep
	LCRI/UNIMAID
	

	10
	Zonal Steering Committee Meeting
	4
	Decided By The ADPs
	LCRI/ZONAL ADPs
	

	11
	Zonal Technical Committee Meeting
	2
	Jun/Nov
	LCRI/ZONAL ADPs
	

	12
	In-house Review Meeting/Cropping Scheme Meeting
	1
	May
	LCRI/ADPs
	

	13
	National Agricultural Extension Review and Planning Meeting (NAERPM)
	1
	Nov
	NAERLS/ADPs/NARIs
	

	14
	Adopted Village to be established
	2
	    June
	LCRI
	

	15
	Training Workshop (To Organize)
	3
	Jan/ Mar/ Aug
	LCRI/CRS/ AND ICRC
	

	16
	Training Workshop (To attend) 
	5
	Within The Calendar Years
	LCRI
	

	17
	Trade Fair
	1
	Dec/Jan
	LCRI/KANO MINISTRY OF TRADE AND INVESTMENT
	

	18
	Research Institute Field day
	3
	Sep and April
	LCRI/FARMERS/
	

	19
	World food day
	1
	October
	
	

	20
	Wet season evaluation
	1
	August
	LCRI/ALL NARIS
	

	21
	Dry season evaluation
	1
	January
	LCRI/OLAM/AVISA
	

	22
	National Agric. Shows, State, NGOs and others
	1
	Nov
	National Agric Foundation/Naris/Farmers

NGOs/Input Dealers Agencies/ State& Local Govt Council


	


B.    TECHNOLOGY DEVELOPMENT

	S/No
	Technology to be Developed within the Year Under Review 
	Level of Preparedness (%)
	Month to be Released
	Target Audience
	Expected Output/Outcome

	1
	
	
	
	
	

	2
	
	
	
	
	

	3
	
	
	
	
	

	4
	
	
	
	
	

	5
	
	
	
	
	

	6 
	
	
	
	
	

	Etc.
	
	
	
	
	


C. EXTENSION PUBLICATIONS
	SN
	Title
	Target Copies
	Expected Month of Completion 
	Collaborators

	1
	Bulletins

1. Improved Millet

2. Improved Wheat

3. Improved barley

4. 

5.

Etc.
	3
	March
	LCRI

	2
	Guides

1. Improved Millet

2. Improved Wheat

3. Improved barley

4.

5.

Etc.
	
	
	

	5
	Others (Specify)

1. 

2.

3.

4.

5. 2025 Year Planner
	1000
	February
	LCRI


D. RADIO PROGRAMMES
	SN
	Proposed Titles
	Channels/Station
	Duration 
	Proposed number to be aired 
	Collaborators

	1
	Faraskiram Barewuye
	BRTV Maiduguri
	One Year
	52
	LCRI/AVISA

	2
	Filin  Monoma


	FRCN/Peace FM Maiduguri
	One Year
	52
	LCRI/AVISA

	Etc.
	
	
	
	
	


E. TELEVISION PROGRAMMES

	SN
	Proposed Titles
	Channels/Station
	Duration 
	Proposed number to be aired 
	Collaborators

	1
	Faraskiram Barewuye
	NTA Maiduguri
	One Year
	27
	LCRI/AVISA

	2
	TV Documentary In English On Our Mandate Crops


	NTA Maiduguri
	One Year
	27
	LCRI/AVISA

	Etc.
	
	
	
	
	


F. TRAINING WORKSHOP
	SN
	Title
	Category of trainees
	No of trainees
	Collaborators
	Duration

	1
	National Pre-season training workshop for farmers on the production and utilization of cereal and legumes in Borno State
	Farmers
	100
	LCRI/UNIMAID
	One day

	2
	National pre-season training workshop  for farmers on the production of irrigated wheat in Nigeria
	Farmers
	100
	LCRI
	Two days

	Etc.
	
	
	
	
	


G.    ADOPTED VILLAGES AND SECONDARY SCHOOLS ACTIVITIES
	SN
	Activities
	No. Proposed
	Target Audience
	Technologies to be Promoted
	Remarks

	1
	Production of improved millet variety/ at mustapha umar el-kanemi school farm


	1
	Agricultural Science Students
	improved millet production technologies/processing/value addition and marketing
	Promote Agricultural Science as a venture business among secondary school students

	2
	Class lecture session for students on agronomic practice of improved millet production technologies
	1
	Agricultural Science Students
	Theoretical aspect of improved millet production technologies/processing/value addition and marketing
	

	Etc.
	
	
	
	
	


Name of Contact Person: Dr.Jidda Umar
Post/Rank: HOD Agric Economics & Extension Phone Number: 08032275499

Name of Research Institute: National Agricultural Extension and Research Liaison Services (NAERLS)
Postal Address: NAERLS, ABU Zaria, P.M.B. 1067, Zaria, Kaduna State, Nigeria.

Website: www.naerls.gov.ng                                         
E-mail: director@naerls.gov.ng 

Telephone: 08056694565











A.   EXTENSION SUPPORT ACTIVITIES

	SN
	Title
	No Proposed
	Date Proposed
	Collaborating Institute
	Remarks

	1
	Diagnostic survey
	87
	
	
	

	2
	On-Station Research (OSR)
	
	
	
	

	3
	OFR
	
	
	
	

	4
	MTRM
	
	
	
	

	5
	Joint Scientific Field Evaluation
	
	
	
	

	6
	Field days
	
	
	
	

	7
	Zonal REFILS Workshop
	4
	
	
	

	8
	Pre-post season training
	
	
	
	

	9
	Zonal Steering Committee Meeting
	1
	
	
	

	10
	In-house Review Meeting/Cropping Scheme
	1
	
	
	

	11
	Zonal Technical Committee Meeting
	4
	
	
	

	12
	National Agricultural Extension Review and Planning Meeting (NAERPM)
	1
	
	
	

	13
	Adopted Village
	
	
	
	

	14.
	Training Workshop (To Organize)
	87
	
	
	

	15.
	Training Workshop (To attend) 
	28
	
	
	

	16.
	Trade Fair
	
	
	
	

	17.
	Research Institute Field day
	2
	
	
	

	18.
	World food day
	1
	
	
	

	19.
	Wet & dry season evaluation
	2
	
	
	

	20.
	National Agric. Shows/others, state, NGOs
	
	
	
	


B.    TECHNOLOGY DEVELOPMENT

	S/No
	Technology Developed within the Review Year 
	Level of Preparedness (%)
	Month of Release
	Target Audience
	Expected Output/Outcome

	1
	
	
	
	
	

	2
	
	
	
	
	

	3
	
	
	
	
	

	4
	
	
	
	
	

	5
	
	
	
	
	

	6
	
	
	
	
	


C. EXTENSION PUBLICATIONS
	SN
	Title
	Target Copies
	Expected Month of Completion 
	Collaborators

	1 

2 

3

4

5

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

23

24

25

26

27

28

29

30

31

32

33

34

35

36

37

38

39

40

41

42

43

44

45

46

47

48

49

50

51

52

53

54

55

56

57

58

59

60

61

62

63

64

65

66

67

68

69

70

71

72

73

74

75

76
	BULLETTINS
Smart Technologies for Primary Processing of Agricultural Produce

Basic farm equipment and machineries and their management (features, use, and maintenance) will be compiled for farmers within Kaduna state. Where this equipment and machineries can be found and possibly the current market prices will be compiled to enhance farmers decisions and choice.
Construction of an in-situ Rain harvesting Structure for Irrigation
 Irrigation Techniques for efficient water management
Groundnut Production under Irrigation
Tomato Production under Irrigation
Maintenance of Some Selected farm Structure
Construction and Management of Aquaponic
 Post-harvest handling and storage of Yam
 Strategies to reduce post-harvest loss on cereals
General Maintenance of Rice polishing machine
Management of Salt-affected Soils of Irrigated Lands
Rain Water Harvest for Irrigation Purpose
Strategies to reduce post-harvest losses
 Solar water pumping for irrigation
 Biochar production for farm use
Maintenance and Operation of Rice Dehusking Machine
 Extraction of oil from Jatropha
 Solar Drying of Selected Fruit and Vegetables
 Techniques on how to Establish  and manage Adopted School
Ways of estimating crop yield using a crop-cut box in Nigeria Carrot Marketing, Processing and Utilization in Nigeria

Costs and returns of Beekeeping in the Nigerian Savanna

Cabbage Production, Processing, Utilization and Marketin
 
UnderstandingClimateSmartAgriculture forsmallholder Farmers
Aggregating of Smallholder farmers for Better Support Services Agricultural Marketing Information for EAs and Farmers.

Local weights, measures and conversions of Nigerian food commodities

Group resource mobilization and management for CBA’s in Nigeria

Application of Artificial Intelligence to Boost Agricultural production in Nigeria

Techniques for Sourcing Vital Information on Agricultural Research for Extension Personnel and Farmers

Economic-Benefit of Groundnut oil Processing and marketing in Nigeria

Staking and Pruning of Tomatoes

Facilitating farmer's agripreneurship

Marketing strategies for small-scale farmers

Communal Farming in Nigeria

Tea farming business in Nigeria

Understanding Climate Smart Agriculture for smallholder Farmers

Techniques for Effective Supervision of Extension Programmes

The Economic potential of Moring

Ethics, Readability, and Content Requirements for Extension Bulletin Writing

 Precision Extension Service Delivery in Nigeria

Enhancing Cocoa Production Through Risk Management

Risk Identification and Management in Fish Farming

Economics of Kenaf Production

Expected role of women in Rice production

Empowering farmers through climate-smart agriculture techniques for resilience and productivity

Risk management in vegetable production

Mobilizing for viable Gender Based Cooperative Societies
Agricultural Extension Communication Approach in Intercultural Farming Community Conflict Resolution
Empowering Rural Farmers through Climate-Smart ICTs and Extension Advisory Services.
Application of Artificial Intelligence to boost Agricultural production in Nigeria

Leveraging on Smart Agriculture to improve Agricultural Productivity Amongst Small Holders  Farmers in Nigeria

Saffron Production, Processing and Marketing in Nigeria.

Climate-Smart Agriculture Practices for Resilient Farming Communities in Nigeria
Empowering Farmers Through Climate-Smart Agriculture: Techniques for Resilience and Productivity

Effective Communication in Agricultural Extension Services
Agricultural Extension Communication Approach in Intercultural Farming Community Conflict Resolution

Empowering Rural Farmers through Climate-Smart ICTs and Extension Advisory Services.

Techniques of Producing Agricultural Extension Radio Programmes
The Use of Drones for Agricultural Television programmes Production
Community entry protocols for Extensionists and Advisors.  
The Use of Drones for Agricultural Television programmes Production
Community entry protocols for Extensionists and Advisors.  
Extension Communication Channel for Extension and Advisory Services Delivery in Nigeria
Youth and women empowerment through extension services
Breaking barriers: women leading agricultural transformation in rural communities
Methods of Fertilizer Application for Enhanced Soil Conditions and Crop Yield
The Bulleting will provide an information on different method of fertilizer application.    
Groundnut Production, Processing, Utilization and Marketing in Nigeria 
Lettuce production, marketing, processing and utilization in Nigeria
 Method of fertilizer Application to Enhanced Soil Condition and Crop Yield 
 Management of Soil Through Crop Production Practices 
Organic Farming for better soil and crop
Tillage practices for better soil and crop  
Scent leave (Ocimum gratissimum) utilization and marketing:
 Processing, utilization and marketing of sweet melon in Nigeria.
Solar Food Processing and Cooking Methodologies
Composition, Nutrition and Utilization of plantain dish in health and Diseases.
Production, Processing and Utilization of Orange fleshed sweet potato (OFSP)Sweet potato leaves: Nutritional value, benefits and utilization
The Nutritional Composition and Marketing Value of Grasscutter
Preparation, Utilization and Marketing of Snail meat in Nigeria.
Nutrition and Health Benefits Awareness of Some Essential Oils
Processing and Utilization of Legumes
Community-based infant food formulation and preparation
Processing and Utilization of African Fan Palm in Nigeria
Empowering Rural Farmers through Climate-Smart ICTs and Extension Advisory Services.
Using Agroforestry Nature's Benefits to Boost Biodiversity and Food Security.
Economic importance of rabbit droppings and urine
 Fattening of meat type rabbit
 Feed formulation and feeding practices in sheep and goats production
Disease Management in poultry  
Livestock Breed Improvement and Fertility Management Techniques
Poultry Product Handling, Processing, Packaging/Labelling and Storage
Dromedary Camel Husbandry
Egg Handling, Egg Glut and Processing Technology
Fundamentals of grasshopper farming
Ostrich production in Nigeria
Hatchery Maintenance and Management Practic 
	
	
	FMAFS, Other NARIs

	1

2

3

4

5

6

7

8

9

10

11

12

13

14

15

16

17

18

19

20

21

22

23

24

25

26

27

28

29

30

31

32

33

34

35

36

37

38

39

40

41

42

43

44

45

46

47

48

49

50

51

52

53

54
	GUIDES

Construction of a maize size grader

Automation Of a Mechanical Stirrer For Stirring Grain Spread Processing and Preservation of Onion 

Processing and Preservation of Tomato
Processing and Utilization of Sesame

Improved Cowpea Storage Using PICS Bags for Smallholder Farmers
Extension Guide on Enhancing Farm Labor Efficiency for Smallholder Farmers
Improve small ruminants production using home waste 

Improve local chicken production (Hausa version)
Farm record and accounting (Hausa version

Causes of farmers cooperative conflict and resolution (H/version)
Tomato processing, preservation and utilization in Nigeria Agricultural Market Information Sourcing and Use

Effective Agricultural Communication

Dabarun Noman Dankalin Hausa a Buhu (Hausa version)

 Dabarun wanke Iri (Hausa version)
Guide on how entre a community for extension delivery at initial stage 
How to organize rural youth clubs

Importance of modern beekeeping practices
Method of writing research report in Agricultural Extension Production, packaging and marketing of tomato powder

A Guide on Turmeric Production
A Guide on How to Make Cooled Press Coconut oil 
A Guide on How to Raise Tomatoes in Nursery Trays
Cowpea Storage Using PICS Bags for Small Holder Farmers Extension guide on labor efficiency 
Production of flour with higher fiber that will be very Vita for the diabetics and loss of weight
NAERLS Service Delivery Charter (Updated Edition 2026
Guide on the transportation of day old chicks during dry                          season period.  
Guide on fertilizer use for pepper production
 Guide on fertilizer application for tomatoes production
Production of Fluted Pumpkin (Telferia occidentalis) 
Formulating Rations with the Pearson Square
Performance Evaluation in Poultry Production
Guide on Nutrition and Feeding in Rabbit
Formulating Rations with the Pearson Square

 Performance Evaluation in Poultry Production

Cattle Milk Processing


Guide on Nutrition and Feeding in Rabbit

Guide on Breeding and Reproduction in Rabbit

Guide On Fodder Processing And Utilization

Healthy Animals Healthy Soils Better Harvests; A system Approach to Agriculture
Formulating Rations with the Pearson Square

Performance Evaluation in Poultry Production
Cattle Milk Processing


 Guide on Nutrition and Feeding in Rabbit
Guide on Breeding and Reproduction in Rabbit

Guide On Fodder Processing And Utilization
Healthy Animals Healthy Soils Better Harvests; A system Approach to Agriculture

Healthy Animals Healthy Soils Better Harvests; A system approach to agriculture
Formulating Rations with the Pearson Square

Performance Evaluation in Poultry Production
Cattle Milk Processing

Guide on Nutrition and Feeding in Rabbit
Guide on Breeding and Reproduction in Rabbit
Guide On Fodder Processing And Utilization
Healthy Animals Healthy Soils Better Harvests; A system Approach to Agriculture
Healthy Animals Healthy Soils Better Harvests; A system approach to agriculture
Formulating Rations with the Pearson Square
Performance Evaluation in Poultry Production

Cattle Milk Processing

Guide on Nutrition and Feeding in Rabbit
Guide on Breeding and Reproduction in Rabbit
Guide On Fodder Processing And Utilization

Healthy Animals Healthy Soils Better Harvests; A system Approach to Agriculture
	
	
	


D. RADIO PROGRAMMES

	SN
	Topic
	Channels/Station
	Duration 
	Language of communication
	Proposed number of airing 
	Collaborators

	1
	Assessing the suitability of various water sources for irrigation Purpose
 
	
	30 mins
	English

	
	

	2
	Management of Salt - affected soils in Agricultural land

	
	30 mins
	English and Hausa
	
	

	3
	Operation and Maintenance of Power Tiller Machine

	
	30 mins 
	English
	
	

	4
	General Maintenance of Rice Milling/Processing Machines and Equipment
	
	30 mins 
	English/Hausa
	
	

	5
	Sustainable Water harvesting practices

	
	30 min
	English/Hausa
	
	

	6
	Management of Salt –affected soils in irrigated land

	
	30 min
	English/Hausa
	
	

	7
	Essentials of tractor Operation and maintenance
	
	30 min
	English
	
	

	8
	Simple farm soil erosion control measured
	
	30 min
	English
	
	

	9
	Maintenance of Tractor, Implement and Field Operation
	
	30 min
	English
	
	

	10
	Irrigation water measurements system
	
	30 min
	English
	
	

	11
	The impact of excess tillage on the agricultural soil
	
	30 min
	English
	
	

	12
	Mu raya karkara (name of the programme) but the topics are  various aspects (crops, livestock, group dynamics and income generation).
	
	30 min
	Hausa/English
	
	Ashaka Cement

	13
	Challenges of Food Security in Nigeria




	
	30 min 


	English
	
	

	14
	The Effect of price fluctuation on food safety and security in Nigeria
	
	30 min
	English
	
	

	15
	The Effect of inflation on agricultural value chain in Nigeria
	
	30 min
	English
	
	

	16
	Commodity Market Prices
	
	30 min
	English
	
	

	17
	Planning and conducting farmers’ training

	
	20 min
	English
	
	

	18
	Introducing tomato powder to rural farmers for income generation 


	
	20 min
	English
	
	

	19
	Gender differences in access to extension services and Agricultural productivity.
	
	30 mins
	English
	
	

	20
	Effect of privatization of Agricultural extension services.
	
	30 min
	English
	
	

	21
	How to 

organizerural youth clubs


	
	20 min
	English
	
	

	22
	Yaddaakehada kungiyar matasa a karkara


	
	30 min 
	Hausa
	
	

	23
	The 5Cs of credit

 

	
	15 min
	English
	
	

	24
	ICTs and mobile applications for Agricultural development and productivity amongst small scale farmers in Nigeria.
	
	30 mins 
30 mins 
	English
English
	
	

	25
	 Cooperatives savings and loans


	
	20 mins 
	Hausa
	
	

	26
	Cooperatives savings and loans


	
	20 mins
	Hausa
	
	

	27
	Abubuwan dake kawo Rushewar kungiyoyin Manoma da Hanyoyin maganchesu 

	
	30 mins
	Hausa
	
	

	28
	Women Empowerment and Social Change in Agriculture


	
	30 mins
	Hausa/English
	
	

	29
	Formation and Management of farmers group 


	
	30 mins
	Hausa
	
	

	30
	How to facilitate the formation of young farmers’ club in schools . 
	
	30 mins 
	Hausa
	
	

	31
	How to enter  a community for extension delivery at initial stage
	
	30 mins 
	English
	
	

	32
	Insight From the Gender Unit.

	
	10 mins
	English
	
	

	33
	 Noman Zamani Radion Programme
	
	30 mins
	Hausa 
	52 episodes
	

	34
	Mu  raya karkara Radio Program


	
	30 mins
	Hausa
	52 episodes
	

	35
	 Baturen Gona

Language: Hausa




	
	30 min
	Hausa
	52 episodes
	

	36
	Effect of plant density on cowpea production


	
	30 mins 
	Hausa/English
	
	

	37
	Yadda ake zaben ingattaccen iri kafin shuka


	
	30 mins
	Hausa
	
	

	38
	 Nutrition and Utilization of plantain dish in health and Diseases


	
	30 mins
	English
	
	

	39
	Solar Food Processing and Cooking Methodologies
	
	30 mins 
	English
	
	

	40
	Smart storage keeping your fruits nd vegetables fresher for longer proper ways to store food and reduce spoilage 
	
	30 mins 
	English
	
	

	41
	Mahimmancin amfani da buhun zamani ajen ajiyar amfanin gona
	
	30 mins
	Hausa
	
	

	42
	 Super foods from your farm: what to eat for better health – nutrient-rich local foods like moringa, ginger, and beans


	
	30 mins
	English
	
	

	43
	 Mahimmancin wankin iri kafin shuka

 

	
	30 mins
	Hausa
	
	

	44
	Salon ajiyar albasa ta hanyar amfani da tafarnuwa
	
	30 mins
	Hausa
	
	

	45
	Nutritional knowledge and health practices for the elderly
	
	30 mins 
 
	English
	
	

	46
	 The right formulation of food for breakfast for an adult.


	
	30 mins 
	English
	
	

	47
	Foods for depression and anxiety


	
	30 mins
	English
	
	

	48
	Orange fleshed sweet potatoes in Nigeria: The New Gold
	
	30 mins 
	English
	
	

	49
	Weaner Rabbit Production and Fostering


	
	30 mins
	English
	One month
	

	50
	 Brooding Management in Poultry Production
	
	30 mins
	English
	
	

	51
	Radio Programme Proposed Palm 
	
	30 mins
	English
	
	

	52
	Oil Value, Nupe

Producer: 
	
	1hr 
	Nupe
	
	NSASDP/

MOKWA/Mo

	53
	Momordica balsamina (Garafuni) and its health benefits


	
	30 mins
	English
	
	


E. TELEVISION PROGRAMMES
	SN
	Topic
	Channels/Station
	Duration 
	Language of Communication 
	Duration
	Collaborators

	1
	Irrigation water measurements system

	
	30 mins 
	English
	
	

	2
	Good Agricultural Practices for Maize production
	
	30 mins
	Hausa
	
	

	3.
	Good Agricultural Practices for Rice production
	
	30 mins
	Hausa
	
	

	4.
	Good Agricultural Practices for Soybean production

	
	30 mins
	Hausa
	
	

	5
	Group formation and management
	
	30 mins 
	Hausa
	
	

	6
	Improve Small Ruminants production using home waste

	
	30 mins 
	Hausa
	
	

	7
	Campaign against misuse of agrochemicals among farmers in Nigeria

	
	30 mins 
	English
	
	

	8
	Empowering Women Farmers: Voices from the Field


	
	30 mins 
	Hausa
	Weekly
	

	9
	Momordica balsamina (Garafuni) and its health benefits


	
	30 mins
	English
	
	

	10
	Common Food allergies


	
	30 mins 
	Engish
	
	

	11
	Nutritional knowledge and health practices for the elderly


	
	30 mins 
	English
	
	

	12
	The Mission and Objectives of creating animal husbandry in Nigeria
	
	30 mins
	English
	
	

	13
	The Causes of Farmers and Herdsmen Crises and possible solutions


	
	30 mins 
	English
	
	

	14
	Processing of some Orange fleshed sweet potato (OFSP) product 
	
	30 mins 
	English
	
	

	15
	Green tea and their health benefits 

Presenter: 
	
	30 mins 
	English
	
	

	16
	Food insecurity: Ways to utilize the available food in a nutritive way.


	
	30 mins 
	English
	
	


F. TRAINING WORKSHOP
	SN
	Title
	Category of trainees
	No of trainees
	Collaborators
	Duration

	1
	Pre-season training on Maize, Rice and Soybeans
	Adopted Village farmers of Giwa, S/gari and Zaria LGAs, Kaduna State.
	
	Giwa, S/gari and Zaria LGAs, Kaduna State.
	

	2
	Sensitization training on Maize, Rice, Millet, G/nut and Soybean Production
	Farmers from Ashaka and Mai-ganga communities.
	
	Ashaka and Mai-ganga communities.
	

	3
	Training on Income Generation (Value addition to crops
	Adopted Village farmers
	
	FT&E Programme
	

	4
	Applying ChatGPT for Content Creation and Knowledge Sharing in Agricultural Extension
	
	
	
	

	5
	How flywheel coupled with spring and alternator generate electricity for irrigation purposes.
	
	
	
	

	6
	Hands On  Training on Camera Operations
	Farm Broadcast TV Producers
	
	
	

	7
	Audio editing and programmes production



	Staff of Farm Broadcast Radio & TV Producers
	
	
	

	8
	Script Writing Techniques



	Participants: Staff farm Broadcast Radio & TV Producers
	
	
	

	9
	Skill acquisition and business planning on household and domestic products for women.




	Participants: Women in Sabon gari and Giwa Local Government Areas.
	
	Collaborators: Sabon gari and Giwa Local Governments.
	

	10
	Home processing of tomato puree for unemployed youths in Zaria Local Government.


.
	Women in Zaria Local  Government Areas.
	
	Zaria Local  Government Areas.
	

	11
	Confectionary Making Using Vitamin A Cassava and Orange Fleshed Sweet potato.


	Participants: Retired Women in Sabon gari Local Government.
	
	Collaborators: NGO, Sabon gari Local Government.
	

	12
	Training on Home Making for Young Married Women in Samaru.



 
	Participants: Young Married Women
	
	Collaborators: Rahama Girl Child & Women Empowerment, Kano Nigeria
	

	13
	Using hot stone to cut down high cost of cooking.

             
	          ParticipantSabongari Women group.


	
	Collaborators. Sabongari Women group.
	

	14
	Analytical Decision Making

	Participants: Gender Unit members
	
	
	

	15
	Leadership and Stakeholder Management

	Participants: Gender Unit members
	
	
	

	16
	Dynamic Group Management and Gender Mainstreaming

	 Participants: Gender Unit members
	
	
	

	17
	Resource Mobilization/ Proposal Writing and Grants Management
	Participants: Gender Unit members
	
	
	

	18
	Project Monitoring and Evaluation
	Participants Gender Unit members
	
	
	

	19
	Data Management and Analysis
	Participants: Gender Unit members
	
	
	

	20
	A.I Fundamentals and Applications in Agriculture


	ParticipantsNAERLS Staff         
	
	
	

	21
	Understanding AI-Driven Decision Support Systems for Agricultural Extension 


	ParticipantsNAERLS Staff.
	
	
	

	22


	Full Adoption & utilization of  The Developed  Adopted Village & School Outreach Database Management Application  

	Participants: Adopted Village & School Outreach  Unit
	
	
	

	23
	Training for Extension Advisors and farmers on egg processing and marketing  
Role: To be Facilitated by Livestock and Fishery programme unit (NAERLS) 


	No. participants:  100 Selected farmers chosen from across Sabon Gari Local government
	
	
	

	24
	Training for butchers/meat processors on ethical meat handling practices and marketing 

	Participant 100 Selected farmers chosen from across Sabon Gari Local government.
	
	
	

	25


	Training for the dairy producers/processors on milk value chain
	
	
	
	

	26
	Adoption  & Utilization of The Developed Commodity Prices Software.
	ParticipantsCommodity Prices Commodity & AEED Department(NAERLS
	
	
	

	28
	Fiber optic cable Network maintenance 
	Participants: NAERLS ICT Unit Staff (Network Section)
	
	Collaborators: NIS (Network and Information Systems) ABU, Zaria
	

	32
	 Email Etiquette in Work Place 
	Participants: NAERLS Staff
	
	
	

	34
	Poultry Production as a business at Yerwa Girls Secondary Schools, Maiduguri.
	   Participants: North East Zonal Office Staff
	
	             Collaborators: YGSS Maiduguri
	

	35
	Utilization of crop residues in ruminant feeding
	
	
	
	

	26
	Good Agricultural Practices on the major staple crops in the NWZ
	        Participants: NAERLS NWZO Staff, IT Students, interested staff from IAR, ICRIST, IITA
	
	Collaborators: IAR, ICRIST, IITA
	

	37
	Induction training and inauguration of NAERLS Servicom unit staff
	 Participants: Servicom unit staff
	
	Collaborators: SERVICOM Office             , Ahmadu Bello University, Zaria
	

	37
	Improving Organizational Performance and Service Delivery in NAERLS
	ParticipantsAll NAERLS staff and Zonal officers
	
	Collaborators: SERVICOM Office, Ahmadu Bello University, Zaria
	

	38
	Enhancing interdepartmental collaboration
	ParticipantsAll NAERLS Staff
	
	Collaborators: SERVICOM National Directorate Abuja
	

	40
	Customer Service and Feedback Management
	ParticipantsNAERLS help tline and Administrative Staff
	
	
	

	41
	Enhancing Staff Ethics and Accountability
	ParticipantsAll Senior and Junior Staff of NAERLS.
	
	Collaborators: ABU SERVICOM
	

	42
	Enhancing service delivery through data analysis and Evaluation
	Participants All NAERLS Servicom staff and Zonal officers
	
	Collaborators: SERVICOM Office, Ahmadu Bello University, Zaria and 
	

	43
	Servicom Annual International Conference      
	Participants Executive Director, Deputy Director, and Servicom Unit Head
	
	            collaborators: Servicom  Head Office Abuja, NAERLS A.B.U  Zaria  
	

	44
	Understanding SERVICOM Principles for Institutional Excellence
	ParticipantsNAERLS staffs


	
	
	

	45
	Monitoring and Evaluation of Service Delivery in Research Institutes
	Participants NAERLS Unit Heads, Monitoring         Officers and Programme leaders
	
	
	

	46
	Production and Packaging of Locally Processed Spaghetti in Zogarawa and Danhassan adopted villages (NWZ)
	Participants30 Women from the selected adopted villages in NWZ
	
	           Collaborators: Zogarawa and Danhassan adopted villages (NWZ)
	

	47
	Household Nutrition and Food Safety Practices
	Participants 25 (women leaders, youth, and IT students)
	
	Collaborators: Ministry of Women Affairs, Kano ADP
	

	48
	Basic tools for Effective Presentation in Extension
	No. of participant

Staff of NAERLS southeast zone/NRCRI/ ADP
	
	Collaborators: ADPs, NRCRI
	

	49
	Ideal technique for effective vaccination in poultry production.
	participants Adopted village farmers/ ADPs
	
	Collaborators: ADPs, NRCRI
	

	50
	Tomatoes production in humid tropical ecology of Nigeria
	
	
	
	

	
	Pepper production in humid tropical ecology of Nigeria
	Participants: Farmers and ADPs
	
	
	

	54
	Formulation of balance poultry diets with local feed ingredients
	
	
	     
	

	55
	Effect of rural banditry on the livelihood activities of the rural dweller
	Participants Staff/ADP/Adopted village farmers
	
	     
	

	56
	Basic tools for Effective Presentation in Extension
	Participants Staff of NAERLS southeast zone/NRCRI/ ADP
	
	 Collaborators: ADPs, NRCRI Ps, NRCRI
	

	57
	Ideal technique for effective vaccination in poultry production
	Participants Adopted village farmers/ ADPs
	
	Collaborators: ADPs, NRCRI Ps, NRCRI
	

	58
	Tomatoes production in humid tropical ecology of Nigeria
	Participants Farmers and ADPs
	
	ADPS ,NAERLS 
	

	59

60

61

62

63

64

65

66


	Ideal technique for effective vaccination in poultry  production. 
Pepper production in humid tropical ecology of Nigeria
Utilization of non-conventional fertilizer use in crop  
Production: Case study of Florahumus organic fertilizer
The Dynamics of Participatory Communication in Agricultural  Development.
Growing food crops in bags. Examples tubers and vegetables.
Significance of fertilizer use to enhanced productivity by small holder farmers in NAERLS Adopted Villages in Rivers


State
Use of Information and Communication Technology (ICT) in Agricultural Extension Service delivery in Rivers State
Significance of soil management practices for improved crop yield   of selected crops.
societies, Community base NGO
Sponsor: NAERLS/ABU Zaria.

	Participants Adopted village farmers/ ADPs

Participant:    ADP, State Ministry of Agric/AFAN River State Chapter
Participant:    Adopted Village Farmers
Participant:   ADP Staffs/AFAN
	
	Collaborators: ADPs, NRCRI

Collaborators:  NAERLS SOUTH-SOUTH ZONE

	


G.    ADOPTED VILLAGES AND SECONDARY SCHOOLS ACTIVITIES

	SN
	Activities
	No. Proposed
	Target Audience
	Technologies to be Promoted
	Remarks

	1
	 Mu raya karkara (Radio  programme) 
Duration: 30 minutes


	
	Mostly Hausa and in some cases English

	
	

	4
	TV Programme 

Topic:1  Good Agricultural Practices for Maize production
Duration:30 minutes
Topic 2: Good Agricultural Practices for Rice production
Duration:30 minute

Topic3 : Good Agricultural Practices for Soybean production
Duration:30 minutes

Topic 4: Group formation and management
Duration:30 minutes
Topic 5: Improve Small Ruminants production using home waste
Duration:30 minutes
	5
	Hausa speaking audience 
	Good Agronomic practices 
	

	
	Total Adopted Villages
	52
	
	
	

	
	New adopted villages
	03
	
	
	

	6
	New groups to be formed
	15
	
	
	

	7
	New groups to be trained
	11
	
	
	

	8
	Demo plots
	12
	
	
	


[image: image61.jpg]


                                                                                                                                             [image: image62.png]



Name of Research Institute: National Institute for Freshwater Fisheries Research, New Bussa

Postal Address: P.M.B. 6006

Website:www.niffrng.org                           E-mail: niffish@gmail.com , contact@niffr.gov.ng

Telephone: 08063093027

A.   EXTENSION SUPPORT ACTIVITIES

	SN
	Title
	Proposed No 
	Proposed Date
	Collaborating Institute
	Remarks

	1
	Diagnostic survey
	2
	March 
	Kwara State government 
	

	2
	On-Station Research (OSR)
	4
	Jan- oct. 
	-
	

	3
	OFR
	5
	Jan- oct. 
	Private fish farm
	

	4
	MTRM
	12
	Jan- Dec
	ADPs
	

	5
	Joint Scientific Field Evaluation
	1
	August 
	ARMTI 
	

	6
	Field days
	2
	July & Dec
	Stakeholders 
	

	7
	Zonal REFILS Workshop
	4 
	Quarterly
	Stakeholders 
	

	8
	Pre-season training
	1
	March 
	Stakeholders 
	

	9
	Post-season training
	1
	November 
	Stakeholders 
	

	10
	Zonal Steering Committee Meeting
	2
	Jan & oct
	Stakeholders 
	

	11
	Zonal Technical Committee Meeting
	4
	Quarterly 
	Stakeholders 
	

	12
	In-house Review Meeting/Cropping Scheme Meeting
	5
	
	Stakeholders 
	

	13
	National Agricultural Extension Review and Planning Meeting (NAERPM)
	1
	November 
	Stakeholders 
	

	14
	Adopted Village to be established
	3
	Jan – Nov. 
	Village Heads
	

	15
	Training Workshop (To Organize)
	4
	Quarterly 
	ATA global 
	

	16
	Training Workshop (To attend) 
	4
	Jan- Dec
	Stakeholders 
	

	17
	Trade Fair
	1
	August 
	
	

	18
	Research Institute Field day
	1
	August 
	
	

	19
	World food day
	1
	October 
	
	

	20
	Wet season evaluation
	1
	July 
	
	

	21
	Dry season evaluation
	1
	February 
	
	

	22
	National Agric. Shows, State, NGOs and others
	1
	October 
	
	


B.    TECHNOLOGY DEVELOPMENT

	S/No
	Technology to be Developed within the Year Under Review 
	Level of Preparedness (%)
	Month to be Released
	Target Audience
	Expected Output/Outcome

	1
	Motorized Atala gear 
	90
	May 
	Fishermen
	Efficiency 

	2
	Fingerling counting machine
	90
	June  
	Fish farmers
	    Efficiency  

	4
	A  monitoring device  for  fish dryer
	         50 
	   August 
	Fish processor
	Hygienic fish for export

	5
	Multi-sensing device for monitoring water quality
	50
	 August 
	Fish farmers 
	Improved productivity

	6 
	Fingerling sorting machine
	         50
	April 
	Fish farmers
	Easy sampling


C. EXTENSION PUBLICATIONS
	SN
	Title
	Target Copies
	Expected Month of Completion 
	Collaborators

	1
	Bulletins

Fish feed formulation

handling fish inland water 
	200

200
	October /November

October /November
	

	2
	Guides

 1.management of homestead fish pond

2.precautions for good water quality management in fish ponds

3. fertilizer application in fish ponds

4. prevention of losses in stored dried fish

5.feeding practices in fish farming

6.species combination and stocking density in fish ponds
	200

200

200

200

200

200
	May /June

July /August

April/May

March /April

October /November

September/October


	

	3
	Leaflets

1. control of some common diseases in fish pond

2. integrated rice cum fish farming
	200

200
	October /November

October /November
	

	4
	Posters

1. control of some common disease in fish pond
	200
	October /November
	

	5
	Others (Specify)

1. 

2
	Nil 
	Nil 
	


D. RADIO PROGRAMMES
	SN
	Proposed Titles
	Channels/Station
	Duration 
	Proposed number to be aired 
	Collaborators

	1
	Fish farming and types of farming practices
	ARCN  FM & Bida FM
	1month
	  Once a week
	ARCN

	2
	Best practices in fisheries & aquaculture
	ARCN FM & Bida FM
	1 month
	Once a week
	

	3
	Fish feed formulation for culture fish
	ARCN FM & Bida FM
	1 month
	Once a week
	

	4
	Water quality parameters in fish farming
	ARCN FM & Bida FM
	1month
	Once a week
	

	5
	Hatchery management practices
	ARCN FM & Bida FM
	1month
	Once a week
	

	6
	Fish processing techniques 
	ARCN FM & Bida FM
	1month
	Once a week
	

	 7
	Fisheries cooperatives
	ARCN FM & Bida FM
	1month
	Once a week
	


E. TELEVISION PROGRAMMES

	SN
	Proposed Titles
	Channels/Station
	Duration 
	Proposed number to be aired 
	Collaborators

	1
	Documentary on aquaculture activities
	NTA/ NYSC
	1 month
	    4
	


F. TRAINING WORKSHOP
	SN
	Title
	Category of trainees
	No of trainees
	Collaborators
	Duration

	1
	Capacity building and empowerment training for youth and women  
	Youth & women
	50 
	ATA global
	1 week

	2
	Capacity building and empowerment training for youth in fish processing & value addition 
	Youth 
	100
	HYPPADEC
	3months

	3
	Training on fish feed formulation & production
	Fish farmers
	50
	NIFFR
	1 week

	5
	Entrepreneurship skills in fish processing, preservation, value addition & quality control
	Intending fish processors

Fish processors
	80
	NIFFR
	1 week

	6
	Training on fish pond construction techniques
	Artisans
	50
	  NIFFR
	3-days


G.    ADOPTED VILLAGES AND SECONDARY SCHOOLS ACTIVITIES
	SN
	Activities
	No. Proposed
	Target Audience
	Technologies to be Promoted
	Remarks

	1
	Stocking of ponds
	5
	Youth , women & students  
	Fish farming
	

	2
	Fish processing &value addition
	5
	Youth , women & students
	Fish dryer
	

	3
	Formation of new adopted villages & Schools
	3
	Youth , women & students
	Fish farming
	

	4
	Renovations pond faciltiies in adopted villages & schools
	5
	
	Fish farming & processing
	

	5
	Introduction of all male tilapia, modern smoking dryers
	5
	
	Fish farming & processing
	

	6
	Training on fish farm management practices
	5
	
	Fish farming & processing
	

	7
	Alternative income generating activities
	5
	fisherfolk
	
	


Name of Contact Person: Dr. Toyin Olowosegun
Post/Rank: Director/ HOD (Research Outreach) Phone Number: 08055362948, 08036328919

[image: image63.jpg]


                                                                                                                              [image: image64.png]



Name of Research Institute: NATIONAL CEREALS RESEARCH INSTITUTE           

BADEGGI NIGER STATE

Postal Address: P.M.B. 8 Bida Niger State

Website: www.ncribadeggi.org.ng                    E-mail: ncribadeggi15@yahoo.com ncribadeggi@gmail.com  infor@ncribadeggi.org.ng   








SUPPORT ACTIVITIES

	SN
	Title
	No Proposed
	Date Proposed
	Collaborating Institute
	Remarks

	1
	Diagnostic survey
	1
	
	
	

	2
	On-Station Research (OSR)
	2
	
	
	

	3
	OFR
	5
	
	
	

	4
	MTRM
	96
	
	
	

	5
	Joint Scientific Field Evaluation
	1
	
	
	

	6
	Field days
	10
	
	
	

	7
	Zonal REFILS Workshop
	1
	
	
	

	8
	Pre-post season training
	8
	
	
	

	9
	Zonal Steering Committee Meeting
	4
	
	
	

	10
	In-house Review Meeting/Cropping Scheme
	1
	
	
	

	11
	Zonal Technical Committee Meeting
	2
	
	
	

	12
	National Agricultural Extension Review and Planning Meeting (NAERPM)
	1
	
	
	

	13
	Adopted Village
	1
	
	
	

	14
	Training Workshop (To Organize)
	10
	
	
	

	
	Training Workshop (To attend) 
	5
	
	
	

	15
	Trade Fair
	6
	
	
	

	16
	Research Institute Field day
	10
	
	
	

	17
	World food day
	1
	
	
	

	18
	Wet & dry season evaluation
	-
	
	
	

	19
	National Agric. Shows/others, state, NGOs
	1
	
	
	


B.    TECHNOLOGY DEVELOPMENT

	S/No
	Technology Developed within the Review Year 
	Level of Preparedness (%)
	Month of Release
	Target Audience
	Expected Output/Outcome

	1
	New rice varieties
	95
	
	Rice farmers and private sector
	10t/ha 

	2
	New Acha varieties
	90
	
	Farmers and private sector
	High yielding (3 t/ha)

	3
	New soybean variety
	95
	
	Farmers and private sector
	Climate resilient variety and high yielding

	4
	New Beniseed variety
	95
	
	Farmers and private sector
	High yielding, abiotic stress.

	5
	
	
	
	
	

	6
	
	
	
	
	


C. EXTENSION PUBLICATIONS
	SN
	Title
	Target Copies
	Expected Month of Completion 
	Collaborators

	1
	Bulletins

1. NCRI newsletters
	1000
	Quarterly
	-

	2
	Guides

1. Extension guides on all the institutes mandate crops
	1000 each
	June 2026
	-

	3
	Leaflets

1.  rice pest and diseases

2. seed production
	1000

1000

1000
	March 2026

March 2026

March 2026
	


D. RADIO PROGRAMMES
	SN
	Topic
	Channels/Station
	Duration 
	Proposed number of airing 
	Collaborators

	1
	Agric panoramma
	Power FM Bida 100.5 
	30min
	52
	Radio Nigeria

	2
	Agric quiz
	Power FM Bida 100.5
	60min
	2
	Radio Nigeria and National Assembly


E. TELEVISION PROGRAMMES
	SN
	Topic
	Channels/Station
	Duration 
	Proposed number of airing 
	Collaborators

	1
	Documentary on NCRI
	NSTV, NTA Bida and Minna
	1 hour
	6
	NTA, NSTV,ADPs and Farmers in the NCZ


F. TRAINING WORKSHOP
	SN
	Title
	Category of trainees
	No of trainees
	Collaborators
	Duration

	1
	Pre-season Training for rice Farmers
	 Youth women and adults
	100
	FMAFS
	5 days

	2
	
	
	
	
	


G.    ADOPTED VILLAGES AND SECONDARY SCHOOLS ACTIVITIES
	SN
	Activities
	No. Proposed
	Target Audience
	Technologies to be Promoted
	Remarks

	1
	Demonstration on GAP for rice
	3
	Farmers and private sector
	FARO 71 &FARO 72

 
	NEW VARIETIES

	2
	Demonstration on GAP for Soybean
	3
	Farmers and private sector
	NCRISOY 5M
	NEW VARIETIES


Name of Contact Person: Dr. Habib Abubakar Ndagi

Post/Rank: Chief Research Officer/Zonal REFILS Coordinator (NCZ) 

Phone Number: 08062707390

Name of Research Institute: Nigerian Institute for Oil Palm Research (NIFOR)
Postal Address: P.M.B. 1030, Benin City, Edo State

Website:                                            

E-mail: info@nifor.org

Telephone: 08068012422

A.   EXTENSION SUPPORT ACTIVITIES

	SN
	Title
	Proposed No 
	Proposed Date
	Collaborating Institute
	Remarks

	1
	Diagnostic survey
	1
	April
	ADPs
	

	2
	On-Station Research (OSR)
	1
	March
	ADPs
	

	3
	OFR
	1
	June-August
	ADPs
	

	4
	MTRM
	12
	January-December
	ADPs
	

	5
	Joint Scientific Field Evaluation
	1
	July
	ADPs, FMAFS, MANR 
	

	6
	Field days
	1
	February
	ADPs, FMAFS
	

	7
	Zonal REFILS Workshop
	1
	March
	ADPs,  IAR&T, MANR 
	

	8
	Pre-season training
	1
	January
	ADPs, OPGAN, NACOPPMAN
	

	9
	Post-season training
	1
	September
	ADPs, OPGAN, NACOPPMAN
	

	10
	Zonal Steering Committee Meeting
	4
	March, June, September, December 
	ADPs, NARIs, UNIVERSITIE, INPUT AGENCIES, FMAFS, FARMERS ORGANIZATION 
	

	11
	Zonal Technical Committee Meeting
	1
	April
	NARIs, MANR, FMAFS, UNIVERSITIES, INPUT AGENCIES, FARMERS ORGANIZATIONS, ADPs 
	

	12
	In-house Review Meeting/Cropping Scheme Meeting
	1
	October
	ADPs, NARIs,  UNIVERSITIES, INPUT AGENCIES, FMAFS, FARMERS ORGANIZATION 
	

	13
	National Agricultural Extension Review and Planning Meeting (NAERPM)
	1
	November
	NEARLS
	

	14
	Adopted Village to be established
	2
	May, June, July, August, October, December
	ADP
	

	15
	Training Workshop (To Organize)
	3
	April, September, November
	OPGAN, NPPAN, ADP, NACOPPMAN
	

	16
	Training Workshop (To attend) 
	-
	-
	-
	-

	17
	Trade Fair
	1
	December
	MANR, OPGAN, NPPAN, RRIN, FMAFS 
	

	18
	Research Institute Field day
	1
	June
	NARIS, ADPs, MANR 
	

	19
	World food day
	1
	October
	FMAFS
	

	20
	Wet season evaluation
	1
	August/September
	NAERLS, ADPs 
	

	21
	Dry season evaluation
	1
	November
	ADPs
	

	22
	National Agric. Shows, State, NGOs and others
	1
	November
	FMAFS
	


B.    TECHNOLOGY DEVELOPMENT

	S/No
	Technology to be Developed within the Year Under Review 
	Level of Preparedness (%)
	Month to be Released
	Target Audience
	Expected Output/Outcome

	1
	Mechanical Shredder
	100
	December
	Farmers/processors of oil palm and coconut
	Increase productivity, increase numbers of shredded fresh fruit bunches, increase income


C. EXTENSION PUBLICATIONS
	SN
	Title
	Target Copies
	Expected Month of Completion 
	Collaborators

	5
	Others (Manuals)

1. Oil palm production 
2. Coconut production 
3. Small scale processing equipment 
4. Date palm production

5. Shea butter production
	500

1000

1000

1000

1000
	February

February

June

September

September
	-

-

-

-

-


D. RADIO PROGRAMMES
	SN
	Proposed Titles
	Channels/Station
	Duration 
	Proposed number to be aired 
	Collaborators

	1
	Make we farm
	101.5/ Radio Ng FM
	15 minutes
	6
	OPGAN, NACOPPMAN

	2
	Food matters
	96.9/ Speed FM 
	15 minutes
	6
	OPGAN, NACOPPMAN

	Etc.
	
	
	
	
	


E. TELEVISION PROGRAMMES

	SN
	Proposed Titles
	Channels/Station
	Duration 
	Proposed number to be aired 
	Collaborators

	1
	Farming hints
	95.7/ EBS
	15 Minutes
	12
	-

	2
	
	
	
	
	


F. TRAINING WORKSHOP
	SN
	Title
	Category of trainees
	No of trainees
	Collaborators
	Duration

	1
	Nursery establishment and management techniques for oil palm 
	Oil palm field supervisors,  Youth 
	200
	-
	5 days

	2
	Operation & Maintenance of NIFOR SSPE 
	Fabricators & Oil palm field supervisors 
	100
	-
	5 days

	3
	Oil palm harvesting techniques
	Oil palm harvesters, oil palm growers/ supervisors
	50
	-
	5 days

	4
	Coconut Nursery establishment, field development, harvesting, processing and marketing 
	Coconut Farmers/Harvesters/ Processors/ Marketers 
	150
	-
	5 days

	5
	Techniques for Effective Plantation Management in the Palm Industry 
	Oil palm field supervisors
	100
	-
	5 days

	6
	Packaging and Storage of Palm oil 
	Processors, Farmers groups, cooperatives, Entrepreneurs and Interested Members of the Public 
	100
	-
	5 days


G.    ADOPTED VILLAGES AND SECONDARY SCHOOLS ACTIVITIES

	SN
	Activities
	No. Proposed
	Target Audience
	Technologies to be Promoted
	Remarks

	1
	Establishment of oil palm nursery 
	2
	Oil palm farmers/ students
	Tenera (NIFOR Extension Work Seeds) 
	

	2
	Oil palm processing
	2
	Oil palm farmers/processors and students
	NIFOR developed Small Scale Processing Equipment
	


Name of Contact Person: Dr Lucky Igene

Post/Rank: Head, Extension Division/ Chief Research Officer

Phone Number: 08068012422

[image: image65.jpg]


                                                                                            [image: image66.jpg]FEDERAL GOVERNMENT OF

NIGERIA




Name of Research Institute: Nigerian Stored Products Research Institute
Postal Address: KM 3 Asa Dam Road Ilorin, Kwara State

Website: https://www.nspri.gov.ng          E-mail: nspriheadquarters@yahoo.com

Telephone: 
08117767204


A.   EXTENSION SUPPORT ACTIVITIES

	SN
	Title
	No Proposed
	Date Proposed
	Collaborating Institute
	Remarks

	1
	Diagnostic survey
	20
	January- December 2026
	FAMAN
	

	2
	On-Station Research (OSR)
	12
	January- December 2026
	ADPs
	

	3
	OFR
	NA
	
	
	

	4
	MTRM
	12
	January- December 2026
	ADPs, CATFAN, FAMAN
	

	5
	Joint Scientific Field Evaluation
	6
	January- December 2026
	Relevant Stakeholders
	

	6
	Field days
	3
	January- December 2026
	FAMAN
	

	7
	Zonal REFILS Workshop
	3
	As updated by the Zone
	Zonal REFILS
	

	8
	Pre-post season training
	NA
	
	
	

	9
	Zonal Steering Committee Meeting
	NA
	
	
	

	10
	In-house Review Meeting/Cropping Scheme
	1
	October 2026
	Relevant Stakeholders
	

	11
	Zonal Technical Committee Meeting
	NA
	
	
	

	12
	National Agricultural Extension Review and Planning Meeting (NAERPM)
	1
	November 2026
	
	

	13
	Adopted Village
	24
	January- December 2026
	Relevant Stakeholders
	

	14
	Training Workshop (To Organize)
	6
	As updated by the Zone
	Relevant Stakeholders
	

	
	Training Workshop (To attend) 
	6
	As updated by the Zone
	Relevant Stakeholders
	

	15
	Trade Fair
	1
	As updated by the Zone
	Relevant Stakeholders
	

	16
	Research Institute Field day
	1
	As updated by the Zone
	NARIs
	

	17
	World food day
	1
	As updated by the Zone
	Relevant Stakeholders
	

	18
	Wet & dry season evaluation
	NA
	
	
	

	19
	National Agric. Shows/others, state, NGOs
	3
	As updated by the Zone
	Relevant Stakeholders
	


B.    TECHNOLOGY DEVELOPMENT

	S/No
	Technology Developed within the Review Year 
	Level of Preparedness (%)
	Month of Release
	Target Audience
	Expected Output/Outcome

	1
	Solar Powered Cooling System
	50
	June 2026
	Farmers’ Markets
	Reduced loss of fruits and vegetables

	2
	Pelleted Bio pesticides
	
	
	
	


	SN
	Title
	Target Copies
	Expected Month of Completion 
	Collaborators

	1
	Bulletins

1. Postharvest news
	2000
	June 2026
	NAERLS

	2
	Guides

1. Postharvest Management of Pests of Perishable Agricultural Products
2. Postharvest Management of Pests of Durable Agricultural Products
	2000
	June 2026
	NAERLS

	3
	Leaflets

1. Advisory leaflet on application of bio pesticides
	1000
	June 2026
	NAERLS

	4
	Posters

1. Diagrammatic description of tomato paste processing 

2. Diagrammatic description of odorless fufu processing
	2000
	June 2026
	NAERLS

	5
	Others (Specify)

1. Mitigating the effect of COVID-19 on Smallholder farmer through the use of Postharvest Technologies as incentives
	1000
	June 2026
	NAERLS


D. RADIO PROGRAMMES
	SN
	Topic
	Channels/Station
	Duration 
	Proposed number of airing 
	Collaborators

	1
	NA
	
	
	
	

	2
	NA
	
	
	
	


E. TELEVISION PROGRAMMES
	SN
	Topic
	Channels/Station
	Duration 
	Proposed number of airing 
	Collaborators

	1
	NA
	
	
	
	

	2
	NA
	
	
	
	


F. TRAINING WORKSHOP
	SN
	Title
	Category of trainees
	No of trainees
	Collaborators
	Duration

	1
	Entrepreneurship training for NYSC on postharvest value addition
	Corp Members
	240
	NYSC
	5days

	2
	Step down training of ADP Staff postharvest pests managements
	ADP Staff
	240
	ADP
	5days


G.    ADOPTED VILLAGES AND SECONDARY SCHOOLS ACTIVITIES
	SN
	Activities
	No. Proposed
	Target Audience
	Technologies to be Promoted
	Remarks

	1
	Empowerment and training on postharvest value addition
	25
	Youths and Women
	Modified Ice Fish Box, fish smoking kiln, silos, parabolic solar dryers
	

	2
	Technology Distribution to rural women
	25
	Women
	Modified Ice Fish Box, fish smoking kiln, silos, parabolic solar dryers
	


Name of Contact Person: Dr Atibioke O. A.

Post/Rank: Assistant Director (Research)

Phone Number: 08030671659

[image: image67.jpg]


                                                                                                                          [image: image68.jpg]



Name of Research Institute: NATIONAL HORTICULTURAL RESEARCH INSTITUTE (NIHORT)
Postal Address: PMB 5432, Idi-Ishin, Jericho, Ibadan

Website:   www.nihort.org                                                           E-mail: info@nihort.gov.ng

Telephone: 

A.   EXTENSION SUPPORT ACTIVITIES

	SN
	Title
	Proposed No 
	Proposed Date
	Collaborating Institute
	Remarks

	1
	Diagnostic survey
	15
	April - December 2026
	
	

	2
	On-Station Research (OSR)
	20
	April - December 2026
	
	

	3
	OFR
	9
	April - December 2026
	
	

	4
	MTRM
	6
	April - December 2026
	South west Agricultural Development Programme/Authority
	

	5
	Joint Scientific Field Evaluation
	6
	April - December 2026
	
	

	6
	Field days
	2
	April - December 2026
	
	

	7
	Zonal REFILS Workshop
	1
	FEB. 2026
	
	

	8
	Pre-season training
	1
	FEB. 2026
	
	

	9
	Post-season training
	1
	
	
	

	10
	Zonal Steering Committee Meeting
	1
	NOT YET FIXED
	
	

	11
	Zonal Technical Committee Meeting
	1
	NOT YET FIXED
	
	

	12
	In-house Review Meeting/Cropping Scheme Meeting
	3
	NOT YET FIXED
	
	

	13
	National Agricultural Extension Review and Planning Meeting (NAERPM)
	1
	DEC., 2026
	
	

	14
	Adopted Village to be established
	2
	April - December 2026
	
	

	15
	Training Workshop (To Organize)
	20
	April - December 2026
	
	

	16
	Training Workshop (To attend) 
	2
	April - December 2026
	

	17
	Trade Fair
	6
	April - December 2026
	South west states 
	

	18
	Research Institute Field day
	2
	April - December 2026
	
	

	19
	World food day
	1
	April - December 2026
	
	

	20
	Wet season evaluation
	1
	April - December 2026
	
	

	21
	Dry season evaluation
	1
	April - December 2026
	
	

	22
	National Agric. Shows, State, NGOs and others
	4
	April - December 2026
	
	


B.    TECHNOLOGY DEVELOPMENT

	S/No
	Technology to be Developed within the Year Under Review 
	Level of Preparedness (%)
	Month to be Released
	Target Audience
	Expected Output/Outcome

	1
	Onion
	95.0%
	
	Farmers, Entrepreneurs, Students, Youths
	Increased yield and productivity;

Extended shelf-life;

Enhanced flavor and nutritional attributes;

Climate- resilient varieties that are able to withstand extreme weather conditions

	2
	Egusi melon
	60.0%
	
	Farmers, Entrepreneurs, Students, Youths
	Increased yield and productivity;

Improved taste;

Extended shelf-life;

Enhanced flavor and nutritional attributes;

Superior quality;

Climate- resilient varieties that are able to withstand extreme weather conditions

	3
	Garden Egg
	      75.0%
	
	Farmers, Entrepreneurs, Students, Youths
	Early maturity;

Increased yield and productivity;

Disease tolerance;

Extended shelf-life;

Enhanced flavor and nutritional attributes;

Climate- resilient varieties that are able to withstand extreme weather conditions

	4
	Tomato
	      90.0%
	
	Farmers, Entrepreneurs, Students, Youths
	Heat tolerance;

Early maturity;

Increased yield and productivity;

Climate- resilient variety that can withstand extreme weather conditions

	5
	Plantain 
	 95.0%
	
	Farmers, Entrepreneurs, Students, Youths
	Increased yield and productivity;

Fruit size and quality.

	6
	Sweet pepper
	20.0%
	
	Farmers, Entrepreneurs, Students, Youths
	Early maturity;

Increased yield and productivity;

Adaptation to field conditions;

Extended shelf-life;

Enhanced flavor and nutritional attributes;

Climate- resilient varieties that are able to withstand extreme weather conditions


C. EXTENSION PUBLICATIONS
	SN
	Title
	Target Copies
	Expected Month of Completion 
	Collaborators

	1
	Bulletins

1. Guide to Post Harvest Handling and Processing of citrus

2.

3.

4.

5.
	500 
	Dec, 2025
	

	2
	Guides

1. Production Guide for HORTITOM 4 and HORTITOM 5

2. Production Guide for HORTIPEP 1 and HORTIPEP 2

3.

4.
	1,000

1,000


	July, 2026

July, 2026
	

	3
	Leaflets

1. 

2.

3.

4.

5.
	
	
	

	4
	Posters

1. Posters on NIHORT Institutional Seminar programmes 

2.

3.

4.

5.
	12
	Jan. – Dec. 2026
	

	5
	Others 

1.Fliers for radio programme

2.NIHORT Newsletter


	39

2


	39

2


	


D. RADIO PROGRAMMES

	SN
	Proposed Titles
	Channels/Station
	Duration 
	Proposed number to be aired 
	Collaborators

	1
	Agbe Loba
	93.5FM
	30 minutes
	39
	-   -

	2
	
	
	
	
	

	Etc.
	
	
	
	
	


E. TELEVISION PROGRAMMES

	SN
	Proposed Titles
	Channels/Station
	Duration 
	Proposed number to be aired 
	Collaborators

	1
	Special Television Broadcast
	NTA Ibadan
	30 minutes
	5
	-

	2
	
	
	
	
	

	Etc.
	
	
	
	
	


F. TRAINING WORKSHOP
	SN
	Title
	Category of trainees
	No of trainees
	Collaborators
	Duration

	1
	Principles of Beekeeping for Profitable Honey Production
	Potential bee farmers, existing bee farmers, Farmers, Students, Food processors
	
	- -
	3 days

	2
	Mango Juice Production
	Youths, Small scale Processors, students, women
	
	- -
	3 days

	3
	Mushroom Production Technology 

An Easy Way to wealth
	Farmers, students, Food processors, Agricultural Entrepreneurs
	
	- -
	3 days

	4
	Ginger and Turmeric Cultivation for wealth creation
	Farmers, Civil servants, Students, Youths, Men, Women
	
	- -
	3 days

	5
	Principles and Practice of Citrus Production
	Farmers, Civil servants, Students, Youths, Men, Women
	
	- -
	3 days

	6
	Plant Tissue Culture Techniques
	Students, Researchers, Lecturers, Post graduate students, Agric. Technologists, Laboratory technologists
	
	- -
	3 days

	7
	Introduction to Molecular Techniques in Agriculture
	Students, Researchers, Lecturers, Post graduate students, Agric. Technologists, Laboratory technologists
	
	- -
	3 days

	8
	Orange Juice Production
	Farmers, Civil servants, Students, Youths, Men, Women
	
	- -
	3 days

	9
	Green House Production Techniques for Horticultural Crops
	Students, Researchers, Lecturers, Post graduate students, Agric. Technologists, Laboratory technologists
	
	- -
	3 days

	10
	Mushroom Production Technology
	Farmers, Civil servants, Students, Youths, Men, Women
	
	- -
	3 days

	11
	Intensive Training on Spawn Multiplication
	Farmers, Civil servants, Students, Youths, Men, Women
	
	- -
	3 days

	12
	Green House Cultivation Techniques for Horticultural Crops
	Students, Researchers, Lecturers, Post graduate students, Agric. Technologists, Laboratory technologists
	
	- -
	3 days

	13
	Production and Management of Exotic Vegetables  (Cucumber and Lettuce
	Farmers, Civil servants, Students, Youths, Men, Women
	
	- -
	3 days

	14
	Dry Season Vegetable Production
	Farmers, Civil servants, Students, Youths, Men, Women
	
	- -
	3 days

	15
	Curbing Waste in Plantain/Banana value addition
	Farmers, Civil servants, Students, Youths, Men, Women
	
	- -
	3 days

	16
	Pineapple Juice Production
	Farmers, Civil servants, Students, Youths, Men, Women
	
	- -
	3 days

	17
	Improved Practices of Mango Production
	Farmers, Civil servants, Students, Youths, Men, Women
	
	- -
	3 days

	18
	Tomato: Turning waste into Wealth through Value Addition
	Farmers, Civil servants, Students, Youths, Men, Women
	
	- -
	3 days

	19
	Principles and Practice of Pineapple Production
	Farmers, Civil servants, Students, Youths, Men, Women
	
	- -
	3 days

	20
	Principles and Practice of Beekeeping for Profitable Honey Production
	Potential bee farmers, existing bee farmers, Farmers, Students, Food processors
	
	- -
	3 days


G.    ADOPTED VILLAGES AND SECONDARY SCHOOLS ACTIVITIES
	SN
	Activities
	No. Proposed
	Target Audience
	Technologies to be Promoted
	Remarks

	1
	Promotion of Fruits and Vegetables for food security and nutrition
	30
	All NIHORT adopted schools, adopted villages and communities around NIHORT
	Promotion of urban horticulture;

Rapid multiplication technique in Plantain/Banana, Pineapple, citrus, mango;

Grafting techniques for mango seedlings;

High density orchard establishment;

Integrated weed management;

Integrated nutrient management in fruits and vegetables;

Integrated pest and disease management in fruits and vegetables;

Mulching methods for growth and productivity of guava, soursop amongst others.
	


Name of Contact Person: Dr. Oluyemisi M. ADEWALE

Post/Rank: Assist. Director (Research)/ Head Extension Programme 

Phone Number: 07054057515

                                       ADP 2026 WORKPLAN

STATE

Abia

Adamawa

Akwa Ibom 

Anambra 

Bauchi 

Bayelsa 

Benue 

Cross 

River 

Delta 

Ebonyi

Edo

 Ekiti 

Enugu 

FCT

Gombe 

Imo 

Jigawa 

Katsina 

Kebbi 

Kogi 

Lagos 

Nassarawa

 Niger

 Ogun

 Ondo 

Osun 

Plateau 

Sokoto 

Taraba 

Yobe 

Zamfara

Name of ADP: ABIA
Postal address: 

Email:




                Telephone_______________________

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	

	2
	FNTs
	24
	

	3
	OFARs
	5
	

	4
	No. of Farm Families
	650,000
	

	5
	No. of SPATs established 
	1120
	

	6
	No. of MTPs
	112
	

	7
	No. of Field days
	22
	

	8
	No. of Agric Shows
	2
	

	9
	No. of group formed
	70
	

	10
	No. of Pre-season training per year
	6
	

	11
	No. of Post-season training per year
	6
	

	12
	Extension publications to be produced (No. of Titles)
	
	

	
	Bulletins 
	2
	

	
	Guides
	2
	

	
	Leaflets
	2
	

	
	Posters
	2
	

	
	Others
	2
	

	13
	Zonal Steering Committee Meeting
	4
	

	14
	Zonal Technical Committee Meeting
	4
	

	15
	Zonal REFILS workshops
	1
	

	16
	No of Extension Workers (VEAs)
	280
	

	17
	No of Extension workers (BESs)
	38
	

	18
	EA/Farmer ratio in the state
	1:800
	


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins

1. Extension Bulletin on Poultry production

2.Extension bulletin on Orange flesh, sweet potato

3.

4.

5.


	500

500
	ABIA ADP

ABIA ADP

	2
	Guides

1. Extension Guide on fall Army worm infestation on maize

2. Extension Guide on Die-back Disease of cassava 

3.

4.

5.
	500

500
	NIL

NIL

	3
	Leaflets

1.  Extension Posters 

2.

3.

4.
	200
	NIL


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2

3

4

5
	NIL


	NIL
	NIL
	NIL


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 

2. 

3.

4.

5.
	NIL
	NIL
	NIL
	NIL


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1

2
	Training of women and youths on processing, preservation and utilization of agricultural product

Seed yam multiplication 


	ABIA ADP
	Women 

Youths 
	1st – 2nd Quarter 
	ABIA ADP


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	Cassava/Maize/Sweet potato
	NRCRI, Umudike
	

	2
	Cassava/Maize/Telfairia
	NRCRI, Umudike
	

	3
	Yam minisett/Maize f6 coupea
	NRCRI, Umudike
	

	4
	Poultry production
	NRCRI, Umudike
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	CSS-Trained Farmers
	2024
	Ongoing 
	Fisheries

	2
	Project 
	
	
	Poultry agro-processing, cassava

	3
	
	
	
	

	4
	
	
	
	

	5
	
	
	
	

	6
	
	
	
	

	7
	
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Ministry of Agriculture is in charge 

	2
	Credit
	Ministry of Agriculture is in charge

	3
	Agro-chemical
	Available in the open market but costly 

	4
	Tractor/Animal Traction
	Ministry of Agriculture is in charge

	5
	MTRM/QTRM situation Report 
	MTRM has not held this year due to lack of funding


Name of ADP: Adamawa Agricultural Development Programme 

Postal address: P.O.BOX 956 Yola

Email:
adamawaadp@gmail.com



                

Telephone 07037679978

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	

	2
	FNTs
	26
	

	3
	OFARs
	42
	

	4
	No. of Farm Families
	530,000
	

	5
	No. of SPATs established 
	1210
	

	6
	No. of MTPs
	46
	

	7
	No. of Field days
	1256
	

	8
	No. of Agric Shows
	4
	

	9
	No. of group formed
	100
	

	10
	No. of Pre-season training per year
	1
	

	11
	No. of Post-season training per year
	1
	

	12
	Extension publications to be produced (No. of Titles)
	
	

	
	Bulletins 
	
	

	
	Guides
	
	

	
	Leaflets
	
	

	
	Posters
	
	

	
	Others
	
	

	13
	Zonal Steering Committee Meeting
	
	

	14
	Zonal Technical Committee Meeting
	
	

	15
	Zonal REFILS workshops
	1
	

	16
	No of Extension Workers (VEAs)
	536
	

	17
	No of Extension workers (BESs)
	46
	

	18
	EA/Farmer ratio in the state
	1:800
	


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins

1. 

2.

3.

4.

5.


	
	

	2
	Guides

1. 

2.

3.

4.

5.
	
	

	3
	Leaflets

1. 

2.

3.

4.

5.
	
	


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2

3

4

5
	Agric Digest 

Hadari Malafan Duniya 

Noma tushen arziki 

Ina Matasa 


	FM 90.5

FM 91.1

FM 101.5

89.9
	Usaku

Gotel 

Fombina 

NAS
	45min

1hour 

1hour

1hour 


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 

2. 

3.

4.

5.
	Mu koma gona 
	ATV
	ATV Yola
	1 hour


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1

2

3

4

5
	Pre- season 

In- season 

Post harvest 

Dry season 

Processing and market linkages 


	FAO

ADAS

FMARD

UNDP

SCL
	EAs

Farmers

Leaders 

N- Agro

Stake holders 
	March -April 

June- August 

Sept -Oct

Dec- Feb.


	ADP

FAO

SCL

FMARD 

CRS


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	Use and handling of aflasate 
	
	Reduce effect of afflotoxin 

	2
	Bio pesticide formulation 
	
	Environmentally friendly 

	3
	Fertilizer micro dozing 
	
	Climate smart

	4
	Composting 
	
	Soil conservation and nutrition 

	5
	Water shed(half moon) and zai
	
	Water harvesting 


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	FAO
	2007
	Ongoing 
	Humanitarian, Developmental, and Advisory services 

	2
	WOFAN
	2023
	Ongoing 
	Humanitarian Developmental and Advisory services 

	3
	SCL (Project juri)
	2023
	Ongoing 
	Humanitarian, Developmental and Advisory services 

	4
	OXFARM
	2016
	6years 
	Humanitarian Developmental and Advisory services 

	5
	GIZ
	2018
	5years 
	Farmer Field school Farmer business school 

	6
	UNDP
	2019
	Ongoing 
	Humanitarian Developmental and Advisory services 

	7
	
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Barn on the procurement of urea fertilizer 

	2
	Credit
	Loan to farmers by financial institutions and ADAS

	3
	Agro-chemical
	More adulteration in the open market, High cost of chemicals as a result of fuel subsidy removal 

	4
	Tractor/Animal Traction
	Inadequate number of tractors to farmers in the state 

	5
	MTRM/QTRM situation Report 
	No funding 


Name of ADP: AKWA IBOM STATE AGRICULTURAL DEVELOPMENT PROGRAMME (AKADEP)

Postal address: MBIAOBONG ETOI, P.M.B 1089, UYO

Email:
akadep@gmail.com



Telephone_______________________

A. 2026 EXTENSION WORK PLAN 
	S/N
	SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	

	2
	FNTs
	26
	

	3
	OFARs
	5
	

	4
	No of Farm Families
	685,095
	

	5
	No of SPATs established 
	2115
	

	6
	No of MTPs
	94
	

	7
	No of Field days
	94
	

	8
	No of Agric Shows
	2
	

	9
	No of group formed
	376
	

	10
	No of Pre-season training per year 
	1
	

	11
	No. of post-season training 
	1
	

	12
	Extension publication produce (No. of Titles)
	
	

	
	Bulletins
	2,000
	

	
	Guides 
	1,000
	

	
	Leaflets
	1,000
	

	
	Posters 
	1,000
	

	
	Others (specify)
	
	

	13
	Zonal Steering Committee Meeting
	4
	

	14
	Zonal Technical Committee Meeting
	2
	

	15
	Zonal REFILS workshops
	4
	

	16
	No of Extension Workers (VEAs)
	274
	We are hopeful that government will employ more extension staff and deploy them to ADP

	17
	No of Extension workers (BESs)
	31
	

	18
	EA/Farmer ratio in the state
	1:2500
	


B. DETAILS OF EXTENSION PUBLICATIONS PRODUCED 

	S/N
	Title
	Target
	Collaborators

	1
	Bulletins

1. Crops 

2. Fisheries 

3. Livestock 

4. Agrofroestry

5. Processing 


	2000
	

	2
	Guides

1. Crops 

2. Fisheries 

3. Livestock 

4. Agrofroestry

5. Processing 
	1000
	

	3
	Leaflets

1. Crops 

2. Fisheries 

3. Livestock 

4. Agrofroestry

5. Processing 
	1000
	

	4
	Leaflets

1. Crops 

2. Fisheries 

3. Livestock 

4. Agrofroestry

5. Processing
	1000
	

	5
	Others (specify)


	
	


C: RADIO PROGRAMMES PRODUCED AND AIRED 

	S/N
	Programme Title/Topics
	Frequency of airing (e.g Weekly)
	Broadcasting station
	Duration

	1.


	Topics on crop, fisheries, livestock, agroforestry and processing will be presented in a unified manner 


	2 times a week
	Akwa Ibom State radio station (AKBC) and other private radio stations 
	1hr


D. TELEVISION PROGRAMMES PRODUCED AND AIRED 
	S/N
	Programme Title/Topics
	Frequency of airing (e.g Weekly)
	Broadcasting station
	Duration

	1.


	Topics on Crops, 

Fisheries,  

Livestock 

Agrofroestry 

Processing to be presented in a unified manner 


	Once a week
	State owned television station AKBC
	15min.


E. TRAINING PROGRAMMES

	S/N
	Title
	Organizers
	Categories of Trainees
	Date of Training
	Collaborators 

	
	Processing of orange Fresh Potatoes into confectionaries for bread making 
	ADP
	Youth and Women
	March
	

	
	Processing of fish feed using local raw materials
	ADP
	Youth
	February
	Uniuyo



	
	Processing of poultry feed using available local materials 
	ADP
	Ext agents and farmers
	December
	

	
	Artificial brooding of Local chicks
	ADP
	Farmers
	January - December
	

	
	Training on the identification of symptoms, management and prevention of Brown streak viral disease in cassava 
	ADP
	Ext. agent and farmers
	January – December
	WAVE, NCRI


F. TECHNOLOGIES TO BE PROMOTED

	S/N
	Title
	Source 
	Comment

	
	Cultivation of tomato 
	FMARD, NSPRI
	

	
	Production of yam flour
	FMARD, NSPRI
	

	
	Effective drying and packaging of fish
	NSPRI
	

	
	Utilization of Orange flesh potato OFSP fin baking
	FMARD
	

	
	Management of soil resources for increased yield 
	NISS
	

	
	Yam minisett production
	REFILS
	

	
	Swamp Rice Production 
	REFILS 
	

	
	Pig fattening
	SHELF
	

	
	Beekeeping technology
	REFIL, NCRI
	

	
	Cultivation of forest vegetable e.g., Gnetum 
	REFIL
	

	
	Processing of cocoyam into confectioneries 
	REFIL, NCRI
	


Name of ADP: Anambra ADP

Postal address: 

E Email: maduabuchisachi@gmail.com
Telephone: 08039366162, 08037725172

judenwankwo@rocketmail.com 

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	To be supported by special projects 

	2
	FNTs
	26
	To be funded by ASADEP and Min. of Agriculture.

	3
	OFARs
	10
	To be funded by research in institutions

	4
	No. of Farm Families
	700,000
	This is no. of farm families in the state.

	5
	No. of SPATs established 
	
	MTPs are being emphasized.

	6
	No. of MTPs
	600
	To be established by EAs and special projects 

	7
	No. of Field days
	48
	One per Extension Agent 

	8
	No. of Agric Shows
	2
	To be funded by State Govt. 

	9
	No. of group formed
	600
	To be funded by special projects.

	10
	No. of Pre-season training per year
	1
	To be funded by special projects.

	11
	No. of Post-season training per year
	1
	To be funded by special projects.

	12
	Extension publications to be produced (No. of Titles)
	
	

	
	Bulletins 
	12 (ASADEP HERAID)
	To be funded by ASADEP 

	
	Guides
	1000
	To be funded by special projects. 

	
	Leaflets
	1000
	To be funded by special projects.

	
	Posters
	1000
	To be funded by special projects.

	
	Others
	
	

	13
	Zonal Steering Committee Meeting
	1
	ADP, NAERLS and stakeholders to help 

	14
	Zonal Technical Committee Meeting
	1
	ADP, NAERLS and stakeholders to help

	15
	Zonal REFILS workshops
	1
	ADP, NAERLS and stakeholders to help

	16
	No of Extension Workers (VEAs)
	177
	More Extension officers to be recruited 

	17
	No of Extension workers (BESs)
	21
	Govt. to employ Extension Officers 

	18
	EA/Farmer ratio in the state
	1:1000
	More EAs to be recruited to maintain the ratio.


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins

1.  ASADEP   HERALD

2.

3.

4.

5.


	12
	ADP will assist 

	2
	Guides

GAPs of crops, livestock, fishery etc, regenerative farming.

2.

3.

4.

5.
	1000
	Special projects to assist  

	3
	Leaflets

GAPs of crops, livestock, fishery etc, regenerative farming.

2.

3.

4.

5.
	1000
	Special projects to assist  


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2

3

4

5
	GAPs on Rice, Cassava, Yam production  and Regenerative farming. 


	Once a week 
	ABS  88.5FM
	1hr


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 

2. 

3.

4.

5.
	
	
	
	


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1

2

3


	Preseason/post season trainings.

Capacity building to Extension Officers in the State.

Value chain addition
	ADP/VCDP/ NAERLS

ADP, Special projects

ADP/Special projects
	Farmers/Extension Officers

Extension Officers

Extension Officers


	Feb. – April

Preseason

April – Aug.

Aug.-Nov. 
	ADP, NAERLS

ADP/NCAM/ARMTI

ARMTI, ADP, IITA


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	Cocoyam die back control 
	MOA/ADP
	Cocoyam production is going extinct due to dieback  

	2
	Popularization of regenerative Agriculture
	ADP/MOA
	To produce healthier foods

	3
	Popularization of Economic Frees 
	ADP/MOA
	To boast economy of farmers


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	
	
	
	

	2
	
	
	
	

	3
	
	
	
	

	4
	
	
	
	

	5
	
	
	
	

	6
	
	
	
	

	7
	
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Govt. should subsidize fertilizer and also promote organic farming.

	2
	Credit
	More credit facilities should be provided for farmers.

	3
	Agro-chemical
	This should be made affordable to farmers also organic farming promoted.

	4
	Tractor/Animal Traction
	More tractors should be provided and land made more tractorable.

	5
	MTRM/QTRM situation Report 
	ADP should be funded adequately by Research Institutes and Special Projects. 


Name of ADP: Bauchi ADP

Postal address: PMB 0050, Dass Road, Bauchi

Email:
bauchistateadp2@gmail.com



                Telephone_______________________

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	

	2
	FNTs
	28
	

	3
	OFARs
	150
	

	4
	No. of Farm Families
	3,250,000
	

	5
	No. of SPATs established 
	
	

	6
	No. of MTPs
	5000
	

	7
	No. of Field days
	24
	

	8
	No. of Agric Shows
	1
	

	9
	No. of group formed
	250
	

	10
	No. of Pre-season training per year
	1
	

	11
	No. of Post-season training per year
	1
	

	12
	Extension publications to be produced (No. of Titles)
	
	

	
	Bulletins 
	10,000
	

	
	Guides
	15,000
	

	
	Leaflets
	20,000
	

	
	Posters
	500
	

	
	Others
	
	

	13
	Zonal Steering Committee Meeting
	4
	

	14
	Zonal Technical Committee Meeting
	4
	

	15
	Zonal REFILS workshops
	1
	

	16
	No of Extension Workers (VEAs)
	1,500
	

	17
	No of Extension workers (BESs)
	50
	

	18
	EA/Farmer ratio in the state
	1:6500
	


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins

1. Guide to cereals production 

2. Guide to Legumes production  

3.

4.

5.


	
	

	2
	Guides

1. post-harvest and storage 

2.

3.

4.

5.
	
	

	3
	Leaflets

1. Guide to Poultry production 

2. Small Ruminant management

3.

4.

5.
	
	


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2

3

4

5
	Akoma Gona

Noma da Raya Karkara


	52 weeks

52 weeks
	BRC 2 

Albarka Radio
	30 Mins.

30 Mins.


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 

2. 

3.

4.

5.
	Akoma Gona

Noma Tushen Arziki


	52 weeks

52 weeks
	NTA Bauchi

BATV
	30 Mins.

30 Mins.


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	
	Staff capacity building on the use of ICT
	BSADP
	EAs/Enumerators


	2026
	ATBU

	
	Training of extension Agents and farmers on Good Agronomic practices on cereals and legumes 
	BSADP
	Extension Agents & Farmers 
	2026 
	

	
	Training of farmers and extension agents on prevention and control of poultry diseases and parasite 
	BSADP
	Extension Agents & Farmers 
	2026 
	Ministry of Livestock Development (L-PRES)

	
	Capacity Building of farmers on small ruminant production and management  
	BSADP
	Extension Agents & Farmers 
	2026 
	L-PRES

	
	Pre season training Dry season 
	BSADP
	Extension Agents & Farmers 
	2026 
	

	
	Pre season training 
	BSADP
	Extension Agents & Farmers 
	2026 
	

	
	Pre season training (Enumerators) 
	BSADP
	Extension Agents & Farmers 
	2026 
	

	
	Training of women group and youths on Fish production 
	BSADP
	Extension Agents & Farmers 
	2026 
	

	
	Training of women on processing and utilization of Soybeans, orange flesh potatoes and ginger   
	BSADP
	Extension Agents & Farmers 
	2026 
	

	
	Capacity building of extension agents on soil fertility and management 
	BSADP
	Extension Agents & Farmers 
	2026 
	SOIL Value/OCP

	
	Training of farmers and extension agents on climate smart  agriculture 
	BSADP
	Extension Agents & Farmers 
	2026 
	TOURBA

	
	Training on production of economic trees 
	BSADP
	Extension Agents & Farmers 
	2026 
	ACReSAL 

	
	Training of students on establishment of School gardening and orchard  
	BSADP
	Students 
	2026
	UNICEF 


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	Promotion of E-Extension
	BSADP
	

	2
	Use of combine harvester and reaper for rice harvest 
	BSADP
	

	3
	Use of planters, power tillers to reduce drudgery during farm operations   
	BSADP
	

	4
	Promotion of new improved variety of seeds 
	IITA, IAR, LCRI, ICRISAT and NASC
	

	5
	Promotion of improved breeds of poultry (Noiler birds) and small ruminants (Fat tail rams)
	Amo Farms Ibadan, Open Markets Yobe state
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	Agro-climatic Resilience in Semi-Arid landscape (ACReSAL)
	2022
	5 Years
	Community Climate resilience-

Community investment

Community strengthening

	2
	Livestock Productivity and Resilience Support Project (L-PRES)
	2023
	5 years
	Improving livestock productivity and commercialization.

(iii) Supporting Livestock Producer Organizations  and other value chain operators to improve their performance and for promoting inclusive and resilience supply chains.  

	3
	Small Holder Horticulture Empowerment and Promotion (SHEP)
	2022
	Years
	1. Market linkage to vegetable farmers

2. Capacity building on vegetable production and marketing 

	4
	Soil Value Project

 
	2025
	10 Years
	Improving soil fertility

Maximum utilization of water shed in the state

	5
	OCP Africa
	2024
	5 Years
	Improving soil fertility

Soil fertility test

Promoting use of appropriate fertilizer.

	6.
	Women Farmers Advancement Network (WOFAN)
	2024
	10 years 
	Support and empowerment to women groups, Youth and people with special needs.

	
	
	
	
	


Name of ADP: BENUE

Postal address: 

Email:




                Telephone_______________________

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs/QTRM
	4
	If funded

	2
	FNTs
	12
	”

	3
	OFARs
	7
	”

	4
	No. of Farm Families
	1,225,564
	”

	5
	No. of SPATs established 
	270
	”

	6
	No. of MTPs
	270
	”

	7
	No. of Field days
	47
	”

	8
	No. of Agric Shows
	2
	”

	9
	No. of group formed
	270
	”

	10
	No. of Pre-season training per year
	1
	”

	11
	No. of Post-season training per year
	1
	”

	12
	Extension publications to be produced (No. of Titles)
	
	”

	
	Bulletins 
	2000
	If funded

	
	Guides
	
	

	
	Leaflets
	
	

	
	Posters
	50
	”

	
	Others
	
	

	13
	Zonal Steering Committee Meeting
	1
	”

	14
	Zonal Technical Committee Meeting
	1
	”

	15
	Zonal REFILS workshops
	1
	”

	16
	No of Extension Workers (VEAs)
	2,115
	Each block 45 EA

	17
	No of Extension workers (BESs)
	47
	

	18
	EA/Farmer ratio in the state
	
	


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins

1. Innovative indoor farming in all season

2. Organic pest management/soil Health

3.

4.

5.


	1000

1000
	Donor agencies

Donor agencies

	2
	Guides

1. 

2.

3.

4.

5.
	
	

	3
	Leaflets

1. 

2.

3.

4.

5.
	
	


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2

3

4

5
	Tom sule/good farming

Update on farming activities


	Monthly

”
	Radio Benue

”
	One hour

One hour


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 

2. 

3.

4.

5.
	Tom sule/good farming

Update on farming activities


	Monthly

”
	Alia TV

”
	One hour

One hour


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1

2

3

4

5
	Innovative indoor farming in all season

Organic pest management/soil Health


	
	
	
	


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	Regenerative Agriculture
	Sasakawa/SHEP
	Scale up

	2
	Market oriented Agriculture
	SHEP
	Scale up

	3
	Torba Carbon farming
	Tourba
	Scale up

	4
	e-Extension
	Digital green virtual Agronomy
	Scale up


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	Tourba Carbon farming
	2025
	5
	

	2
	Sasakawa Africa
	2024
	5
	TOT/Demonstrations

	3
	WOFAN/Palm valley
	2022
	5
	TOT/Empowerment

	4
	Heifer International
	2022
	5
	TOT/Input mechanics

	5
	Extension Africa
	2022
	5
	TOT/System rice later

	6
	
	
	
	

	7
	
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	500 trucks of assorted fertilizer

	2
	Credit
	[image: image156.png]




	3
	Agro-chemical
	1.5 Billion Naira worth of Agrochemicals

	4
	Tractor/Animal Traction
	1000 Tractors

	5
	MTRM/QTRM situation Report 
	Number 4 planned for 2026


Name of ADP: BORNO

Postal address: 

Email:




                Telephone_______________________

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	

	2
	FNTs
	24
	

	3
	OFARs
	30
	

	4
	No. of Farm Families
	470,000
	

	5
	No. of SPATs established 
	24
	

	6
	No. of MTPs
	8
	

	7
	No. of Field days
	50
	

	8
	No. of Agric Shows
	2
	

	9
	No. of group formed
	20
	

	10
	No. of Pre-season training per year
	2
	

	11
	No. of Post-season training per year
	
	

	12
	Extension publications to be produced (No. of Titles)
	6000
	

	
	Bulletins 
	1000
	

	
	Guides
	1000
	

	
	Leaflets
	2000
	

	
	Posters
	2000
	

	
	Others
	
	

	13
	Zonal Steering Committee Meeting
	2
	

	14
	Zonal Technical Committee Meeting
	4
	

	15
	Zonal REFILS workshops
	2
	

	16
	No of Extension Workers (VEAs)
	500
	

	17
	No of Extension workers (BESs)
	60
	

	18
	EA/Farmer ratio in the state
	
	


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins

1. 

2.NIL

3.

4.

5.


	NIL
	NIL

	2
	Guides

1. 

2.NIL

3.

4.

5.
	nlNIL
	NIL

	3
	Leaflets

1. NIL

2.

3.

4.

5.
	NIL
	NIL


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2

3

4

5
	FILIN MANOMA= (Hausa programme)

Paraskuram  barewuye= ( kanuri programme)
	Once in a week

Once a week
	BRTV

BRTV
	45 mins

45 mins


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 

2. 

3.

4.

5.
	NOMA TUSHEN ARZIKI

BACK TO FARM
	Once in  a week

Once in a week
	BRTV

BRTV
	45 min

1 hr




E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1

2

3

4

5
	INTERGRATED PEST MANAGEMENT ( IPM)

Small ruminant upgrading

CLIMATE SMART AGRICULTURE
	BOSADP

L-PRES

BOSADP
	Ext, workers &

Local govt. desk officers

Livestock ext. agents, livestock superintendents’

Local govt. agric staff and VEAs 


	3 days

3 days

2 days
	ICRC

BOSADP

WFP


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	
	
	

	2
	SHEP
	SHEP
	

	3
	
	
	

	4
	
	
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	FADAMA NG-CARE
	2023
	4 yrs
	Livelihood, irrigation activity & infrastructure

	2
	L-PRES
	2024
	5 yrs
	Livestock improvement

	3
	CSDP
	2023
	5 yrs
	Community social development, provision of portable water

	4
	RAAMP- [ RURAL ACCESS AGRICULTURAL MARKETING PROJECT]
	2026
	4 yrs
	Create Market linkages & strengthening rural infrastructure 

	5
	SAPZ, [SPECIAL AGRO-PROCESSING ZONE]
	2026
	4 yrs
	Agro processing

	6
	
	
	
	

	7
	
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Available in the Open Market, but expensive

	2
	Credit
	No special agricultural credit

	3
	Agro-chemical
	Available in agro shops

	4
	Tractor/Animal Traction
	State and Local Government own

	5
	MTRM/QTRM situation Report 
	Inadequate funds 


                                                                                            

Name of ADP: Cross River
Postal address: P.M.B 1178
Email:
cradpcalabar@gmail.com



              Telephone: 08064219782

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	

	2
	FNTs
	26
	

	3
	OFARs
	5
	

	4
	No. of Farm Families
	-
	

	5
	No. of SPATs established 
	Nil
	

	6
	No. of MTPs
	225
	

	7
	No. of Field days
	4
	

	8
	No. of Agric Shows
	2
	

	9
	No. of group formed
	225
	

	10
	No. of Pre-season training per year
	2
	

	11
	No. of Post-season training per year
	2
	

	12
	Extension publications to be produced (No. of Titles)
	
	

	
	Bulletins 
	500
	

	
	Guides
	500
	

	
	Leaflets
	500
	

	
	Posters
	500
	

	
	Others
	-
	

	13
	Zonal Steering Committee Meeting
	2
	

	14
	Zonal Technical Committee Meeting
	2
	

	15
	Zonal REFILS workshops
	1
	

	16
	No of Extension Workers (VEAs)
	144
	

	17
	No of Extension workers (BESs)
	18
	

	18
	EA/Farmer ratio in the state
	1:1000
	


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins

1. Climate Smart Farming

.


	1000
	FAO/SAPZ/LIFE-ND

	2
	Guides

1. Soil Testing: A must do for increase crop production

.
	1000
	Project Grow/CRADP

	3
	Leaflets

1. Fall Army Worms (FAW), Prevention and Control.

.
	1000
	Project Grow


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1


	FARMERS CORNER


	FORTNIGHTLY
	CRBC/HIT FM
	30 minutes


D. TELEVISION PROGRAMMES TO BE PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 


	FARMERS CORNER
	FORTNIGHTLY 
	CRBC/HIT FM
	1 HOUR


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1


	Monthly Technology Review Meeting (MTRM)


	CRADP


	ZMs, ZEOs, SMSs, Sub prog.Heads


	March


	FAO/LIFE-ND/CRADP



	
	Pre-season training
	CRADP
	Extension personnel
	May, 2026
	FAO/NIFOR

	
	Post – season training
	CRADP
	Extension Personnel
	Nov,2026
	FAO/NIFOR


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	Pod Borer Resistant Cowpea Cultivation
	IAR&T
	Already planted as foundation seeds. 

	2
	Rapid Cassava Stem Multiplication
	NRCRI
	To encourage adoption

	3
	Climate Smart Agriculture Practices (CSAP)
	FAO/USAID FTF
	Encourage mitigation approaches

	4
	Good Agronomic Practices (GAP)
	FAO
	Continuous promotion of GAP


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	PROJECT GROW
	2023
	6 Years
	Creating opportunities for farmers access to credit and markets.

	2
	SAPZ Program
	2024
	5Years
	 Production of Crops to feed processing hubs.

	3
	IFAD LIFE-ND Project (Additional Financing) 
	2020
	3Years
	Identifies enterprises that guarantees quick ways of making money called Quick Wins


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Though Fertilizer is costly in the open market, government is still proposing to distribute more fertilizers through the states to the farmers.

	2
	Credit
	It is always difficult for farmers to access credit from banks but Project Grow is guaranteeing access to credit

	3
	Agro-chemical
	High cost of Agrochemicals at the open market poses hindrances to farmers making progress.

	4
	Tractor/Animal Traction
	The state government intends to procure more for distribution to farmer cooperatives.

	5
	MTRM/QTRM situation Report 
	We are assured that FAO will continue to support MTRM.

	6
	Improved Seeds
	Apart from the Cowpea procured by the State Ministry of Agric for farmers, the farmers also renew their seeds from Premier seeds.



Name of ADP:
DELTA AGRICULTURE AND RURAL DEVELOPMENT 

AUTHORITY (DARDA)

Postal Address:
P.M.B. 1006, Ibusa, Delta State.


Email:

mamodeogboru@gmail.com





Telephone:
08032711644, 07038485500

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	

	2
	FNTs
	24
	

	3
	OFARs
	6
	

	4
	No. of Farm Families
	545,987
	

	5
	No. of SPATs established 
	-
	

	6
	No. of MTPs
	125
	

	7
	No. of Field days
	25
	

	8
	No. of Agric Shows
	2
	

	9
	No. of group formed
	200
	

	10
	No. of Pre-season training per year
	1
	

	11
	No. of Post-season training per year
	1
	

	12
	Extension publications to be produced (No. of Titles)
	12
	

	
	Bulletins 
	3
	

	
	Guides
	3
	

	
	Leaflets
	3
	

	
	Posters
	2
	

	
	Others
	1
	

	13
	Zonal Steering Committee Meeting
	4
	

	14
	Zonal Technical Committee Meeting
	-
	

	15
	Zonal REFILS workshops
	1
	

	16
	No of Extension Workers (VEAs)
	200
	

	17
	No of Extension workers (BESs)
	25
	

	18
	EA/Farmer ratio in the state
	1:1000
	


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins

Planting improved varieties of vegetables (Tomato, Pumpkin, Watermelon, Cucumber)

Most impactful practices in Maize Cultivation

Most impactful practices in Aquaculture production
	12,500

12,500

12,500
	FMARD

USAID Extension Activity

USAID Extension Activity

	2
	Guides

.

Planting improved varieties of vegetables (Tomato, Pumpkin, Watermelon, Cucumber)

Most impactful practices in Maize Cultivation

Most impactful practices in Aquaculture production
	12,500

12,500

12,500
	FMARD

USAID Extension Activity

USAID Extension Activity

	3
	Leaflets

Planting improved varieties of vegetables (Tomato, Pumpkin, Watermelon, Cucumber)

Most impactful practices in Maize Cultivation

      3. Most impactful practices in         Aquaculture production
	12,500

12,500

12,500
	FMARD

USAID Extension Activity

USAID Extension Activity


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1


	Army worm control in maize
	1 per week
	Radio Delta, Warri and Asaba
	30mins

	2


	Improved rice processing techniques
	1 per week
	Radio Delta, Warri and Asaba
	30mins

	3
	Seed treatment before planting
	1 per week
	Radio Delta, Warri and Asaba
	30mins

	4
	Production of cassava flour
	1 per week
	Radio Delta, Warri and Asaba
	30mins

	5
	Insect pest control in root and tuber crops
	1 per week
	Radio Delta, Warri and Asaba
	30mins

	6
	Crop storage and preservation
	1 per week
	Radio Delta, Warri and Asaba
	30mins

	7
	Common pest and diseases of vegetable crops and their control
	1 per week
	Radio Delta, Warri and Asaba
	30mins

	8
	PBR Cowpea production
	1 per week
	Radio Delta, Warri and Asaba
	30mins

	9
	Bee keeping
	1 per week
	Radio Delta, Warri and Asaba
	30mins

	10
	Production and utilization of compost manure
	1 per week
	Radio Delta, Warri and Asaba
	30mins


D. 

	1
	Proper vaccination regime in poultry
	1 per week
	DBS Asaba & DRTV Warri
	30mins

	2
	Pineapple juice production
	1 per week
	DBS Asaba & DRTV Warri
	30mins

	3
	Cowpea threshing and storage
	1 per week
	DBS Asaba & DRTV Warri
	30mins

	4
	Improved rice processing techniques
	1 per week
	DBS Asaba & DRTV Warri
	30mins

	5
	Fish hatching technology
	1 per week
	DBS Asaba & DRTV Warri
	30mins

	6
	Proper lining and establishment of oil palm
	1 per week
	DBS Asaba & DRTV Warri
	30mins

	7
	Hybrid maize production
	1 per week
	DBS Asaba & DRTV Warri
	30mins

	8
	Fish feed formulation
	1 per week
	DBS Asaba & DRTV Warri
	30mins

	9
	Fish processing using charcoal energy source
	1 per week
	DBS Asaba & DRTV Warri
	30mins

	10
	Improved plantain and banana production
	1 per week
	DBS Asaba & DRTV Warri
	30mins

	11
	Best Agronomic Practices for PBRC
	1 per week
	DBS Asaba & DRTV Warri
	30mins


E. TRAINING PROGRAMMES

	S/N
	Title
	Organizers
	Categories of Trainees Expected
	Proposed Period/Time
	Collaborators

	1
	Pre-season training for extension officers
	DARDA 
	EAs, BEAs, BESs, ZEOs, SMSs.
	Jan – March
	MANR

	2
	Best Agronomic Practices for PBRC
	DARDA
	Cowpea Farmers
	July – Aug.
	AATF/IAR

	3
	Most impactful practices for maize, fish and broiler productions
	DARDA 
	Farmers.
	March-June 
	USAID Extension Activity

	4
	Use of technological innovation for post-harvest management.
	DARDA 
	Farmers.
	Oct -Dec
	NSPRI

	5
	Post season training for extension officers
	DARDA 
	Extension workers
	Oct -Dec
	MANR


F. TECHNOLOGIES TO BE PROMOTED

	S/N
	Title
	Source
	Comment

	1
	Vegetable production using improved varieties 
	NIHORT
	To be promoted through MTP

	2
	Plantain and banana production using improved plantlets 
	NIHORT
	To be promoted through MTP

	3
	Cassava production using improved varieties 
	NRCRI/IITA
	To be promoted through MTP

	4
	Rice production using improved varieties
	NSS/NCRI
	To be promoted through MTP

	5
	Improved pig production practices (proper feeding and sanitation)
	NARIs
	To be promoted through MTP

	6
	Improved poultry production practices
	NARIs
	To be promoted through MTP

	7
	Improved homestead fish pond production practices
	NIOMR
	To be promoted through MTP

	8
	Yam beetle control
	NRCRI
	To be promoted through MTP

	9
	Bee keeping
	NARIs
	To be promoted through MTP

	10
	Pineapple production (lining and establishment)
	NARIs
	To be promoted through MTP

	11
	Hybrid maize production
	IAR&T
	To be promoted through MTP

	12
	Lining out/establishment of oil palm
	NIFOR
	To be promoted through MTP

	13
	Pod Borer Resistant Cowpea
	IAR/AATF
	To be promoted through Sensitization and MTP


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	
	
	
	

	2
	
	
	
	

	3
	
	
	
	

	4
	
	
	
	

	5
	
	
	
	

	6
	
	
	
	

	7
	
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Delta Agricultural Procurement Agency (DAPA) to continue providing input support to the farmers in the state.

Procurement and distribution by DAPA is a routine.

	
	
	

	2
	Credit
	-

	3
	Agro-chemical
	More agro-chemicals to be procured by DAPA for distribution and sales.

	4
	Tractor/Animal Traction
	Farmers to benefit from the tractors procured by the State Government at a subsidized rate.

	5
	MTRM/QTRM Situation Report
	Only 1 MTRM was conducted for the year under review


[image: image69.jpg]


                                                                                                              [image: image70.png]



Name of ADP:  EBONYI STATE 

Postal address: PMB 040 ABAKALIKI

Email:ebonyistateadp@gmail.com


 Telephone 08066836476

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	

	2
	FNTs
	26
	

	3
	OFARs
	4
	

	4
	No. of Farm Families
	1,500,000
	

	5
	No. of SPATs established 
	10,100
	

	6
	No. of MTPs
	500
	

	7
	No. of Field days
	450
	

	8
	No. of Agric Shows
	25
	

	9
	No. of group formed
	3,300
	

	10
	No. of Pre-season training per year
	2
	

	11
	No. of Post-season training per year
	2
	

	12
	Extension publications to be produced (No. of Titles)
	500
	

	
	Bulletins 
	100
	

	
	Guides
	200
	

	
	Leaflets
	100
	

	
	Posters
	100
	

	
	Others
	
	

	13
	Zonal Steering Committee Meeting
	2
	

	14
	Zonal Technical Committee Meeting
	2
	

	15
	Zonal REFILS workshops
	1
	

	16
	No of Extension Workers (VEAs)
	450
	

	17
	No of Extension workers (BESs)
	36
	

	18
	EA/Farmer ratio in the state
	1/8270
	


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED IN 2026

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins

Improve use of organic fertilizer in crop production

2. Aggressive scaling of home  garden

3. Embark on smart farming to reduce the effect of climate resilience

4. Dry season vegetable production

5. Promote GAP and MIP on rice and use of certified seed

6.  Promote E-extension service delivery and impart new innovation in Agriculture


	4,000

4,000

4,000

4,000

4,000

4,000
	ADP/MIN OF AGRIC

ADP/ALL AGRIC  DEVELOPMENT PROGRAMME

ADP/MIN OF AGRIC

ADP/MIN OF AGRIC

ADP/MIN OF AGRIC

ADP/MIN OF AGRIC



	2
	Guides

1. A guide to proper and safety handling of pesticides and herbicides

2. A guide to correct fertilizer application and use of soil test

3. A guide on post harvest management and handling techniques to reduce losses

4. Use of organic herbicides and fertilizers 


	3,000

3,000

3,000

3,000
	ADP/MIN OF AGRIC

ADP/MIN OF AGRIC

ADP/MIN OF AGRIC

ADP/MIN OF AGRIC



	3
	Leaflets

1. Production of high quality cassava flour

Tips why we should go back into farming .

Good housing and feeding of sheep and goat, piggery and poultry

. Adding value to cassava and rice production

Every home a garden to scale up home garden production to reduce malnutrition


	3,000

3,000

3,000

3.000

3,000
	ADP/MIN OF AGRIC

ADP/MIN OF AGRIC

ADP/MIN OF AGRIC

ADP/MIN OF AGRIC

ADP/MIN OF AGRIC




C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED IN 2026

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2

3

4

5


	Home steady garden production

Importance of soil testing

Use of GAP in crop production to achieve optimal yield

Good and proper management of livestock production

The use of certified seed and market source


	Weekly

Weekly

Monthly

Weekly

Weekly
	EBBC

EBBC

EBBC

EBBC

EBBC
	1 HR

30MINS

1HR

1 HR

30MINS


D. TELEVISION PROGRAMMES TO BE PRODUCED AND AIRED IN 2026 

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 

2.

3.

4.
	Scaling up home garden production and livestock to reduce malnutrition and increase food security

Smart farming to close the gap of climate resilience to reduce the effect on farmers

Promote organic and inorganic fertilizers

Management of pest and disease in rice and cassava farms


	Twice a week 

monthly 

monthly 

Twice a month 


	NTA ABAKALIKI

NTA ABAKALIKI

NTA ABAKALIKI

NTA ABAKALIKI
	30Mins

30Mins

30Mins

45Mins


E. TRAINING PROGRAMMES TO BE HELD IN 2026

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1

2

3

4

5

6

7

8
	Pre-season training 

In –season and post-harvest training 

Capacity Building for Rural Farmers in Ebonyi State on Rice Value Addition

Promote the use organic fertilizer and inorganic fertilizer

Promote soil testing before cropping and use of GAP in crop production

Smart agricultural farming and home steady garden

Digital use of extension service delivery

Repositioning Agricultural cooperatives as a vehicle for emergence of sustainable clusters 
	EBADEP 

EBADEP 

EBADEP 

EBADEP

EBADEP

EBADEP 

EBADEP

EBADEP
	Extension Agents, ZEOs and Lead Farmers 

Extension Agents, ZEOs and Lead Farmers 

Farmers 

Farmers 

Farmers 

Rural Women 

Farmers

Farmers

 
	Jan-Feb,2026

June-Sep,2026 

April,2026 

January 2026 

March,2026 

Feb,2026 

March,2026 

Feb,2026 


	EBADEP/VCDP/MIN OF AGRIC 

EBADEP/VCDP/MIN OF AGRIC 

EBADEP 

EBADEP 

EBADEP and State Min of Agric & Natural Resources 

EBADEP and State Min of Agric & Natural Resources 

EBADEP and State Min of Agric & Natural Resources 

EBADEP and State Min of Agric & Natural Resources 




F. TECHNOLOGIES TO BE PROMOTED IN 2026

	SN
	Title
	Source 
	Comment

	1
	Promote use of organic fertilizers and soil testing. 
	EBADEP/VCDP 


	Small holders farmers are targeted 

	2
	Use of certified improved seeds that are resistance to pest and diseases and flood tolerance varieties 
	EBADEP/VCDP 


	High yielding, early maturing and flood tolerance varieties to be demonstrated to the farmers. 



	3
	Promote and improve home steady garden


	EBADEP/VCDP 


	Small holders’ farmers are targeted 

	4
	Digital E-Extension services delivery using Rice Advice tools, Area Calculator for farm measurements etc 


	EBADEP/VCDP 


	Farmers will optimally utilize their android phones for farming activities. 




G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	IFAD VCDP 
	2014/2015 
	On-going
	to enhance on a sustainable basis Incomes and food security of poor rural households engaged in the production, processing and marketing of rice and cassava value chain 


	2
	ZERO HUNGER PROJECT 
	2021
	On-going
	Promotion on GAP in Rice Production, processing and value addition 



	3
	Nigeria Covid Action Recovery Economic Stimulus (NG-CARES) 


	2020
	On-going
	Empowering rural farmers through support of agricultural inputs, fertilizers, herbicides, seeds, poultry, piggery, cassava cuttings etc 


	4
	ACTION AIDS /PDA


	2006
	On-going
	Agro-Ecology promotion, Educational support and Health 



	5
	Transforming lives through nutrition by Hellen Kellers and vitamin angels


	2024


	On-going
	Transformation of life through Nutrition and Agricultural products


	6
	SPAC Project


	2006


	On-going
	Agro ecology production ,empowering small women holder farmers




H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	The cost of organic and inorganic fertilizers are on the increase daily. Government should as a matter of necessity subsidize the cost so that it can be affordable to the farmers

	2
	Credit
	The Government should facilitate the soft credit facilities to farmers at a single digit interest.

	3
	Agro-chemical
	The cost of Agro-chemical is on the increase equally. Integrated farm management to be adopted.

	4
	Tractor


	More tractor should be procured and the ones already procured should not be left in the hand of politicians. Smaller machines such as power tillers should be procured to supplement the already procured tractors.  



	5
	MTRM/QTRM situation Report 
	The MTRM and QTRM should be held accordingly and the adequate documentation and appraisal to be given 




[image: image71.jpg]


                                                                                                                     [image: image72.png]FEDERAL GOVERNMENT OF

NIGERIA




Name of ADP: Edo ADP

Postal address: 

Email:
edoadp@gmail.com

                Telephone 08054499997

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	

	2
	FNTs
	26
	

	3
	OFARs
	7
	

	4
	No. of Farm Families
	>300,000
	

	5
	No. of SPATs established 
	760
	

	6
	No. of MTPs
	114
	

	7
	No. of Field days
	20
	

	8
	No. of Agric Shows
	10
	

	9
	No. of group formed
	200
	

	10
	No. of Pre-season training per year
	12
	

	11
	No. of Post-season training per year
	5
	

	12
	Extension publications to be produced (No. of Titles)
	
	

	
	Bulletins 
	0
	

	
	Guides
	5
	

	
	Leaflets
	0
	

	
	Posters
	0
	

	
	Others
	0
	

	13
	Zonal Steering Committee Meeting
	4
	

	14
	Zonal Technical Committee Meeting
	2
	

	15
	Zonal REFILS workshops
	1
	

	16
	No of Extension Workers (VEAs)
	26
	

	17
	No of Extension workers (BESs)
	12
	

	18
	EA/Farmer ratio in the state
	1:800
	


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins

1. 

2.

3.

4.

5.


	
	

	2
	Guides

1. Groundnut Production.

2. Layer Production.

3. Vaccination in Birds.

4. Fingerling Production.

5. Homestead Gardening.
	5
	NIL

	3
	Leaflets

1. 

2.

3.

4.

5.
	
	


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2

3

4

5
	
	
	
	


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 

2. 

3.

4.

5.
	Land preparation.

Good Agricultural practices

Good Animal husbandry practices

Coconut meat processing etc.


	Weekly
	EBS
	30MIN


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1

2

3

4

5
	Nil.


	
	
	
	


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	Popularization of sweet potato.
	NRCRI.
	

	2
	Intensification of Cocoyam production
	IITA and NRCRI
	

	3
	Bio-fortified crops (sweet potato, cassava)
	IITA and NRCRI 
	

	4
	Good Animal husbandry practices
	NAPRI
	

	5
	Water quality in fishery and stocking density
	NIFFR
	

	6
	Post-harvest handling of rice and use of false bottom in rice par-boiling,
	JICA
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	EDO CARES (FADAMA)
	2020
	On-going
	Provision of Agricultural Input such as cassava, maize, vegetable seeds, fertilizers, poultry and fish.

-Provision of small irrigation facilities and rehabilitation of feeder roads,

-Provision of Agricultural Assets such as cassava mill. Rice mill, power tiller. Defeathering and generators

-Upgrading of wet market with water and sanitation facilities.

	2
	IFAD LIFE-ND
	2020
	On-going
	-Establishment of sustainable Agribusiness Enterprises.

-Training of Incubators and incubates

-Conduct of survey Baseline in selected Local government Areas and communities.

-Establishment of Agribusiness- Driven infrastructure (Earthen farm roads, land development etc.)

-Financial inclusion support to Agribusiness.

-Rural Institution strengthening

-Project management and coordination.

	3
	LPRES
	2023
	On-going
	-Capacity Building, Farmer Field School, Extension Service Delivery, Animal Health Service, Infrastructural Development.



H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	

	2
	Credit
	

	3
	Agro-chemical
	

	4
	Tractor/Animal Traction
	

	5
	MTRM/QTRM situation Report 
	


[image: image73.jpg]


                                                                                                          [image: image74.jpg]



Name of ADP: Ekiti State Agricultural Development Programme

Postal Address: PMB 5016, Behind Fire Service Station, Ijesa-Isu Road, Ikole – Ekiti

E-mail: ekadep@yahoo.com                      Telephone: 0864460268, 08062147247 

 2026  EXTENSION SUPPORT INDICATORS 

	SN
	SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	To be supported by the 16 LGAs of the State

	2
	FNTs
	24
	Funded by ADP

	3
	OFARs
	10
	To be funded by ADP

	4
	No. of Farm Families
	235,000
	Number of farm families in the State

	5
	No. of SPATs established 
	280
	10 SPATS by EAs & 5 SPATS by BEAs

	6
	No. of MTPs
	64
	4 MTPs per LGA

	7
	No. of Field days
	17
	1 field day per LGA and 1 for Headquarters

	8
	No. of Agric Shows
	2
	Dry and wet season

	9
	No. of group to be formed

    
	160
	10 groups per block

	10
	No. of Pre-season training per year
	1
	To be funded by ADP

	11
	No. of Post-season training per year
	1
	To be funded by ADP

	12
	Extension publications to be produced (No. of Titles)
	10,000
	To be funded by ADP

	
	Bulletins 
	3,000
	To be funded by ADP

	
	Guides
	4,000
	To be funded by ADP

	
	Leaflets
	2,500
	To be funded by ADP

	
	Posters
	500
	To be funded by ADP

	
	Others
	Nil
	

	13
	Zonal Steering Committee Meeting
	4
	Jointly organized by ADP and Coordinating NARIs

	14
	Zonal Technical Committee Meeting
	1
	Executive Directors of NARIs and PM-ADPs meeting

	15
	Zonal REFILS workshops
	1
	ADPs, NARIs and other stakeholders

	16
	No of Extension Workers (VEAs)
	177
	More hands to be employed by the State Government

	17
	No of Extension workers (BESs)
	16
	Some BESs were also served as SMSs

	18
	EA/Farmer ratio in the state
	1: 5,875
	Mass Employment of EAs will reduce the ratio


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED

	Title
	Target Copies
	Collaborators

	Bulletins:

1. Ekadep voice

2. Ekadep Calendar
	2,000

1,000
	ADP and Service Providers

ADP

	Guides:

Good Agricultural Practices (GAP) in Cocoa Value Chain.

Good Agricultural Practices (GAP) in Maize Value Chain.

3. Rapid multiplication of yam, rice, cassava

4. Value addition and improved storage techniques

5. Organic fertilizer preparation and utilization

6. Value addition to poultry products and fishery
	5,000

5,000

2,000

2,000

2,000

2,000
	ADP 

ADP & NIRSAL

ADP and IITA

ADP, IAR&T, FUOYE

ADP & IAR&T, BIOWISH Africa

ADP & WAAPP

	Leaflets:

1. Improved Rice Production & Processing

2. Fishery production and processing

3. Good management practices in poultry

4. Oil palm production and processing

5. Value addition to arable crops
	1,000

1,000

1,000

1,000

1,000
	ADP, WAAPP, NAERLS, JICA

,,

,,

,,

,,


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	Programme Title/Topics
	Frequently
	Broadcasting station
	Duration

	Agbeloba
	Daily (except Sundays)
	BSES 91.5FM
	5.40 -5.50am


D. TELEVISION PROGRAMMES PRODUCED AND AIRED 

	Programme Title/Topics
	Frequently 
	Broadcasting station
	Duration 

	Lahere
	 Weekly 
	EKTV Ch.41
	5.30 pm - 6.00pm on Mondays


E. TRAINING PROGRAMMES

	S/N
	Title
	Organizers
	Categories of Trainees expected
	Proposed Period/Time
	Collaborator

	1.
	 Pre & Post season trainings
	Extension/ADP
	EAs, BEAs, BESs, ZEOs, & other field Officers.
	Feb – April/ Oct – Dec
	IAR&T

	2.
	Capacity building on strengthening Extension Services in Ekiti State
	ADP
	Extension &Technical field Officers
	January-December
	IAR&T, ARMTI, IITA, NCRI, etc.

	3.
	Capacity building on Computer usage/ICT
	ADP
	SMSs, 
	Jan. – Dec
	IAR&T

	4.
	Monitoring and evaluation
	ADP
	Enumerators & M&E Officers
	Feb- July
	National Statistics Dept

	5.
	Value addition and packaging
	ADP
	EAs, and other Ext Officers
	Jan-Dec
	IITA, IAR&T

	6.
	Climate change effects and mitigation strategies


	ADP
	Extension Technical field officers


	Jan – Dec


	FUNAAB, IAR&T




F. TECHNOLOGIES TO BE PROMOTED

	S/N
	Title 
	Source
	Comments

	
	i. Cocoa rehabilitation by coppicing/total replanting

ii. Introduction of New cocoa breed (TCN 1-8)
	CRIN
	Supply of improved cocoa seedlings and pods

	
	Yam multiplication technique (yam minisett tech.)
	IITA, UI (Yam for export programme)
	Training on yam  minisett production and popularization

	
	Production of cassava recipes eg. High quality Cassava flour for bread, quality gari, odorless fufu etc.
	IITA, CAVA II Project
	HQCF popularization for bread and other cassava products.

	
	Control of fruit piercing moths in citrus.
	NIHORT
	Training of SMSs and other field staff (TOT)

	
	Popularization and Utilization of Orange Flesh sweet potato(OFSP) into various recipes
	ARMTI
	Popularization and Utilization of Orange Flesh sweet potato(OFSP) into various recipes for the farmers and other field staff.

	
	Control of fall army worn in maize
	IAR &T
	Popularization of recommended agro-chemicals


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	IsDB-NPFS


	
	
	To ensure food security in the state

	2
	
	
	
	

	3
	
	
	
	

	4
	
	
	
	

	5
	
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	S/N
	                                     Input Situation

	1
	Fertilizer
	Not readily available at farmers disposal and high cost.

	2
	Credit
	High rate of interest, not easily available at the required time and amount.

	3
	Agro-chemical
	High cost, low potency and not readily available at farmers disposal.

	4
	Tractor/Animal Traction
	Very few tractors (less than 15) were available for farmers use in Ekiti State and this has subsequently reduced mechanization activities in the State. Animal traction not available.

	5
	MTRM/QTRM Situation report
	Fund to support Resource persons and for hosting the MTRM were difficult. Meanwhile, we still trust LGAs for hosting and support.



Name of ADP: FCT Agricultural Development Project (FCT ADP)

Postal address: P.M.B 165, Gwagwalada Abuja

Email:
fctadp1990@yahoo.com
                              Telephone: 08065977756 (PM/MD)

A. EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	With condition of fund availability.

	2
	FNTs
	24
	With condition of fund availability.

	3
	OFARs
	12
	With condition of fund availability.

	4
	No. of Farm Families
	170,000
	Engagement into Agricultural activities is increasing in the state.

	5
	No. of SPATs established 
	-
	Not applicable

	6
	No. of MTPs
	6
	With condition of fund availability.

	7
	No. of Field days
	12
	With condition of fund availability.

	8
	No. of Agric Shows
	6
	With condition of fund availability.

	9
	No. of group formed
	200
	With condition of fund availability.

	10
	No. of Pre-season training per year
	2
	With condition of fund availability.

	11
	No. of Post-season training per year
	2
	With condition of fund availability.

	12
	Extension publications to be produced (No. of Titles)
	
	

	
	Bulletins 
	10,000
	With condition of fund availability.

	
	Guides
	10,000
	With condition of fund availability.

	
	Leaflets
	5,000
	With condition of fund availability.

	
	Posters
	5,000
	With condition of fund availability.

	13
	Zonal Steering Committee Meeting
	4
	With condition of fund availability.

	14
	Zonal Technical Committee Meeting
	4
	With condition of fund availability.

	15
	Zonal REFILS workshops
	1
	With condition of fund availability.

	16
	No of Extension Workers (VEAs)
	131
	FCTA in in the Process of recruiting more EAs

	17
	No of Extension workers (BESs)
	26
	1BES/Block

	18
	EA/Farmer ratio in the state
	1:800
	 Subject to recruitment of EAs



B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins
1. Principles and Practices of Organic Agriculture. 

2. Prevention and control of common diseases of fish in ponds. 

3. Cow pea production.

4. Appropriate Postharvest technologies.

5.  Organic livestock production.
	 

5,000

      “

      “

      “

      “
	FCT ADP &NAERLS

	2
	Guides
1. Poultry Production

2. Climate Smart agricultural practices for maize production.

3. Introduction to Aquaponics .

4. Rabbit Production

5. Production and utilization of Potatoes
	 

5,000

   “

    “

    “

    “
	FCT ADP &NAERLS

	3
	Leaflets
1.  Processing of ginger into juice.

2. Backyard sack Farming. 

3. Uses and Management of Snails.

4. Improved methods of shear-butter processing. 

5 Pests and diseases of vegetables and their control.
	 

5,000

   “

   “

   “

   “
	FCTADP &NAERLS


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 
	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2

3

4

5
	Principles of Organic Agricultural Production.

Common Pest and Diseases of livestock

Fish farming and Processing

Agricultural Entrepreneurship training.

Savings Mobilization
	Weekly

          ‘’

          ‘’

          ‘’

          ‘’

          ‘’


	Capital FM

          ‘’

          ‘’

          ‘’

          ‘’

          ‘’


	30 Minutes

          ‘’

          ‘’

          ‘’

          ‘’

          ‘’




D. TELEVISION PROGRAMMES TO BE PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 

2

3.

4

5
	Principle and Practices of Organic Agriculture.

Climate smart agricultural practices for maize production.

Aquaponics principle and practices

Farmer’s information Desk

Livestock production 

Backyard Sack Farming


	Weekly

 “

‘’

‘’

‘’

‘’

‘’
	NTA, Channel 5

‘’             ‘’

‘’             ‘’

‘’             ‘’

‘’             ‘’

‘’             ‘’ 
	 30 minutes

‘’          ‘’

‘’          ‘’

‘’          ‘’

‘’          ‘’ 

“            “


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1.

2.

3.

4.

5.

6.


	Training on crop utilization, cassava and OFSP.

Communication Technology for Extension workers

Agribusiness promotion for Farmers and EAs.

Electronic Extension services delivery.

Agro ecology practices in crop production

Soil fertility evaluation as a tool for predicting fertilizer recommendation.

Effect of climate change on trees ornamentals, Horticultural crops, & also mitigation for better profit
	FCT ADP

FCT ADP

FCT ADP

FCTA ADP

FCT ADP

FCT ADP

FCT ADP
	EAs & Farmers

EAs & Farmers

EAs & Farmers

Farmers

EAs & Farmers

Farmers &EAs

Staff & Farmers
	September

January

August

February

March

February


	SWOFON

NISS

  -


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	 Handling of Processing Equipment
	FCT ADP
	To train women farmers on processing Equipment 

	2
	  Organic Agriculture
	Contec Global & FCT ADP
	To train farmers on organic Agric in Entrepreneurial way.

	4
	Nutrition Improvement Programme
	FCT ADP
	Train Farmers on nutrition improvement practices 


G: SPECIAL PROJECTS:
	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	ACRESAL
	2023
	6 Years
	Restoration of degraded landscapes and soils with planting Agro-forestry seedlings and drought resilient crops established as a pilot scheme Project in some selected Area Councils of FCT.

	2
	SAPZ
	2023
	5 Years
	To concentrate Agro processing activities within areas of high agricultural potentials to boost productivity and integrate production, processing, and marketing of selected commodities.


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Intervention of Government may continue in 2026

	2
	Credit
	More Farmers will be linked to the financial lending institutions for credit.

	3
	Agro-chemical
	Organic pesticides and herbicides are gaining popularity among farmers, this may impact the cost of production positively.

	4
	Tractor/Animal Traction
	The FCTA is making efforts to resuscitate the Tractor Hiring System in the Territory

	5
	MTRM/QTRM situation Report 
	The activities may improve in funding is provided.


Name of ADP: GOMBE STATE ADP

Postal address: P.M.B. 0046

Email:
gombeadp@yahoo.com
                Telephone_______________________

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	4
	PAUCITY OF FUNDS

	2
	FNTs
	-
	-

	3
	OFARs
	-
	-

	4
	No. of Farm Families
	1,000,000
	-

	5
	No. of SPATs established 
	160
	-

	6
	No. of MTPs
	24
	-

	7
	No. of Field days
	40
	-

	8
	No. of Agric Shows
	24
	-

	9
	No. of group formed
	500
	-

	10
	No. of Pre-season training per year
	4
	-

	11
	No. of Post-season training per year
	4
	-

	12
	Extension publications to be produced (No. of Titles)
	
	

	
	Bulletins 
	500
	

	
	Guides
	1,000
	

	
	Leaflets
	250
	

	
	Posters
	1,000
	

	
	Others
	
	

	13
	Zonal Steering Committee Meeting
	4
	

	14
	Zonal Technical Committee Meeting
	2
	

	15
	Zonal REFILS workshops
	2
	

	16
	No of Extension Workers (VEAs)
	150
	

	17
	No of Extension workers (BESs)
	22
	

	18
	EA/Farmer ratio in the state
	1:500
	


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins

1. M & E TRAINING

2.POST HARVEST TRANING, PROCESSING AND STORAGE OF PRODUCE

3.

4.

5.


	100

500
	RICOWAS

SAA


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2

3

4

5
	NOMA DON RIBA

FILIN SASAKAWA

NOMA DA KIWO


	FM

FM

FM
	AMANA, GMC

VISION FM, GMC

GMC, PROGRESS FM
	20 MIN

20 MIN

20 MIN


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 

2. 

3.

4.

5.
	FILIN SASAKAWA GAMANOMA

NOMA DON RIBA

FILIN ANOMAN ZAMANI
	NTA

NTA

NTA
	NTA

NTA

NTA
	15 MIN

15 MIN

30 MIN


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1


	TRAINING ON CLIMATE CHANGES AND ITS EFFECTS ON FARMING
	RICOWAS
	EAs & FARMERS
	3RD QUARTER OF THE YEAR
	RICOWAS & SAA


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	SYSTEM RICE INTENSIFICATION
	RICOWAS
	SRI

	2
	HOME GARDENING
	SAA
	

	3
	
	
	

	4
	
	
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	RICOWAS
	2024
	2
	RESILIENT RICE PRODUCTION


H. GENERAL: BRIEF REMARKS ON:

	SN
	                              Input situation

	1
	Fertilizer
	GOVERNMENT, OPEN MARKET

	2
	Credit
	BANKS   AND COOPERATIE SOCIETIES

	3
	Agro-chemical
	OPEN MARKET

	4
	Tractor/Animal Traction
	PRIVATE OWNERS AND GOVERNENT

	5
	MTRM/QTRM situation Report 
	-


Name of ADP: IMO 

Postal Address: P.O. Box 1977 

Email:
oliviachinagorom2018@gmail.com
Telephone_______________________

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	Luck of funds

	2
	FNTs
	26
	FNT carried out

	3
	OFARs
	4
	Lack of funds to carry out

	4
	No. of Farm Families
	303,500
	

	5
	No. of SPATs established 
	1000
	

	6
	No. of MTPs
	1200
	Encourage faster adoption  

	7
	No. of Field days
	150
	

	8
	No. of Agric Shows
	3
	No funds

	9
	No. of group formed
	200
	

	10
	No. of Pre-season training per year
	3
	No fund to finance it

	11
	No. of Post-season training per year
	3
	No fund to finance it

	12
	Extension publications to be produced (No. of Titles)
	5000
	Lack of funds

	
	Bulletins 
	1000
	Lack of funds

	
	Guides
	1000
	Lack of funds

	
	Leaflets
	1000
	Lack of funds

	
	Posters
	1000
	Lack of funds

	
	Others
	1000
	Lack of funds

	13
	Zonal Steering Committee Meeting
	2
	No fund

	14
	Zonal Technical Committee Meeting
	2
	No fund

	15
	Zonal REFILS workshops
	1`
	No fund

	16
	No of Extension Workers (VEAs)
	305
	Reduction in work force

	17
	No of Extension workers (BESs)
	27
	

	18
	EA/Farmer ratio in the state
	1:1500
	High rate of EA/farmer ration


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins


	5000
	ADP component head

	2
	Guides Homestead

1. Homestead fish production

2.Tomato paste production

3.Snail production

4. Bee keeping (Honey production 

5.Cucumber production 
	200

200

200

200

200
	ADP component head

ADP component head

ADP component head

ADP component head

ADP component head


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2

3

4

5
	Fish processing for improved shelf 

Cassava production improved variety

Oil palm production 

Bee keeping

Raising sleep goat on raised platform
	Twice a week

Twice a week

Twice a week

Twice a week

Twice a week
	Orient FM

Orient FM

Orient FM

Orient FM

Orient FM
	30 minutes

30 minutes

30 minutes

30 minutes

30 minutes


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1
	Fingerlings to fork 


	BATNF/ADP
	Fish farmers
	6 months
	ADP/BATNF


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	Fish feed compounding 
	NIFFR/ADP
	Old

	2
	Production of high quality cassava flour
	
	

	3
	Dry Season Farming
	
	

	4
	Planting of Improved Cassava cutting 
	
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	Fingerlings to fork project
	2022
	4 years
	Training on farming on Fingerlings & table fish production 

	2
	FADAMA (NG-CARES)
	2021
	4 years
	Input distribution and advisory service


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	High cost of fertilizer

	2
	Credit
	High interest rate 

	3
	Agro-chemical
	Increase in use due to awareness created 

	4
	Tractor/Animal Traction
	-

	5
	MTRM/QTRM situation Report 
	Lack of funds to organize 




Name of ADP: JIGAWA

Postal address:  JARDA PMU Dutse, opp, SAHAD Store, Kiyawa Road, Jigawa State

Email:
mhabib010@gmail.com



   Telephone_________07039772123______________

A.  EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	

	2
	FNTs
	24
	

	3
	OFARs
	8
	

	4
	No. of Farm Families
	900,000
	

	5
	No. of SPATs established 
	
	

	6
	No. of MTPs
	80
	

	7
	No. of Field days
	20
	

	8
	No. of Agric Shows
	2
	

	9
	No. of group formed
	800
	

	10
	No. of Pre-season training per year
	2
	

	11
	No. of Post-season training per year
	2
	

	12
	Extension publications to be produced (No. of Titles)
	
	

	
	Bulletins 
	2000
	

	
	Guides
	1500
	

	
	Leaflets
	5000
	

	
	Posters
	10,000
	

	
	Others
	
	

	13
	Zonal Steering Committee Meeting
	1
	

	14
	Zonal Technical Committee Meeting
	1
	

	15
	Zonal REFILS workshops
	1
	

	16
	No of Extension Workers (VEAs)
	2000
	

	17
	No of Extension workers (BESs)
	60
	

	18
	EA/Farmer ratio in the state
	1:400
	


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins

1. Wheat production

2.Rice Production

3. Cowpea Production

4. Sesame Production


5. Herbiscus Production


	2000
	JARDA/SAA

	2
	Guides

1. Animal feeds

2. Major crops

3. Innovation plat form

4.

5.
	1,500


	

	3
	Leaflets

1. Safe use of agro chemical

2. pest and disease management on wheat

3. pest and disease management on rice

4.

5.
	5,000
	


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Program Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2

3

4

5
	Jagoran manoma


	WEEKLY
	RADIO JIGAWA
	30 MINITES


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 

2. 

3.

4.

5.
	NADUKE
	WEEKLY
	NTA JIGAWA
	30 MINUTES


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1

2
	Pre-season training, mid-season and post-harvest handling technics to both extension agent and BES.

Soil sample training technics


	SAA/JSG

OCP/JSG
	EAS and BES

EAE and BES
	QURTERLY

Pre seasoned and mid seasoned
	JARDA/SAA

JARDA/OCP/JSG


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	Climate smart Agriculture technology
	SAA/JARDA
	

	2
	E extension services
	JSG/JARDA/JATA
	

	3
	
	
	

	4
	
	
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	OCP
	2025
	1 YEARS
	Training and soil testing analysis 

	2
	J-CARE
	2024
	2 YEARS 
	Input support Empowerment of small holder

Horticultural farmers



	3
	SASAKAWA
	1992
	
	Training and Demonstration

	4
	MASAKI 2.0/774
	2025
	
	Save the children project.

	5
	
	
	
	

	6
	
	
	
	

	7
	
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	40,000MT

	2
	Credit
	NIL

	3
	Agro-chemical
	30,000 LITRES

	4
	Tractor/Animal Traction
	10 Units of Tractors were distributed to each State House of assembly center. 

	5
	MTRM/QTRM situation Report 
	NIL


Name of ADP: Kaduna State Agricultural Development Agency KADA

Postal address: No. 1 Aliyu Makama, by Gashash Road, Barnawa GRA, Kaduna

Email:
kadphq@yahoo.com

Telephone: 08062513652, 08143436031

A. 2022 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	

	2
	FNTs
	0
	

	3
	OFARs
	90 & 120
	

	4
	No. of Farm Families
	1,322,226
	

	5
	No. of SPATs established 
	Nill
	

	6
	No. of MTPs
	800
	

	7
	No. of Field days
	24
	

	8
	No. of Agric Shows
	1
	

	9
	No. of group formed
	700
	

	10
	No. of Pre-season training per year
	1
	

	11
	No. of Post-season training per year
	1
	

	12
	Extension publications to be produced (No. of Titles)
	
	

	
	Bulletins 
	300
	

	
	Guides
	500
	

	
	Leaflets
	400
	

	
	Posters
	600
	

	
	Others
	
	

	13
	Zonal Steering Committee Meeting
	4
	

	14
	Zonal Technical Committee Meeting
	2
	

	15
	Zonal REFILS workshops
	1
	

	16
	No of Extension Workers (VEAs)
	1,024
	

	17
	No of Extension workers (BESs)
	59
	

	18
	EA/Farmer ratio in the state
	1:1500
	


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins

1. 

2.

3.

4.

5.


	10,000
	

	2
	Guides

1. 

2.

3.

4.

5.
	5,000

10,000

10,000
	

	3
	Leaflets

1. 

2.

3.

4.

5.
	5,000
	


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2
	Noma Babbar Sana’a

Ku Saurara Manoma
	Weekly (Wednesday 3.30 pm

 and Saturday 4.45am)

Weekly ( Sunday  9.15 am and Tuesday9.45 am)
	Nagarta Radio

FRCN Kaduna
	15Minutes

15 Minutes




D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 

2. 

3.

4.

5.
	Nil

Nil
	
	
	


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1


	Pre and post-harvest training.


	KADA


	EAS/Farmers


	April-May
	


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	GAP on rice production (SRI)
	LINKS
	promoting SRI Technology ( System of Rice Intensification)

	2
	Strengthening Nutrition on Priority Staples
	GAIN
	promote the production and consumption of vitamin A yellow maize

	3
	GAP on vegetable production
	East West Seed KT
	Increasing the productivity of small holder vegetable farmer through the adoption of Good Agronomic Practices.

	4
	
	
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	AGRA/EXAF Kaduna Consortium.
	2022
	3 YEARS
	Linking CBA to financial institutions, Training on project knowledge/community entry, Post-harvest handling, Grain quality standard and marketing etc.

	2
	AUDA NEPAD
	2022-2027
	5 Years
	Youth and Women Empowerment on Agricultural Value Chain

	3
	National Livestock Transformation Plan (NLTP)
	2022 – 2037
	10 years
	Establishment of pilot modern grazing reserve

	4
	Livestock Productivity & Resilience Support (L-PRES)
	2022 – 2027
	5 years
	-Conflict    Resolution

-Justice and Peace

-Humanitarian Relief & Early Recovery

-Human Capital Development

-Cross outing Issues

-Economic Investment

	5
	AGRA/SAA Africa
	2025-2028
	3 years
	-Promote Production and market access 

-Soybean and maize Production 

	6
	
	
	
	

	7
	
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	10,860 MT To be distributed to small holder farmers by Kaduna State, Federal government and reliable agro dealers

	2
	Credit
	Farmers to be linked with CBN, Commercial Banks, and NIRSAL

	3
	Agro-chemical
	To be provided by KADA and reliable agro dealers

	4
	Tractor/Animal Traction
	To be provided by Mahindra Tractors Assembly through the KDSG and other Tractor hiring association

	5
	MTRM/QTRM situation Report 
	To be conducted by KADA



[image: image75.jpg]


                                                                                                       

Name of ADP: Kano State Agricultual and Rural Development Authority (KNARDA)  

Postal address: Km 9 Hadejia Road, P.M.B. 3130 Kano

Email:
knarda2010@gmail.com


                Telephone:- 08066020043
A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	

	2
	FNTs
	24
	

	3
	OFARs
	6
	

	4
	No. of Farm Families
	1,620,000
	

	5
	No. of SPATs established 
	440
	

	6
	No. of MTPs
	44
	

	7
	No. of Field days
	4
	

	8
	No. of Agric Shows
	2
	

	9
	No. of group formed
	200
	

	10
	No. of Pre-season training per year
	4
	

	11
	No. of Post-season training per year
	4
	

	12
	Extension publications to be produced (No. of Titles)
	
	

	
	Bulletins 
	300
	

	
	Guides
	1,500
	

	
	Leaflets
	1,000
	

	
	Posters
	1,000
	

	
	Others
	
	

	13
	Zonal Steering Committee Meeting
	3
	

	14
	Zonal Technical Committee Meeting
	3
	

	15
	Zonal REFILS workshops
	3
	

	16
	No of Extension Workers (VEAs)
	2,300
	

	17
	No of Extension workers (BESs)
	176
	

	18
	EA/Farmer ratio in the state
	1:800
	


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins

1. 

2.

3.

4.

5.


	500
	

	2
	Guides

1. 

2.

3.

4.

5.
	1,500
	

	3
	Leaflets

1. 

2.

3.

4.

5.
	1,000
	


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2

3

4

5
	Noma da Hukumar KNARDA


	98.5 FM

& 89.3 FM
	Nasara Radio

&

Radio Kano
	30 minutes


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 

2. 

3.

4.

5.
	Mu Koma Gona


	
	ARTV KANO
	30 minutes


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1

2

3

4

5
	Pre-season training

Mid-season training

Post-harvest training

Family nutrition and income generation

Training on group dynamics and leadership skills


	KNARDA

KNARDA

KNARDA

KNARDA

KNARDA
	Farmers

EAs

Farmers

EAs

Farmers

Eas

Women Farmers

WIA

Farmer group leaders
	May

August

September 

October

November
	FMAFS, IITA, ICRISAT, SAPZ, Deliver Nigeria

ADP

IITA, ICRISAT, SAPZ, Deliver Nigeria

ADP

ADP & SAPZ


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	Good Agronomic Practices (GAP)
	
	

	2
	
	
	

	3
	
	
	

	4
	
	
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	GIZ
	2025
	5 Years
	Soil Health

	2
	THRIVES
	2025
	10 Years
	Vegetables

	3
	NSAND
	2025
	2 Years
	Nutritious Diet

	4
	SAPZ
	2024
	5 Years
	Agro-processing development.

	5
	HORTI-NIGERIA
	2025
	5 Years
	Vegetables

	6
	DELIVER NIGERIA
	2025
	5 Years
	Prod. & Consumption of Healthier Vegetables

	7
	
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	

	2
	Credit
	KNARDA will continuously links farmers with credit sources.

	3
	Agro-chemical
	

	4
	Tractor/Animal Traction
	Tractor services are available in the state but mostly on private ownership.

	5
	MTRM/QTRM situation Report 
	


Name of ADP: KATINA STATE AGRICULTURAL AND RURAL DEVELOPMENT      

             AUTHORITY (KTARDA)

Postal address: KM 4 KANO ROAD, KATSINA PMB2006

Email:
ktardakatsina@gmails.com       Telephone_______________________

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	Subject to availability of funds

	2
	FNTs
	          144
	24 to be conducted in each of the 6 sub zonal offices

	3
	OFARs
	       34    
	One to be established at each LGA of the state

	4
	No. of Farm Families
	      900,000    
	

	5
	No. of SPATs established 
	         7220
	PLANNING TO ESTABLISH 10 By Each EA (722 Eas)

	6
	No. of MTPs
	     68
	Planning To Establish At Least 2 At Each Of The 34 L.G.A Of The State.

	7
	No. of Field days
	            68
	At Least 2 At Each Of The L.G.A 

	8
	No. of Agric Shows
	            3
	National, State, And Zonal Agric Show 

	9
	No. of group formed
	          1000
	

	10
	No. of Pre-season training per year
	             6
	At Least Two To Be Conducted Each Of The 3 Zonal Hqs

	11
	No. of Post-season training per year
	             6
	Planning To Establish Two At Each Of The 3 Zonal Hqs

	12
	Extension publications to be produced (No. of Titles)
	            
	

	
	Bulletins 
	          3000
	To Be Produce In The 3 Major Languages Ie Hausa, English And Ajami

	
	Guides
	          
	

	
	Leaflets
	          3000
	Produce In Hausa, Ajami And English Languages

	
	Posters
	         
	

	
	Others (RADIO AND TELEVISION PROGRMME)
	             RADIO 48

TV        48

              
	Television And Radio Programmes

	13
	Zonal Steering Committee Meeting
	  1
	Subject To Availability Of Funds

	14
	Zonal Technical Committee Meeting
	             1
	Subject To Availability Of Funds

	15
	Zonal REFILS workshops
	             1
	Subject To Availability Of  Funds

	16
	No of Extension Workers (VEAs)
	          1000
	Subject To Govt Approval

	17
	No of Extension workers (BESs)
	             34
	-

	818
	EA/Farmer ratio in the state
	        1: 800
	Currently the ratio  is 1:2000


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins

1. Cowpea production manual 

2. Maize Production Techniques Manual

3. Manual on Fattening of Livestock 

4. Manual on Management of work bulls 

5. Pesticide Spraying Technology 


	3000

3000

3000

3000

3000
	IAR/IITA

IAR/IITA

NARI

NARI

IAR

	3
	Leaflets

1. Post-harvest handling of vegetables 

2. Stone free rice processing Techniques
	3000

3000
	IAR/NIHORT

IAR/NCRI


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2

3

4

5


	Kartau Sarkin Noma

Repeat
	AM970 KHz 

AT 11:00 am on Monday and repeat thursday


	Katsina State Radio

Katsina State Radio
	30 Minutes 2x Weekly

30 Minutes


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 


	Naduke 
	Channel 22 on Tuesday at 10: 00pm
	KTTV
	30 Minutes Weekly


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1


	Pre-Season on Crop production


	KTARDA
	 BEAs, EAs And FARMERS
	3Days
	IAR and other National research institutions 


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	STONE FREE RICE PROCESSING TECHNIQUES
	IAR/NCRI
	

	2
	SPRAYING REGIME ON VEGETABLES AND FRUITS
	IAR/NHORT
	

	3
	SELECTION OF VAREITIES OF CROPS AT VARIUOS ECOLOGICAL ZONES OF THE STATE
	IAR/ OTHER RESEACH INSTITUTIONS
	

	4
	
	
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	FADAMA NG-CARES
	2022
	2 YEARS
	INCREASING CASH TRANSFERS AND LIVELIHOOD SUPPORT TO POOR AND VULNERABLE HOUSEHOLD.

INCREASING FOOD SECURITY AND SAFE FUNCTIONING OF FOOD SUPPLY CHAIN FOR POOR HOUSEHOLD.

PREVENTING COLLAPES AND FACILITATING RECOVERY OF HOUSEHOLD/MICRO ENTERPRICES AND STRENGTHENING INSTITUTIONAL SUPPORT FOR COORDINATION AND DELIVERY.


H. GENERAL: BRIEF REMARKS ON: 2026

	SN
	Input situation

	1
	Fertilizer
	20,000 Metric tons to Be Procured by Katsina State Government

	2
	Credit
	Farmers To Access Credit Through Some Commodity Associations.

Katsina State Government In Collaboration With Boi Will Provide Farmers With Credits In The State

	3
	Agro-chemical
	Katsina State To Empower Farmers With Agro Chemicals

	4
	Tractor/Animal Traction
	2000 Sola Pumping Machines To Be Procured For Distribution To Irrigation Farmers By Katsina State Government

	5
	MTRM/QTRM situation Report 
	MTRM/QTRM (12 MTRM AND 4 QTRM) Programme Will Be Conducted During 2026 Farming Season.




Name of ADP: KEBBI

Postal address: KM 11 Kalgo Junction Birnin Kebbi 

Email:
sulemanhamisu1@gmail.com



                Telephone__08036750482_____________________

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	

	2
	FNTs
	26
	

	3
	OFARs
	20
	

	4
	No. of Farm Families
	950,000
	

	5
	No. of SPATs established 
	1,984
	

	6
	No. of MTPs
	8
	

	7
	No. of Field days
	10
	

	8
	No. of Agric Shows
	5
	

	9
	No. of group formed
	2500
	

	10
	No. of Pre-season training per year
	10
	

	11
	No. of Post-season training per year
	10
	

	12
	Extension publications to be produced (No. of Titles)
	5
	

	
	Bulletins 
	5000
	

	
	Guides
	5000
	

	
	Leaflets
	2000
	

	
	Posters
	4000
	

	
	Others
	
	

	13
	Zonal Steering Committee Meeting
	4
	

	14
	Zonal Technical Committee Meeting
	4
	

	15
	Zonal REFILS workshops
	4
	

	16
	No of Extension Workers (VEAs)
	248
	

	17
	No of Extension workers (BESs)
	64
	

	18
	EA/Farmer ratio in the state
	1:800
	


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins
	5000
	

	2
	Guides
	1000
	


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2

3
	Na Duke

Sallama Manoma

Don Manoma 
	2 times a week
	KB Radio
	30 min.


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 
	MUTUM DA MUHALLIN SA
	ONCE A WEEK
	KB TV
	30 min .


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1

2

3

4

5
	Transforming Lives through Nutrition


	Helen Keller
	EA& Farmers
	12 months

Pre-season and in season 
	Helen Keller 


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	ATASP 1
	2016
	7 YEARS
	Infrastructure Development  ,capacity building , Rice value chain . 

	2
	RAMP 
	2021
	6
	Agro –logistics hubs and Rehabilitations of Rural roads .

	3
	SAPZ
	2024
	5
	Yet to commence activities 


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	State Government has procured Fertilizer and Distribute to Farmers free of Charge

	2
	Credit
	No credit facility this year 

	3
	Agro-chemical
	State Government has procured Agro Chemicals and Distribute to Farmers free of Charge

	4
	Tractor/Animal Traction
	3 Tractor hiring services was provided at one per Senatorial zone.

	5
	MTRM/QTRM situation Report 
	Both trainings have not been conducted in the State for a long period of time.


Name of ADP: KOGI ADP

Postal address: PMB 1067

Email:
 kogiagridev2000@yahoo.com



Telephone: 08065705713

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	

	2
	FNTs
	24
	

	3
	OFARs
	12
	

	4
	No. of Farm Families
	600,000
	

	5
	No. of SPATs established 
	24
	

	6
	No. of MTPs
	60
	

	7
	No. of Field days
	12
	

	8
	No. of Agric Shows
	6
	

	9
	No. of group formed
	60
	

	10
	No. of Pre-season training per year
	1
	

	11
	No. of Post-season training per year
	1
	

	12
	Extension publications to be produced (No. of Titles)
	
	

	
	Bulletins 
	3000
	

	
	Guides
	2000
	

	
	Leaflets
	2000
	

	
	Posters
	3000
	

	
	Others
	
	

	13
	Zonal Steering Committee Meeting
	3
	

	14
	Zonal Technical Committee Meeting
	2
	

	15
	Zonal REFILS workshops
	1
	

	16
	No of Extension Workers (VEAs)
	180
	

	17
	No of Extension workers (BESs)
	36
	

	18
	EA/Farmer ratio in the state
	1:4000
	


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins
	3000
	Kogi State Government

	2
	Guides

1. Improved crop production

2. Crop Disease Control

3. temperature Management in Poultry

4. PPR management in Small Ruminant
	2000

2000

2000

2000
	ACRESAL

ACRESAL

L-PRES

L-PRES

	3
	Leaflets

1. Animal Disease Control

2. Crop Disease Control
	2000

2000
	L-PRES

State Government


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1
	Production and packaging by Agricultural Programme on Radio
	94.5 FM
	Radio Kogi
	30 minutes


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 
	Production and packaging of Farmers programme on Television using Specific Categories of Crops and Animals
	NTA Channel 12
	NTA Lokoja
	30 minutes


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1

2

3
	Virtual Agronomist Training for Lead Farmers

Training of EAs and their Technical Staff

Training of Farmers


	Kogi ADP

Kogi ADP

FMA&FS
	EAs & Lead Farmers

EAs & SMS

Farmers
	Jan. 2026

March 2026

April 2026
	IITA

Kogi ADP

Kogi ADP


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	ACRESAL
	2023
	
	

	2
	VCDP
	2020
	
	

	3
	L-PRES
	2023
	
	

	4
	VIRTUAL AGRONOMIST
	2025
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Proposed to be available by Kogi State Govt

	2
	Credit
	Farmers may be discouraged due to high interest rate

	3
	Agro-chemical
	Proposed to be available by Kogi State Govt

	4
	Tractor/Animal Traction
	May be available

	5
	MTRM/QTRM situation Report 
	Proposed to be held by Kogi ADP


Name of ADP: LAGOS ADP

Postal address: Old Abeokuta Road, Oko Oba, Agege

Email:

ronketojutubi@gmail.com


                Telephone________08023201282_______________

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	11
	

	2
	FNTs
	26
	

	3
	OFARs
	8
	

	4
	No. of Farm Families
	650,000
	

	5
	No. of SPATs established 
	80
	

	6
	No. of MTPs
	12
	

	7
	No. of Field days
	80
	

	8
	No. of Agric Shows
	2
	

	9
	No. of group formed
	600
	

	10
	No. of Pre-season training per year
	1
	

	11
	No. of Post-season training per year
	1
	

	12
	Extension publications to be produced (No. of Titles)
	
	

	
	Bulletins 
	10
	

	
	Guides
	10
	

	
	Leaflets
	10
	

	
	Posters
	3
	

	
	Others
	
	

	13
	Zonal Steering Committee Meeting
	2
	

	14
	Zonal Technical Committee Meeting
	4
	

	15
	Zonal REFILS workshops
	1
	

	16
	No of Extension Workers (VEAs)
	650
	Subject to employment of more extension officers.

	17
	No of Extension workers (BESs)
	16
	

	18
	EA/Farmer ratio in the state
	1:1000
	Subject to employment of more extension officers.


B. DETAIL

S OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins

1. Improved yam minisett and seed multiplication techniques.

2. Improved housing and feeding for poultry farmers in Lagos state.

3.Post harvest handling and reduction of food losses in Lagos state,

4. Building cooperative strength for market access and inputs procurement.

5. Feed formulation and nutrition for pigs and small ruminants.


	5000

5000

5000

5000

5000
	

	2
	Guides

 1. A guide to soil testing and fertilizer application.

2.Post harvest management and handling techniques for crop farmers

3. Youth empowerment and inclusion in urban farming.

.
	2000

2000

2000
	

	3
	Leaflets

1. Steps to establish a keyhole gardening your backyard

2. Cassava stem selection and planting for high yield.

3. Fingerling selection and stocking density.

4.Sheep and Goat housing and feeding tips

5. Adding value to catfish through smoking and branding.
	2000

2000

2000

2000

2000
	


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2

3

4

5

6

7

8
	Dry season vegetable production using simple irrigation techniques

Common poultry diseases and their control

Feed formulation tips for livestock farmers

Simple technologies for small scale agro processors

Waste recycling and composting for urban farmers

Nutrition education: Eating what we grow for better health.

Preparations for rainy season farming

Farmers voices ,experiences from the field


	Weekly, Tuesday
	Radio Lagos EKO107.5FM
	30 MINS


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 

2. 

3.

4.

5.
	Urban Farming, a means to sustainable food production in Lagos state.
	Weekly
	Lagos State Television (LTV ) Channel 35 UHF
	30 Mins.


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1

2

3

4

5
	Importance of Insurance for effective Agri business

Small scale cassava processing into Garri and HQCF

Digital marketing and e-Commerce for Agro - Products

Modern extension methods for participatory approach

Disease prevention and vaccination practices in Livestock


	RID,LSADA

LSADA

LSADA

LSADA

LSADA
	Farmers,Extension agents

Women processors and farmers

Agripreneurs, farmers and extension agents

Extension agents

Extension agents, Livestock officers, Farmers
	May

June

August

September

April
	NAIC

Vet. Department of the Lagos state Min. of Agric. and Food Systems.




F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	Fruit and Vegetable drying using solar technology
	NSPRI
	To safe cost on fuel and ensure quality of dried produce.

	2
	Keyhole and vertical gardens
	IITA/FAO
	Home garden models for nutrition and climate resilience

	3
	Biosecurity and vaccination technology packages
	Vet.dep. FMA&FS
	Training on improved animal health

	4
	Climate information advisory via mobile platforms
	LSADA, NiMet, FMA&FS
	SMS alerts for weather, pest and market information


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	National Program For Food Security ( NPFS )
	2007
	TILL DATE
	Monitoring and supervisory visits to all sites by management team. Conduction of sensitization visits on loan repayment by the NPFS management .

	2
	APPEALS Project
	2017
	2023
	The Project has empowered 1,200 women and youths as well as vulnerable in the state . It has also rehabilitated 155 rural roads in the state.

	3
	LCARES ( FADAMA )
	2021
	TILL DATE
	Empowering small holders farmers and households in Lagos state with inputs and production assets.

	4
	
	
	
	

	5
	
	
	
	

	6
	
	
	
	

	7
	
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Agro input service centres now abound in the state .

	2
	Credit
	Still low as credit organizations still charge high interest and demand collateral from farmers in the state.

	3
	Agro-chemical
	As stated in fertilizer column but adulteration still persists.

	4
	Tractor/Animal Traction
	The state e – tractor booking though still low.

Animal traction is not available in the state

	5
	MTRM/QTRM situation Report 
	MTRM was held (10) times in 2025 with technical messages delivered by competent resource persons from various research institutes . The review meetings were anchored by the states team leader Dr Samuel Olanipekun from IAR&T, Ibadan. In addition, pre –MTRM which involves field visits to farms with either success stories or problems were usually embarked on in order to be abreast of the challenges faced by farmers on the farms and discussions on how to proffer solutions at the MTRM the following day. The attendance by both technical officers as well as resource persons was excellent.


Name of ADP: NASARAWA ADP

Postal address: Agyaragu Tofa Road, PMB 36, Lafia

Email: nasarawaadp@gmail.com 


Telephone: 08036216599

A. 2025 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	

	2
	FNTs
	26
	

	3
	OFARs
	10
	

	4
	No. of Farm Families
	284,000
	

	5
	No. of SPATs established 
	-
	

	6
	No. of MTPs
	376
	

	7
	No. of Field days
	2
	

	8
	No. of Agric Shows
	2
	

	9
	No. of group formed
	100
	

	10
	No. of Pre-season training per year
	1
	

	11
	No. of Post-season training per year
	1
	

	12
	Extension publications to be produced (No. of Titles)
	
	

	
	Bulletins 
	1000
	

	
	Guides
	1000
	

	
	Leaflets
	1000
	

	
	Posters
	1000
	

	
	Others
	
	

	13
	Zonal Steering Committee Meeting
	4
	

	14
	Zonal Technical Committee Meeting
	2
	

	15
	Zonal REFILS workshops
	1
	

	16
	No of Extension Workers (VEAs)
	376
	

	17
	No of Extension workers (BESs)
	47
	

	18
	EA/Farmer ratio in the state
	1:1000
	


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins


	1000


	

	2
	Guides


	1000
	

	3
	Leaflets


	1000
	


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2

3

4

5
	Wealth alternative

Mukoma Gona

Arziki na Gona

Noma Shinkafa Jari

Farmer’s World
	97.1

97.1

97.1

97.1

102.5
	NBS

NBS

NBS

NBS

Precious FM
	30 min

30 min

30 min

30 min

30 min


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 
	Noma Tushi Arziki


	97.1
	NBS
	30 min


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1

2

3
	MTRM

Preseason

Mid-season
	NADP

NADP

NADP
	SMS & EAs

EAs


	Jan-Dec

Jan-March

Jun-Sept
	VCDP or others

VCDP/Sassakawa

VCDP/Sassakawa


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	Control of post-harvest loses of Arable crops, rice, maize, cassava, cowpea and others
	NAERLS
	To reduce the risk of post-harvest

	2
	Electronic Extension, Implementation (EEP)
	NAERLS
	To cover the ratio of EAs/farmers

	3
	Strategies and way forward for  vegetable crop storage, innovation and technology.
	NAERLS
	To improve storage facility for vegetable crops.


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	Renewal of VCDP Project to cover other local government that not benefit
	2026
	5years
	To promote value chain of cassava and rice

	2
	NG-Cares to be renewed
	2026
	2years
	Improve rural farmers livelihood

	3
	Electronic Extension Platform
	2026
	5 years
	Internet extension

	4
	APPEAL Programme
	2026
	3 years
	Improve livelihood of rural farmers


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Subsidize price for farmers affordability 

	2
	Credit
	Needed in low interest rate

	3
	Agro-chemical
	Needed by satisfied agro dealer with guide, legislation against irregular marketers

	4
	Tractor/Animal Traction
	Provision of tractor hiring unit in the state

	5
	MTRM/QTRM situation Report 
	Provision of funds for sponsorship



Name of ADP: Niger State Agricultural & Mechanization Development Authority (NAMDA)

Postal address: P.M.B 132, Maitumbi, Minna, Niger State

Email:
nigeradp.namda@yahoo.com

Telephone: 08188727911 (M.D/PM)

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	With funding

	2
	FNTs
	24
	,,

	3
	OFARs
	8
	,,

	4
	No. of Farm Families
	1,097,409
	Engagement into Agricultural activities is  increasing in the state.

	5
	No. of SPATs established 
	-
	Not applicable

	6
	No. of MTPs
	15
	With funding

	7
	No. of Field days
	150
	,,

	8
	No. of Agric Shows
	6
	,,

	9
	No. of group to be formed
	497
	,,

	10
	No. of Pre-season training per year
	1
	,,

	11
	No. of Post-season training per year
	1
	,,

	12
	Extension publications to be produced (No. of Titles)
	6,000
	‘’

	
	Bulletins 
	1,500
	‘’

	
	Guides
	1,500
	,,

	
	Leaflets
	1,500
	,,

	
	Posters
	1,500
	,,

	
	Others
	
	 

	13
	Zonal Steering Committee Meeting
	4
	,,

	14
	Zonal Technical Committee Meeting
	2
	,,

	15
	Zonal REFILS workshops
	1
	,,

	16
	No of Extension Workers (VEAs)
	2,168
	Government was advised to recruit more EAs

	17
	No of Extension workers (BESs)
	46
	1BES/Block

	18
	EA/Farmer ratio in the state
	1:800
	 more EAs are required to achieve the target


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins

1. Improved methods of Bee-keeping 

2. Prevention and control of common diseases of fish in ponds. 

3. Improved methods of grain storage.

4. Soil fertility management using organic fertilizer.

5.  Principle of Fertilizer Deep Placement (FDP)
	 1,500
	NAMDA&NAERLS

	2
	Guides

1. Soybean cultivation and utilization in Niger State.

2. Good agricultural practices for maize production.

3. Good Agricultural practices for yam production.

4. Good Agricultural practices for Soybean production.

5. Uses and utilization of sesame
	 1,500
	NAMDA&NAERLS

	3
	Leaflets

1.  Processing and utilization of cassava flour.

4.  Fish feed formulation.

2 Common pest and control for rice crop. 

3 Uses and Management of Snails.

4 Improved methods of shear-butter processing. 

5 Effect of bush burning and its control.
	 1,500
	NAMDA&NAERLS

	4
	Posters

Grow more, waste less.

Climate smart farming for a greener Niger State.

Youth in Agriculture.

Protect your seed, secure your future.

Healthy animals, wealthy farmers.
	1,500
	NAMDA&NAERLS 


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2

3

4

5


	Unlocking the potentials of Aquaculture in Niger State. 

Inspiring youth and women to create wealth from Agriculture.

Modern livestock feeding and range land management

Women in Agriculture: Strengthening food security and income.

Common pest and control for maize and cowpea crops.

Formation and management of farmer based organization.
	Weekly

‘’

‘’

‘’

‘’


	Crystal F.M Minna

‘’

‘’

‘’

‘’


	25 Minutes

‘’

‘’

‘’

‘’


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1

2

3


4


	Waste to wealth: Converting farm residues into organic fertilizer.

Weed management techniques for small holder farmers.

Safe and effective use of Agro-chemicals and farm inputs.

Climate information services for farmers (Weather and Early Warning).

Poultry diseases control and vaccination schedules.
	 Weekly

‘’

‘’

‘’

‘’


	NTA, Minna

‘’

‘’

‘’

‘’
	25 minutes

‘’

‘’

‘’

‘’


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1
	Improved techniques  of male production in Tilapia.
	University of Ibadan
	To produce mainly male Tilapia species 
	March, 2026
	Improved techniques of male production in Tilapia.

	2
	Climate - Smart Agriculture
	NAMDA
	EAs and CBOs
	February,2026
	FMA&FS and NAMDA


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	Improved techniques of male production in Tilapia.
	University of Ibadan
	To produce mainly male Tilapia species 

	2
	 Certified seed production by out-growers – rice, maize, sesame and groundnut.
	NAMDA
	To supply quality seeds to farmers at subsidized rate.

	3
	  Ram fattening using crop residues
	NAMDA
	To enhance utilization of the residues and maximize profit.

	4
	Promotion of Banana/ plantain production.
	‘’
	Food security ant nutrition enhancement.


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	 Upgrading of sheep and goat
	2024
	 2 years 
	Use of exotic breed for cross- breeding.

	2
	Fish feed formulation  
	 2024
	 2 year 
	Use of processing unit house, other machines and equipment

	3
	Production and processing of Zinc pearl millet.
	 2024
	 2 years
	Improving nutritional status of the farmers.

	4
	 Control of insects and premature fruit droppings on tree crops.
	2024
	2 years 
	Use of broad spectrum systemic insecticides and other Agro-forestry management practices.

	5
	Improved local chicken production using Sussex. 
	  2024
	  2 years
	Enhance protein production.

	6
	IFAD/ SEDI Project
	2024
	  2 years
	Promotion of vitamin A consumption.

	7
	 Upgrading of sheep and goat
	2024
	 2 years 
	Use of exotic breed for cross- breeding.


H. GENERAL: BRIEF REMARKS ON:

	SN
	                                       Input situation

	1
	Fertilizer
	Government to ensure timely distribution of fertilizer to farmers before the on-set of rain .

	2
	Credit
	Farmers will be linked to the financial institutions and other credit facilities e.g Niger Foods, One Acre Fund etc.

	3
	Agro-chemical
	Farmers will be sensitized on how to identify fake inputs and how to get quality inputs.

	4
	Tractor/Animal Traction
	State Government to procure more tractors, power tillers and other processing machines for hiring services. 

	5
	MTRM/QTRM situation Report 
	With funding, all the MTRMs will be conducted .


[image: image76.jpg]


                                                                                                                          [image: image77.png]



Name of ADP: OGUN STATE AGRICULTURAL DEVELOPMENT PROGRAMME 

Postal address: OLABISI ONABANJO WAY, IDI-ABA, P.M.B 2122 ABEOKUTA

Email:
ogunadp@gmail.com

Telephone: - 08139714266

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	10
	

	2
	FNTs
	24
	

	 3
	OFARs
	3
	

	4
	No. of Farm Families
	360,000
	

	5
	No. of SPATs established 
	
	

	6
	No. of MTPs
	400
	

	7
	No. of Field days
	20
	

	8
	No. of Agric Shows
	2
	

	9
	No. of group to be formed
	200
	

	10
	No. of Pre-season training per year
	1
	

	11
	No. of Post-season training per year
	2
	

	12
	Extension publications to be produced (No. of Titles)
	
	

	
	Bulletins 
	500
	

	
	Guides
	500
	

	
	Leaflets
	500
	

	
	Posters
	100
	

	
	Others
	
	

	13
	Zonal Steering Committee Meeting
	2
	

	14
	Zonal Technical Committee Meeting
	2
	

	15
	Zonal REFILS workshops
	1
	

	16
	No of Extension Workers (VEAs/BEAs)
	69
	

	17
	No of Extension workers (BESs)
	20
	

	18
	EA/Farmer ratio in the state
	1:5,217
	


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins

1. Messages on crop production

2. Messages on Animal production

3. Messages on Fish production

4. Tree crops Production

5. Backyard farming

6. Cassava Agroforestry.


	500
	

	2
	Guides

1. Climate smart Agriculture

2. Value addition to Agricultural products

3. waste management

4. Precision farming

5. Organic farming


	500
	

	3
	Leaflets

1. Bio-security in animal production

2. Safe use of Agrochemical

3. Information on banned chemicals
	500
	


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2
	Topics addressing the current agricultural situations
	Weekly
	OGBC
	15min


D. TELEVISION PROGRAMMES TO BE PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 
	Topics addressing the current agricultural situations
	Weekly
	OGTV
	30min


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees expected
	Proposed period/time
	Collaborators 

	1
	Training Need Analysis & Training Programme
	ARMTI – Ilorin
	Oficers in Research and Training/ Technical services
	May 2026
	

	2
	Organization and Management of Rural Cooperatives for Poverty Alleviation
	ARMTI – Ilorin
	RID officers
	June 2026
	

	3
	Training Presentation Method and Evaluation Skills
	ARMTI – Ilorin
	EXT/Tech.services/R&T
	June 2026
	

	5
	Mainstreaming Gender and Vulnerable Groups into Development Programme
	ARMTI – Ilorin
	EXT/Tech.services/R&T
	June 2026
	

	6
	Agoforestary Extension Management for Sustainable Agricultural Production
	ARMTI – Ilorin
	EXT/Tech.services/R&T
	July 2026
	

	7
	GAP in crop production
	
	Farmers
	Jan- Dec.2026
	

	8
	Pre- season training
	Ogun ADP
	Extension Officers
	March/April 2026
	

	9
	Monthly Training
	Ogun ADP
	Extension Officers
	Jan – Dec.2026
	

	10
	Cassava Agroforestry 
	Ogun ADP
	Extension officers
	March/April 2026
	GIZ/SASAKAWA


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	Sole cassava production using AKILIMO tool
	IITA
	

	2
	Maize/cassava intercrop using AKILIMO tool
	IITA
	

	3
	SAWAH rice production technique for seed
	NCAM
	

	4
	Bio Security in Livestock Production
	IAR&T
	

	5
	Early detection of disease in cassava and control using NURU app.
	WAVE
	

	6
	Sesame production and utilization
	IAR&T
	

	7
	Dry season vegetable farming under irrigation
	NIHORT
	

	8
	Market oriented Agricultural extension system using SHEP approach
	JICA/FMAFS
	

	9
	Improve productivity in crops using Farm Advice app
	Zero Hunger
	

	10
	Cassava Agroforestry 
	GIZ/ Sasakawa
	

	11
	Digital advisory services to farmers
	OGFIMS/IITA
	

	12
	Soybean production and utilization
	IAR&T
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	Value Chain Development Programme ) VCDP
	2015
	Will end in 2026
	Ongoing with Cassava and Rice Value Chain and Nutrition

	3
	NIGERIA COVID-19 ACTION RECOVERY AND 

ECONOMIC STIMULUS PROGRAM- NIGERIA CARES

(OG-CARES)
	2021
	Under extension
	Efforts to mitigate the impacts of COVID19 pandemic on the livelihoods of poor and vulnerable households and micro enterprises in the country

	4
	Smallholders Horticultural Empowerment Promotion ( SHEP)20
	2022
	Streamlined into the ADP workplan
	Promotion of Market Oriented Agricultural Extension System for Livelihood Improvement in Nigeria

	5
	ZERO HUNGER
	2021
	
	Good Agricultural practices in crop production and processing 

	6
	Ogun State Economic Transformation Project
	2021
	5 years
	Improving business enabling environment, strengthening agri-food value chain and upgrading skills.

	7
	Special Agro-Indrustrial Processing Zone( SAPZ)
	2024
	Up to 2026
	Increase Agricultural Productivity, promote agribusiness, and improve food security


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Public Private Partnership ( PPP)

	2
	Credit
	Facilitate Linkages of farmers with credit sources

	3
	Agro-chemical
	Public Private Partnership (PPP)

	4
	Tractor
	Public Private Partnership (PPP)

	5
	MTRM/QTRM situation Report 
	Facilitate support from projects domicile in the ADP


                                       

Name of ADP: Ondo State Agricultural Development Project

Postal address: 88, Obafemi Awolowo Avenue, Alagbaka, Akure.

Email: ondostateadp@yahoo.com
Tel:08032499486


                

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	

	2
	FNTs
	24
	

	3
	OFARs
	8
	

	4
	No. of Farm Families
	180,000
	

	5
	No. of SPATs established 
	100
	

	6
	No. of MTPs
	3
	

	7
	No. of Field days
	6
	

	8
	No. of Agric Shows
	2
	

	9
	No. of group formed
	450
	

	10
	No. of Pre-season training per year
	2
	

	11
	No. of Post-season training per year
	2
	

	12
	Extension publications to be produced (No. of Titles)
	Various
	Extension field diaries, Extension Leaflets/Guides, News bulletin, Farmers Calendar

	
	Bulletins 
	5000
	

	
	Guides
	3000
	

	
	Leaflets
	18000
	

	
	Posters
	1800
	

	
	Others: Animated Videos
	
	

	13
	Zonal Steering Committee Meeting
	4
	To be organized by IAR&T, Ibadan & attended by ADP

	14
	Zonal Technical Committee Meeting
	1
	To be organized by IAR&T, Ibadan & attended by ADP

	15
	Zonal REFILS workshops
	1
	To be organized by IAR&T, Ibadan & attended by ADP

	16
	No of Extension Workers (VEAs)
	144
	Government to recruit more staff

	17
	No of Extension workers (BESs)
	18
	Government to recruit more staff

	18
	EA/Farmer ratio in the state
	1:1000
	


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins
	5000
	

	2
	Guides
	3000
	

	3
	Leaflets

1. Plantain Production

2. Oil Palm Production

3. Cocoa Production

4. Cassava Production

5. Maize Production

6. Cassava/Maize Production

7. Lowland Rice Production

8. Poultry Production

9. Fish Production


	2,000

2,000

2,000

2,000

2,000

2,000

2,000

2,000

2,000
	We are expecting and looking forward for collaborators


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2


	Kaje Kayo Radio Programme

Jingle Production


	Once/Week

4 Slots/Week
	Ondo State

Orange FM 94.5

OSRC 96.5

Radio
	 36

1 Minute


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 

2.

3.
	Obalagbe Technology Transfer Programme

Documentary on ADP Activities

Jingle Production (English & Yoruba)
	Weekly

One/Year

4 Slots/ Week
	OSRC Television

- OSRC Television

- NTA, Akure

- OSRC Television

- NTA, Akure


	30

Minutes

30 Minutes

1-2 Minutes


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1

2.

3

4
	Pre- season 

FFBS

FFS

Organic Way of Controlling Weeds/Preparation of Organic Fertilizer
	ADP

FAO GEF7 FOLUR-IP

L-Press

SPAC/ACTION AID
	EAs

Farmers

Livestock Farmers

Women Groups
	March -April 

Jan -Dec

Feb-Dec

May-Oct
	FAO GEF7 FOLUR-IP

ADP

ADP

ADP


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	Organic Way of Controlling Weeds/Preparation of Organic Fertilizers
	SPAC/Action AID Nigeria
	 

	2
	Yam Mini Sett Techniques
	Ondo ADP
	

	3
	Rapid Multiplication of Plantain Suckers
	Ondo ADP
	

	4
	Soya Bean Utilization
	Ondo ADP
	

	5
	Populirization of Onion Production
	Ondo ADP
	 

	6
	Populirization of Tomatoes Production
	Ondo ADP
	

	
	
	
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	FAO GEF7 FOLUR-IP
	March 2024


	On-going 
	 Development of Integrated land scape management, Training of Farmers on Climate Smart Agriculture(CSA) on Sustainable Cocoa and Oil Palm Value Chain ,Restoration of Degraded Forest Eco-System and Polygon Mapping on EURD Compliance.



	2
	L-PRES
	Preparatory Stage was 2020.Officially was 2022.


	6 years 


	 Training of Farmers on Poultry ,Pigs ,Goat & Sheep through Farmer Field School (FFS). This Value Chain also includes :Producers ,Marketers & Processors. We also offer capacity Building in the Three Value Chains, We assist Farmers in the Three Senatorial  District in the Construction of Veterinary Clinics for the treatment of farm animals. We also help the farmers in the construction of Livestock market in the state.



	3
	IFAD LIFE-ND
	Phase 1 from:2020

Phase 2 from:2025


	5 years

3 years


	Livelihood Improvement Family Enterprise Project in the Niger Delta (LIFE-ND) is being implemented in the nine (9) Niger-Delta States. The project enhances income, food security and job creation for rural youths and women through agribusiness development on a sustainable basis. The first set of beneficiaries; known as Incubatee (coordinated by an incubator) have been selected & trained on their chosen enterprises and empowered by the project. No of beneficiaries engaged is 4,563 and the number empowered is

4,283



	4
	WAVE
	2024
	Ongoing
	To detect Cassava Mosaic Disease (CMD) and Cassava Brown Streak Disease (CBSD).

	5
	SPAC/ACTION AID NIGERIA

	2023
	3 years
	The mandate of the programme is to improve food and nutrition security and enhance agroecological skills of 120,000 smallholder women farmers and young people by facilitating access to early maturing seeds, seedlings, livestock and poultry, thus supporting agroecological practices, indigenous seeds and agrobiodiversity preservation for increased farm yields.

	6
	FADAMA CARES (N-CARES)

PROGRAMME


	2021
	On-going
	The programme addresses food security and challenges in food supply chains in Nigeria and also mitigates the effect of COVID-19 in Nigeria in order to protect livelihood & food security of poor & vulnerable families. Activities include provision of inputs for crop & livestock farmers, construction of feeder roads, aggregation centres & processing centres for value addition e.t.c. 

The programme is gradually coming to a close.



	7
	TRACE
	2022
	5 years
	To build the capacity of farmers through trainings. Linkage of Farmers with exporters. Empowerment of farmers with cocoa seedlings. Training of extension agent on the usage of “Corus 3D App”.




H. GENERAL: BRIEF REMARKS ON:

	S/N
	   Input situation

	1
	Fertilizer
	Ondo State Government shall continue the procurement and distribution of fertilizer in year 2026 in collaboration with FMA&FS

	2
	Credit
	Ondo State Government shall continue the provision of credit to farmers under the Finance and Marketing Dept. of the Ministry of Agriculture and Forestry in year 2026. Similarly, the ADP shall continue to link farmers to sources of credit.

	3
	Agro-chemical
	Ondo State Government shall continue the procurement and distribution of Agro-chemicals in year 2026 through Agricultural Inputs Supply Agency (AISA)

	4
	Tractor
	Inadequate number of tractors to farmers in the state 

Maintenance of the existing number of tractors, Power tillers and Tricycles shall be ensured.



	5
	MTRM Report 
	The meeting was held in year 2025 twice due to lack of fund; we shall push further to hold the meeting in year 2026 as at when due.


Name of ADP: Osun State ADP

Postal address: P.O Box 724, Iwo, Osun State.

Email:




                Telephone_08033798881______________________

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	

	2
	FNTs
	26
	

	3
	OFARs
	6
	

	4
	No. of Farm Families
	256
	

	5
	No. of SPATs established 
	800
	

	6
	No. of MTPs
	80
	

	7
	No. of Field days
	30
	

	8
	No. of Agric Shows
	5
	

	9
	No. of group formed
	150
	

	10
	No. of Pre-season training per year
	1
	

	11
	No. of Post-season training per year
	1
	

	12
	Extension publications to be produced (No. of Titles)
	
	

	
	Bulletins 
	20000
	

	
	Guides
	15000
	

	
	Leaflets
	5000
	

	
	Posters
	6000
	

	
	Others
	3000
	

	13
	Zonal Steering Committee Meeting
	1
	

	14
	Zonal Technical Committee Meeting
	1
	

	15
	Zonal REFILS workshops
	1
	

	16
	No of Extension Workers (VEAs)
	240
	

	17
	No of Extension workers (BESs)
	30
	

	18
	EA/Farmer ratio in the state
	1:7000
	


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins

1. Farming operations calendar 
	6000
	ADP

	2
	Guides

1. GAP in cocoa productions

2.Practical guides on Cassava Brown Streak Disease (CBSD)

3.Good Methods of grain processing 
	15,000

15,000

6,000
	Trace/ADP

WAVE/ADP 

ADP

	3
	Leaflets

1. Farm sanitation 

2.Soil management practices

3.Proper ways of spraying your farm.
	5000

5000

4000
	ADP

ADP

ADP


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1
	AGBELOBA 
	Weekly 
	OSBC 104.5
	30Mins


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 
	EREAGBE 
	Weekly 
	OSBC TV 
	30 Mins.


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1

2

3

4

5
	Pre -season training 

Post -season training 


	ADP 

ADP 
	EAS

SMS

BES

ZEO
	March 2026

Nov. 2026
	Research institutions.

Research institutions.


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	Bora Maize 
	AIR&T
	Resistant to Fall Army Worms.


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	SHEP
	2021
	10 yrs
	Market orientated promotion.

	2
	TRACE on Cocoa.
	2022
	5 yrs
	GAP in Cocoa Production to enhance good money.


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	Procurement of 4000tons NPK plus 5000tons of Urea.

	2
	Credit
	

	3
	Agro-chemical
	Procurement of15,000 litres of herbicides, 5,000 insecticides 

	4
	Tractor/Animal Traction
	

	5
	MTRM/QTRM situation Report 
	


Name of ADP: PLATEAU 

Postal address: 

Email:




                Telephone_______________________

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	Lack of funds

	2
	FNTs
	78
	Holidays Lack of funds

	3
	OFARs
	5
	Lack of funds

	4
	No. of Farm Families
	4,942,10
	Ongoing

	5
	No. of SPATs established 
	NA
	

	6
	No. of MTPs
	370
	

	7
	No. of Field days
	40
	Ongoing

	8
	No. of Agric Shows
	NIL
	

	9
	No. of group formed
	1000
	Ongoing

	10
	No. of Pre-season training per year
	3
	Lack of funds

	11
	No. of Post-season training per year
	3
	Lack of funds

	12
	Extension publications to be produced (No. of Titles)
	
	

	
	Bulletins 
	NIL
	

	
	Guides
	NIL
	

	
	Leaflets
	NIL
	

	
	Posters
	NIL
	

	
	Others Extension Field Dairies 
	1000
	Ongoing  

	13
	Zonal Steering Committee Meeting
	4
	

	14
	Zonal Technical Committee Meeting
	4
	

	15
	Zonal REFILS workshops
	1
	

	16
	No of Extension Workers (VEAs)
	1200
	Retirement 

	17
	No of Extension workers (BESs)
	90
	Ongoing 

	18
	EA/Farmer ratio in the state
	1:800
	Lack of Man Power 


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins

Wheat Production 


	1000

1000
	PADP

Ongoing 

	2
	Guides

1. Doing good business with quality potato 

2. Farms Financial Cycle 


	1000

700
	GIZ

GIZ

	3
	Leaflets


	
	


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2
	Explaning avenue to fence building through Agricultural Potato Production 


	Once weekly once weekly 
	J.FM

PRTVC
	45 Minute 

45 Minute


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 
	Home Garden 
	Once Weekly 
	PRTVC
	1 Hour 


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1

2


	Seed Potato Production 

General Crop Production
	TETFUND

MAFS
	Youth 

Youth
	80

230
	PADP

PAPD


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	Demo on East West Seed (Tomato, Okro, 
	
	Adaptable 

	2
	
	Zaria Shika
	

	3
	Oil Palm, Coconut 
	PADP
	Ongoing 

	4
	Use of Simter Organic Fertilizer 
	Simter Concept 
	Ongoing


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	National Refugee Council 
	2021
	Ongoing
	Traning, distribution of inputs to refugees 

	2
	Seed Co
	2016
	Ongoing
	Demonstration on maize 

	3
	CIP International Potato Centre 
	2021
	Ongoing
	Demonstration on potatoes

	4
	G1Z
	2016
	Ongoing
	New technologies 

	5
	Gospel Health Centre 
	
	Ongoing
	Input and technology empowerment 


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	MAFS/Plateau Government 

	2
	Credit
	NIL 

	3
	Agro-chemical
	Large Quantity Distribution 

	4
	Tractor/Animal Traction
	200 Tractors subsidies farming, school programmes

	5
	MTRM/QTRM situation Report 
	Nil


Name of ADP: RIVERS STATE ADP 

Postal address: 

Email:




                Telephone_____________08064237227__________

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	60
	

	2
	FNTs
	105
	

	3
	OFARs
	1,000,000
	

	4
	No. of Farm Families
	118
	

	5
	No. of SPATs established 
	72
	

	6
	No. of MTPs
	112
	

	7
	No. of Field days
	10
	

	8
	No. of Agric Shows
	64
	

	9
	No. of group formed
	62
	

	10
	No. of Pre-season training per year
	30
	

	11
	No. of Post-season training per year
	48
	

	12
	Extension publications to be produced (No. of Titles)
	56
	

	
	Bulletins 
	24
	

	
	Guides
	6
	

	
	Leaflets
	52
	

	
	Posters
	90
	

	
	Others
	NIL
	

	13
	Zonal Steering Committee Meeting
	24
	

	14
	Zonal Technical Committee Meeting
	24
	

	15
	Zonal REFILS workshops
	12
	

	16
	No of Extension Workers (VEAs)
	50
	

	17
	No of Extension workers (BESs)
	32
	

	18
	EA/Farmer ratio in the state
	1:5000
	


Name of ADP: SOKOTO 

Postal address: 

Email:




                Telephone_______________________

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	Lack of funds

	2
	FNTs
	78
	Holidays Lack of funds

	3
	OFARs
	5
	Lack of funds

	4
	No. of Farm Families
	4,942,10
	Ongoing

	5
	No. of SPATs established 
	NA
	

	6
	No. of MTPs
	370
	

	7
	No. of Field days
	40
	Ongoing

	8
	No. of Agric Shows
	NIL
	

	9
	No. of group formed
	1000
	Ongoing

	10
	No. of Pre-season training per year
	3
	Lack of funds

	11
	No. of Post-season training per year
	3
	Lack of funds

	12
	Extension publications to be produced (No. of Titles)
	
	

	
	Bulletins 
	NIL
	

	
	Guides
	NIL
	

	
	Leaflets
	NIL
	

	
	Posters
	NIL
	

	
	Others Extension Field Dairies 
	1000
	Ongoing  

	13
	Zonal Steering Committee Meeting
	4
	

	14
	Zonal Technical Committee Meeting
	4
	

	15
	Zonal REFILS workshops
	1
	

	16
	No of Extension Workers (VEAs)
	1200
	Retirement 

	17
	No of Extension workers (BESs)
	90
	Ongoing 

	18
	EA/Farmer ratio in the state
	1:800
	Lack of Man Power 


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins

1. 

2. Wheat Production 

3.

4.

5.


	1000

1000
	PADP

Ongoing 

	2
	Guides

1. Doing good business with quality potato 

2. Farms Financial Cycle 
	1000

700
	GIZ

GIZ


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2
	Explaning avenue to fence building through Agricultural Potato Production 
	Once weekly once weekly 
	J.FM

PRTVC
	45 Minute 

45 Minute


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 
	Home Garden 
	Once Weekly 
	PRTVC
	1 Hour 


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1

2
	Seed Potato Production 

General Crop Production
	TETFUND

MAFS
	Youth 

Youth
	80

230
	PADP

PAPD


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	Demo on East West Seed (Tomato, Okro, 
	
	Adaptable 

	2
	
	Zaria Shika
	

	3
	Oil Palm, Coconut 
	PADP
	Ongoing 

	4
	Use of Simter Organic Fertilizer 
	Simter Concept 
	Ongoing


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	National Refugee Council 
	2021
	Ongoing
	Traning, distribution of inputs to refugees 

	2
	Seed Co
	2016
	Ongoing
	Demonstration on maize 

	3
	CIP International Potato Centre 
	2021
	Ongoing
	Demonstration on potatoes

	4
	G1Z
	2016
	Ongoing
	New technologies 

	5
	Gospel Health Centre 
	
	Ongoing
	Input and technology empowerment 

	6
	
	
	
	

	7
	
	
	
	


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	MAFS/Plateau Government 

	2
	Credit
	NIL 

	3
	Agro-chemical
	Large Quantity Distribution 

	4
	Tractor/Animal Traction
	200 Tractors subsidies farming, school programmes

	5
	MTRM/QTRM situation Report 
	Nil




Name of ADP: 
TARABA 

Postal address: 
P.M.B 1037

Email: robiayoila6@gmail.com

Telephone_________________

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	

	2
	FNTs
	24
	

	3
	OFARs
	10
	

	4
	No. of Farm Families
	288,000
	

	5
	No. of SPATs established 
	-
	

	6
	No. of MTPs
	40
	

	7
	No. of Field days
	6
	

	8
	No. of Agric Shows
	2
	

	9
	No. of group formed
	50
	

	10
	No. of Pre-season training per year
	2
	

	11
	No. of Post-season training per year
	2
	

	12
	Extension publications to be produced (No. of Titles)
	Open 
	

	
	Bulletins 
	Open
	

	
	Guides
	Open 
	

	
	Leaflets
	Open 
	

	
	Posters
	Open
	

	
	Others
	Open
	

	13
	Zonal Steering Committee Meeting
	4
	

	14
	Zonal Technical Committee Meeting
	2
	

	15
	Zonal REFILS workshops
	1
	

	16
	No of Extension Workers (VEAs)
	288
	

	17
	No of Extension workers (BESs)
	30
	

	18
	EA/Farmer ratio in the state
	1:1000
	


B. DETAILS OF EXTENSION PUBLICATIONS TO BE PRODUCED 

	SN
	Title
	Target Copies
	Collaborators

	1
	Bulletins


	Open
	

	2
	Guides


	Open
	

	3
	Leaflets


	Open
	


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1
	NA DUKE TSOHON CINIKI: 

Good Agronomic Practices (GAP). (Ingantattun Hanyoyin Noma).
	Forth nightly 
	TSBS 
	1 hour 

	2
	Post-harvest handling (Kula da amfanin gona bayan girbi.)
	
	
	


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1
	Communication & Extension Methodology
	TADP
	Extension agent 
	
	TADP

	2
	Value additional processing training 
	TADP
	Extension agent/ lead farmer
	
	TADP

	3
	Climate change adaptation and mitigation 
	TADP
	VEA/Lead farmers
	
	TADP 


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	Food processing technology 
	TADP 
	

	2
	Precision And agriculture technology 
	TADP
	


 EMBED CorelDraw.Graphic.11 
[image: image78.emf]

Name of ADP: Yobe State Agricultural Deveoplemt Programme 

Postal address:  1038 Damaturu

Email:
yosadp32@gmail.com                 Telephone__08036228959_

A. 2026 EXTENSION SUPPORT INDICATORS 

	SN
	
SUPPORT ACTIVITIES
	TARGET
	REMARKS

	1
	MTRMs
	12
	

	2
	FNTs
	24
	

	3
	OFARs
	32
	

	4
	No. of Farm Families
	593,288
	

	5
	No. of SPATs established 
	32
	

	6
	No. of MTPs
	64
	

	7
	No. of Field days
	2
	

	8
	No. of Agric Shows
	2
	

	9
	No. of group formed
	700
	

	10
	No. of Pre-season training per year
	2
	

	11
	No. of Post-season training per year
	2
	

	12
	Extension publications to be produced (No. of Titles)
	
	

	
	Bulletins 
	500
	

	
	Guides
	500
	

	
	Leaflets
	500
	

	
	Posters
	500
	

	
	Others
	
	

	13
	Zonal Steering Committee Meeting
	4
	

	14
	Zonal Technical Committee Meeting
	2
	

	15
	Zonal REFILS workshops
	1
	

	16
	No of Extension Workers (VEAs)
	540
	

	17
	No of Extension workers (BESs)
	50
	

	18
	EA/Farmer ratio in the state
	1:1000
	


C: RADIO PROGRAMMES TO BE PRODUCED AND AIRED 

	SN
	Programme Title/Topics
	Frequency to be aired 
	Broadcasting stations
	Duration

	1

2
	Zauran Manoma

Mukoma Gona
	FM

FM
	YBC

YBC
	2 hours

2 hours 


D. TELEVISION PROGRAMMES PRODUCED AND AIRED  

	SN
	Programme Title/Topics
	Frequency to be aired
	Broadcasting station
	Duration

	1. 
	From the field
	
	YTV
	2 hours 


E. TRAINING PROGRAMMES

	SN
	Title
	Organizers
	Categories of Trainees
	Proposed period/time
	Collaborators 

	1

2


	Training of Women on Food processing

Training on Making of plant extract as insecticide  
	ADP 

ADP
	EA’s

EA’s
	Jan-June

May-July 
	


F. TECHNOLOGIES TO BE PROMOTED

	SN
	Title
	Source 
	Comment

	1
	The use and maintenance of power tillers
	ADP
	

	2
	The application & usage of fertilizer sprayers 
	ADP
	

	3
	Effective methods of chemical spraying in the field 
	ADP
	


G: SPECIAL PROJECTS:

	SN
	PROJECT NAME
	YEAR STARTED
	DURATION OF PROJECT
	KEY ACTIVITIES

	1
	IFAD Project 
	2025
	5 years
	Value chain development 

	2
	Integrated agricultural development project
	2025
	10 years
	Production & processing 

	3
	Larva Project
	2024
	8 years
	Irrigation development 


H. GENERAL: BRIEF REMARKS ON:

	SN
	Input situation

	1
	Fertilizer
	200 trucks will be procured 

	2
	Credit
	

	3
	Agro-chemical
	5000 litres will be procured 

	4
	Tractor/Animal Traction
	Additional tractors will be purchased 

	5
	MTRM/QTRM situation Report 
	MTRM training will be support 


08063607788





08063607788










_1234567890.unknown

